## Sheet1
Serial Number | SR Name | High Level Status | Low Level Status | Access Vendor | TCO/BAU Vendor | CW Status | TRS Vendor | TRS Status | TRS Sol'n | Target RFTI | Actual RFTI | Lapse (days) | TRS Plan | TRS Actual | ODC | Province | City/Town | Sales Area | Vanguard/Prio Site | Program | 263 List / PLAN (In-Year) | Target Month (TRFS Plan) | Target Quarter (TRFS Plan) | Actual Month (TRFS) | Actual Quarter (TRFS) | Detailed Status | Integration Remarks | TRS Remarks | Latitude | Longitude | Solution Type | Q3 Sprint Target
NS-BIZ22-C14 | BrgyDoroluman_Arakan_Cotabato (North Cotabato) | Awarded | 18. RTB for Mobilization | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (01) Precon/ Eng'g Hold | MW | 2026-03-13 | 2026-02-22 | 139 | 2026-02-14 | 2026-10-30 | 2026-08-05 | COTABATO | ARAKAN | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/05: Integration complete | 7/02: FOC splicing ongoing | 7.2158 | 124.8178 | MW | 33
NS-NTG23-E38 | Holcim_BrgyIlang_EM_01 | TSSR | 30. RFI/TRS Ready | HT | HT | 19. Site Clearing | JISEDAI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-10-15 | 2026-04-12 | 139 | 2026-08-03 | 2026-04-23 | 2026-08-18 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | Small Cell | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 7.2091 | 125.4365 | Fiber Extension | 33
NS-TER24-E565 | Brgy.SanVicente02_PanaboCity_DavaoDelNorte | For Awarding | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 18. RTB for Mobilization | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-06-24 | 2026-05-23 | 39 | 2026-04-21 | 2026-06-22 | 2026-02-22 | DAVAO DEL NORTE | PANABO CITY | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 7.4325 | 125.779 | AN + LEOSAT | 24
NS-BIZ22-C29 | BrgyLa Esperanza_Tulunan_Cotabato (North Cotabato) | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 19. Site Clearing | HT | (02) Survey | MW/FSO | 2026-01-23 | 2026-08-24 | 137 | 2026-03-05 | 2026-07-13 | 2026-02-10 | COTABATO | TULUNAN | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 7.164 | 124.8057 | MW/FSO | 25
NS-TER24-E566 | Brgy.Quezon_PanaboCity_DavaoDelNorte | LGU Permitting | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 18. RTB for Mobilization | HT | (06) RTB (FOC/AN/Pending) | MW | 2026-12-27 | 2026-02-05 | 11 | 2026-12-05 | 2026-04-27 | 2026-05-29 | DAVAO DEL NORTE | PANABO CITY | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 5/20: LOS check passed | 7.4772 | 125.7723 | MW | 25
NS-NTG23-Q31 | BrgyMankilam02_TagumCity_DDN | For Awarding | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 18. RTB for Mobilization | ZTE | (05) Permitting | MW/FSO | 2026-08-21 | 2026-11-22 | 93 | 2026-03-25 | 2026-07-09 | 2026-07-01 | DAVAO DEL NORTE | TAGUM CITY (CAPITAL) | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 12/10: no pole yet | 7.4389 | 125.7942 | MW/FSO | 25
NS-TER24-F130 | Brgy.Batiocan_Libungan_NorthCotabato | TRS Ready | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | ZTE | (06) RTB (FOC/AN/Pending) | MW | 2026-10-01 | 2026-05-06 | 41 | 2026-08-25 | 2026-07-14 | 2026-05-19 | COTABATO | LIBUNGAN | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 7.1836 | 124.813 | MW | 33
NS-TER24-A133 | Brgy.Conel02_GeneralSantosCity_SouthCotabato | TRFS | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | HT | (00) Not Started | MW | 2026-01-17 | 2026-06-11 | 102 | 2026-05-18 | 2026-02-03 | 2026-04-19 | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Unassigned | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | JUN | Q2 | (02) Ongoing Survey | 6/18: Permanent Po | 12/10: no pole yet | 6.1247 | 125.0093 | MW | 27
NS-BIZ18-D21 | Brgy.Buhangin(Pob.)01_DavaoCity_DavaoDelSur | LGU Permitting | 32. Ongoing Integration | HT | FRONTIER | 20. Excavation | COMTEL | (05) Permitting | AN + LEOSAT | 2026-03-15 | 2026-05-16 | 35 | 2026-05-07 | 2026-10-15 | 2026-10-03 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 6/15: MW dish installed | 7.1528 | 125.429 | AN + LEOSAT | 27
NS-NTG19-AG57 | Brgy.Buhangin(Pob.)03_DavaoCity_DavaoDelSur | s-RFI & TRS Ready | 28. sRFI/TRS Ready | HT | HT | 24. Backfilling | FADI | (02) Survey | MW | 2026-03-12 | 2026-09-18 | 126 | 2026-02-16 | 2026-01-25 | 2026-02-26 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | Macro | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 01 Precon/ Eng'g Hold | 7.174 | 125.4219 | MW | 23
NS-NTG23-D61 | Brgy.UpperLabay_GeneralSantosCity_SouthCotabato | RTB'd | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-07-17 | 2026-07-15 | 119 | 2026-09-28 | 2026-05-09 | 2026-10-11 | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 06 RTB (FOC/ AN/ ... | 6.1442 | 125.018 | Fiber Extension | 27
NS-NTG23-E29 | Brgy.Labu-o_PresidentRoxas_NorthCotabato | RTB'd | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | na | (02) Survey | MW/FSO | 2026-02-27 | 2026-05-31 | 111 | 2026-03-22 | 2026-08-21 | 2026-01-02 | COTABATO | PRESIDENT ROXAS | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/20: RfId site 7/15 | 10/17: Pending site | 7.1918 | 124.7991 | MW/FSO | 33
NS-BIZ22-B66 | BrgySisiman_Lutayan_Sultan Kudarat | TRFS | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 24. Backfilling | TBD | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-11-17 | 2026-06-02 | 129 | 2026-11-08 | 2026-04-12 | 2026-03-20 | SULTAN KUDARAT | LUTAYAN | Unassigned | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAY | Q2 | (03) PSH | 6/28: For MOS. Pull | 06 RTB (FOC/ AN/ ... | 7.8829 | 123.9673 | Fiber Extension | 25
NS-TER24-F128 | Brgy.Bual02_Tulunan_NorthCotabato | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 24. Backfilling | na | (00) Not Started | MW/FSO | 2026-09-08 | 2026-01-10 | 28 | 2026-07-05 | 2026-06-07 | 2026-05-03 | COTABATO | TULUNAN | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 5/20: LOS check passed | 7.2035 | 124.7748 | MW/FSO | 27
NS-TER24-E979 | Brgy.Mabay02_Maitum_Sarangani | TRS Ready | 28. sRFI/TRS Ready | NOKIA | PHILTOWER | 24. Backfilling | ZTE | (00) Not Started | AN + LEOSAT | 2026-02-05 | 2026-09-30 | 32 | 2026-03-07 | 2026-12-04 | 2026-09-01 | SARANGANI | MAITUM | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/30: Fiber link verified | 6/15: MW dish installed | 7.9008 | 123.9896 | AN + LEOSAT | 24
NS-TER24-D988 | Brgy.Elian_DatuSaudi-Ampatuan_Maguindanao | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 22. Rebar Installation | na | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-19 | 2026-10-04 | 51 | 2026-06-09 | 2026-07-24 | 2026-12-10 | MAGUINDANAO | DATU SAUDI-AMPATUAN | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 6/24: for checking | 7.8657 | 123.9811 | AN + LEOSAT | 24
NS-TER24-E536 | Brgy.SanVicente_Asuncion(Saug)_DavaoDelNorte | RTB'd | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 23. Concrete Pouring | na | (05) Permitting | Fiber Extension | 2026-05-07 | 2026-04-26 | 16 | 2026-06-23 | 2026-01-11 | 2026-10-29 | DAVAO DEL NORTE | ASUNCION (SAUG) | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 6/24: for checking | 7.4472 | 125.7781 | Fiber Extension | 25
NS-TER24-F51 | Brgy.Katubao_Kiamba_Sarangani | For Awarding | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (00) Not Started | Fiber Extension | 2026-12-29 | 2026-11-20 | 15 | 2026-04-28 | 2026-02-04 | 2026-01-17 | SARANGANI | KIAMBA | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 9/19: Awaiting tower | 7.8515 | 123.9649 | Fiber Extension | 27
NS-NTG20-AT52 | 2020CapSite_BrgyGang_SULTANKUDARAT(NULING)_MGDN | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (02) Survey | AN + LEOSAT | 2026-04-20 | 2026-10-04 | 33 | 2026-10-20 | 2026-10-23 | 2026-08-31 | MAGUINDANAO | SULTAN KUDARAT (NULING) | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 7.8902 | 124.0134 | AN + LEOSAT | 33
NS-TER24-A109 | Brgy.Edwards(Pob.)_T'Boli_SouthCotabato | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | UNITY | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-19 | 2026-12-04 | 110 | 2026-07-01 | 2026-08-05 | 2026-07-30 | SOUTH COTABATO | T'BOLI | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 6/24: for checking | 6.0836 | 125.0208 | Fiber Extension | 33
NS-TER24-A546 | Brgy.Magtuod_DavaoCity_DavaoDelSur | For Awarding | 28. sRFI/TRS Ready | HT | FRONTIER | 26. ODU Pad / Electrical | ZTE | (00) Not Started | AN + LEOSAT | 2026-06-23 | 2026-02-25 | 63 | 2026-04-09 | 2026-04-08 | 2026-10-02 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 9/19: Awaiting tower | 7.194 | 125.493 | AN + LEOSAT | 27
NS-TER24-E354 | Brgy.Tulunan_DatuAnggalMidtimbang_Maguindanao | TRFS | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 23. Concrete Pouring | TBD | (02) Survey | AN + LEOSAT | 2026-05-08 | 2026-02-08 | 113 | 2026-10-09 | 2026-02-20 | 2026-01-26 | MAGUINDANAO DEL SUR | DATU ANGGAL MIDTIMBANG | Unassigned | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | MAR | Q1 | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 10/17: Pending site | 7.8772 | 124.0043 | AN + LEOSAT | 23
NS-TER24-E08 | Brgy.Buayan_DatuPiang_Maguindanao | RTB'd | 18. RTB for Mobilization | ERICSSON | FRONTIER | 19. Site Clearing | JISEDAI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-09-06 | 2026-09-04 | 54 | 2026-07-25 | 2026-01-31 | 2026-03-26 | MAGUINDANAO DEL SUR | DATU PIANG | Unassigned | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 5/20: LOS check passed | 7.8973 | 124.0255 | AN + LEOSAT | 23
NS-BIZ21-A28 | Brgy.Pura01_DatuBlahT.Sinsuat_Maguindanao | LGU Permitting | 18. RTB for Mobilization | ERICSSON | FRONTIER | 23. Concrete Pouring | HUAXIN | (05) Permitting | MW/FSO | 2026-08-05 | 2026-12-23 | 142 | 2026-12-05 | 2026-09-07 | 2026-03-21 | MAGUINDANAO DEL NORTE | DATU BLAH T. SINSUAT | Unassigned | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 7.8635 | 124.0028 | MW/FSO | 24
NS-NTG19-C97 | Brgy.MatinaCrossing02_DavaoCity_DavaoDelSur | LGU Permitting | 28. sRFI/TRS Ready | HT | HT | 20. Excavation | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-06-10 | 2026-01-30 | 12 | 2026-10-27 | 2026-09-02 | 2026-09-15 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | Macro | Yes | DEC | Q4 | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 6/24: for checking | 7.2201 | 125.4533 | Fiber Extension | 25
NS-NTG23-F99 | 2023Cov_BrgyPindasan_MABINI (DOÑA ALICIA)_COMPOSTELA VALLEY | For Awarding | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 19. Site Clearing | na | (00) Not Started | MW | 2026-02-05 | 2026-11-01 | 17 | 2026-12-12 | 2026-05-01 | 2026-07-26 | DAVAO DE ORO | MABINI (DOÑA ALICIA) | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 7.9005 | 123.9981 | MW | 24
NS-TER24-E798 | Brgy.Sugal01_JoseAbadSantos(Trinidad)_DavaoOccidental | TRFS | 27. sRFI Pending Pole | NOKIA | UNITY | 24. Backfilling | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-08-03 | 2026-12-03 | 149 | 2026-10-17 | 2026-09-25 | 2026-06-11 | DAVAO OCCIDENTAL | JOSE ABAD SANTOS | Unassigned | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | MAR | Q1 | (05.2) TSSR for Approval | 7/20: RfId site 7/15 | 3/31: Brgy Permit S | 7.8363 | 124.0322 | Fiber Extension | 25
NS-NTG23-D53 | Brgy.Palian_Tupi_SouthCotabato | RFI'd | 28. sRFI/TRS Ready | NOKIA | UNITY | 26. ODU Pad / Electrical | HT | (01) Precon/ Eng'g Hold | MW/FSO | 2026-07-22 | 2026-03-09 | 76 | 2026-08-23 | 2026-06-11 | 2026-02-07 | SOUTH COTABATO | TUPI | Unassigned | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/21: FOC cut 7/10 | 10/17: Pending site | 6.1338 | 125.0335 | MW/FSO | 25
NS-TER24-F595 | Brgy.Udtong_Lambayong(MarianoMarcos)_SultanKudarat | TRFS | 18. RTB for Mobilization | ERICSSON | UNITY | 24. Backfilling | ZTE | (00) Not Started | MW | 2026-09-17 | 2026-05-16 | 33 | 2026-06-28 | 2026-02-05 | 2026-05-06 | SULTAN KUDARAT | LAMBAYONG | Unassigned | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | MAR | Q1 | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 12/10: no pole yet | 7.902 | 124.024 | MW | 25
NS-TER24-D891 | Brgy.Goma02_DigosCity(Capital)_DavaoDelSur | For Awarding | 28. sRFI/TRS Ready | NOKIA | UNITY | 20. Excavation | COMTEL | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-11-10 | 2026-12-01 | 135 | 2026-01-05 | 2026-12-08 | 2026-10-11 | DAVAO DEL SUR | DIGOS CITY (CAPITAL) | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 10/17: Pending site | 7.2049 | 125.4649 | MW/FSO | 25
NS-TER24-A418 | Brgy.Megkawayan_DavaoCity_DavaoDelSur | For Awarding | 27. sRFI Pending Pole | ERICSSON | LDIC | 20. Excavation | HUAXIN | (00) Not Started | Fiber Extension | 2026-10-11 | 2026-03-21 | 69 | 2026-05-25 | 2026-11-06 | 2026-04-18 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 12/10: no pole yet | 7.1603 | 125.4759 | Fiber Extension | 33
NS-BIZ20-G14 | Baymax2020_BrgyBucana_DAVAO_DDS | Awarded | 30. RFI/TRS Ready | HT | UNITY | 20. Excavation | HUAXIN | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-05-09 | 2026-01-27 | 23 | 2026-11-21 | 2026-08-05 | 2026-05-22 | DAVAO DEL SUR | DAVAO CITY | Davao Region | Y | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (05.3) TSSR Approved | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 7.1645 | 125.494 | AN + LEOSAT | 27
NS-TER24-E754 | Brgy.Poblacion_Monkayo_DavaoDeOro | TRFS | 30. RFI/TRS Ready | ERICSSON | UNITY | 22. Rebar Installation | TBD | (02) Survey | MW | 2026-08-15 | 2026-10-10 | 109 | 2026-10-15 | 2026-01-05 | 2026-02-27 | DAVAO DE ORO | MONKAYO | Unassigned | Y | TowerCo (Macro) - BTS | Yes | JUL | Q3 | MAY | Q2 | (01.1) TBD | 6/30: Fiber link verified | 6/15: MW dish installed | 7.9078 | 124.0247 | MW | 25
M2EM4-NS-BIZ20-G17 | M2EM4_Baymax2020_BrgyMatinaAplaya_DAVAO_DDS | RTB'd | 18. RTB for Mobilization | HT | HT | 24. Backfilling | NOKIA | (02) Survey | MW | 2026-08-09 | 2026-03-07 | 10 | 2026-06-07 | 2026-07-06 | 2026-01-21 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | Small Cell | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 12/10: no pole yet | 7.1608 | 125.4492 | MW | 27
M2SC1-NS-NTG23-D32 | M2SC1_Brgy.Tambler03_GeneralSantosCity_SouthCotabato | For Awarding | 27. sRFI Pending Pole | ERICSSON | NOKIA | 26. ODU Pad / Electrical | JISEDAI | (00) Not Started | MW/FSO | 2026-10-14 | 2026-07-28 | 39 | 2026-05-02 | 2026-03-25 | 2026-04-01 | SOUTH COTABATO | GENERAL SANTOS CITY | Unassigned | N | Small Cell | Yes | SEP | Q3 | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 9/19: Awaiting tower | 6.1558 | 125.0281 | MW/FSO | 25
M2SC2-NS-NTG23-D32 | M2SC2_Brgy.Tambler03_GeneralSantosCity_SouthCotabato | s-RFI & TRS Ready | 27. sRFI Pending Pole | ERICSSON | NOKIA | 20. Excavation | HT | (05) Permitting | MW | 2026-05-17 | 2026-03-23 | 27 | 2026-07-15 | 2026-01-20 | 2026-08-29 | SOUTH COTABATO | GENERAL SANTOS CITY | Unassigned | N | Small Cell | Yes | OCT | Q4 | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 6.1565 | 125.0435 | MW | 33
M2SC3-NS-NTG23-D32 | M2SC3_Brgy.Tambler03_GeneralSantosCity_SouthCotabato | For Awarding | 27. sRFI Pending Pole | ERICSSON | NOKIA | 18. RTB for Mobilization | COMTEL | (02) Survey | MW/FSO | 2026-04-27 | 2026-04-25 | 6 | 2026-12-04 | 2026-04-09 | 2026-07-24 | SOUTH COTABATO | GENERAL SANTOS CITY | Unassigned | N | Small Cell | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 10/17: Pending site | 6.1434 | 125.0139 | MW/FSO | 33
M2SC4-NS-NTG23-D32 | M2SC4_Brgy.Tambler03_GeneralSantosCity_SouthCotabato | LGU Permitting | 27. sRFI Pending Pole | ERICSSON | NOKIA | 18. RTB for Mobilization | ZTE | (02) Survey | MW/FSO | 2026-11-25 | 2026-09-18 | 102 | 2026-12-14 | 2026-10-02 | 2026-06-19 | SOUTH COTABATO | GENERAL SANTOS CITY | Unassigned | Y | Small Cell | Yes | OCT | Q4 | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 6/24: for checking | 6.1496 | 125.0664 | MW/FSO | 27
NS-TER24-E606 | Brgy.Macgum01_NewCorella_DavaoDelNorte | For Awarding | 30. RFI/TRS Ready | ERICSSON | UNITY | 22. Rebar Installation | TBD | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-01-20 | 2026-02-25 | 111 | 2026-06-26 | 2026-06-10 | 2026-08-12 | DAVAO DEL NORTE | NEW CORELLA | Unassigned | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 7.4154 | 125.791 | MW/FSO | 27
NS-TER24-E894 | Brgy.SanIsidro_Lupon_DavaoOriental | s-RFI | 18. RTB for Mobilization | ERICSSON | UNITY | 23. Concrete Pouring | JISEDAI | (02) Survey | Fiber Extension | 2026-12-29 | 2026-08-12 | 0 | 2026-09-24 | 2026-10-03 | 2026-12-18 | DAVAO ORIENTAL | LUPON | Unassigned | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 12/10: no pole yet | 7.8618 | 123.9861 | Fiber Extension | 24
NS-TER24-F94 | Brgy.Kibenes_Carmen_NorthCotabato | TRFS | 18. RTB for Mobilization | ERICSSON | UNITY | 22. Rebar Installation | FADI | (00) Not Started | MW/FSO | 2026-11-16 | 2026-06-10 | 31 | 2026-06-03 | 2026-09-17 | 2026-06-08 | COTABATO | CARMEN | Unassigned | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | JUN | Q2 | (05.1) TSSR for Submission | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 7.1821 | 124.7967 | MW/FSO | 24
NS-TER24-A860 | TcoColoc_Brgy.LaEsperanza_Tulunan_NorthCotabato | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 22. Rebar Installation | FADI | (02) Survey | MW | 2026-04-09 | 2026-08-04 | 97 | 2026-12-13 | 2026-03-31 | 2026-11-12 | COTABATO | TULUNAN | Unassigned | N | TowerCo (Macro) - Coloc | Yes | AUG | Q3 | N/A | N/A | (01) For Awarding | 7/18: Power energized | 7/02: FOC splicing ongoing | 7.2299 | 124.8229 | MW | 23
EM2M_NS-TER25-A867 | SR_MIN_DAVAO DEL SUR_DAVAO CITY_BARANGAY 21-C_2025_001 | RTB'd | 18. RTB for Mobilization | HT | FRONTIER | 23. Concrete Pouring | na | (00) Not Started | MW/FSO | 2026-05-27 | 2026-04-18 | 110 | 2026-10-24 | 2026-11-07 | 2026-12-02 | DAVAO DEL SUR | DAVAO CITY | Davao Region | N | TowerCo (Macro) - Coloc | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 9/19: Awaiting tower | 7.2005 | 125.4571 | MW/FSO | 24
K813 | 2020Capsite_BrgyTagCab_Butuan City (Capital) | For Awarding | 03. For Awarding | ERICSSON | ALLIANCE | 18. RTB for Mobilization | JISEDAI | (02) Survey | MW | 2026-04-12 | 2026-03-17 | 6 | 2026-01-24 | 2026-05-06 | 2026-09-01 | LANAO DEL NORTE | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 9/19: Awaiting tower | 8.9411 | 125.5338 | MW | 24
O714 | 2023M2SC2_BrgyBalLun_Claveria | TRFS | 18. RTB for Mobilization | ERICSSON | LDIC | 18. RTB for Mobilization | ZTE | (05) Permitting | MW | 2026-04-01 | 2026-12-23 | 132 | 2026-08-26 | 2026-01-26 | 2026-10-13 | LANAO DEL NORTE | CLAVERIA | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | FEB | Q1 | (06.2) Brgy Secured | 6/28: For MOS. Pull | 6/24: for checking | 8.5852 | 124.9001 | MW | 25
L610 | 2023CDNPH_BrgyLibBur_Surigao City (Capital) | For Awarding | 27. sRFI Pending Pole | NOKIA | PHILTOWER | 20. Excavation | COMTEL | (05) Permitting | MW/FSO | 2026-05-07 | 2026-11-23 | 70 | 2026-09-24 | 2026-09-06 | 2026-11-17 | LANAO DEL NORTE | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 3/31: Brgy Permit S | 9.8007 | 125.5252 | MW/FSO | 23
F328 | 2020T8_RgPM_BrgyBagSig_Pagadian City (Capital) | Awarded | 03. For Awarding | ERICSSON | UNITY | 26. ODU Pad / Electrical | JISEDAI | (00) Not Started | AN + LEOSAT | 2026-07-28 | 2026-06-19 | 138 | 2026-08-27 | 2026-08-01 | 2026-02-01 | LANAO DEL NORTE | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (03) PSH | 7/18: Power energized | 5/20: LOS check passed | 7.8597 | 123.442 | AN + LEOSAT | 24
A878 | 2023T8_RgPM_BrgyDorMal_Malaybalay City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | UNITY | 18. RTB for Mobilization | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-09-07 | 2026-04-23 | 69 | 2026-08-12 | 2026-09-06 | 2026-01-15 | ZAMBOANGA DEL NORTE | MALAYBALAY CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 8.1256 | 125.1107 | MW | 24
K942 | 2024Capsite_BrgyCabMal_Surigao City (Capital) | RFI'd | 28. sRFI/TRS Ready | NOKIA | PHILTOWER | 19. Site Clearing | ZTE | (05) Permitting | MW | 2026-08-25 | 2026-04-04 | 12 | 2026-05-14 | 2026-07-14 | 2026-06-17 | MISAMIS ORIENTAL | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | JAN | Q1 | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 10/17: Pending site | 9.7829 | 125.4775 | MW | 27
P975 | 2022M2SC2_BrgySanDor_Malaybalay City (Capital) | TRFS | 14. LC Applied | NOKIA | FRONTIER | 22. Rebar Installation | JISEDAI | (00) Not Started | Fiber Extension | 2026-01-16 | 2026-05-07 | 51 | 2026-01-11 | 2026-11-15 | 2026-03-20 | SULU | MALAYBALAY CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAY | Q2 | (01) For Awarding | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 8.1504 | 125.1184 | Fiber Extension | 23
K717 | 2022CDNPH_BrgyBagLib_Zamboanga City | Awarded | 36. TRFS | ERICSSON | EDOTCO | 19. Site Clearing | NOKIA | (02) Survey | AN + LEOSAT | 2026-07-23 | 2026-04-12 | 19 | 2026-10-31 | 2026-12-20 | 2026-11-18 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 6.9202 | 122.0877 | AN + LEOSAT | 23
P124 | 2020T8_RgPM_BrgyKawCab_Cagayan De Oro City (Capital) | Awarded | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HT | (00) Not Started | AN + LEOSAT | 2026-09-08 | 2026-02-24 | 110 | 2026-07-05 | 2026-11-22 | 2026-08-24 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 01 Precon/ Eng'g Hold | 8.4172 | 124.6139 | AN + LEOSAT | 23
E631 | 2023T8_RgPM_BrgyDorBal_General Luna | TRFS | 36. TRFS | ERICSSON | LDIC | 18. RTB for Mobilization | ZTE | (02) Survey | AN + LEOSAT | 2026-05-05 | 2026-08-26 | 145 | 2026-11-09 | 2026-12-09 | 2026-07-14 | LANAO DEL NORTE | GENERAL LUNA | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAY | Q2 | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 9.7543 | 126.1645 | AN + LEOSAT | 27
F817 | 2022CDNPH_BrgyTagLib_Cagayan De Oro City (Capital) | Awarded | 14. LC Applied | NOKIA | FRONTIER | 20. Excavation | ZTE | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-09-08 | 2026-10-12 | 61 | 2026-12-20 | 2026-09-01 | 2026-11-27 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | Yes | SEP | Q3 | N/A | N/A | (05.1) TSSR for Submission | 6/18: Permanent Po | 6/24: for checking | 8.4697 | 124.595 | AN + LEOSAT | 33
G709 | 2022Capsite_BrgyNalLib_Zamboanga City | TSSR | 07. Site Survey | ERICSSON | PHILTOWER | 22. Rebar Installation | FADI | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-06-30 | 2026-12-26 | 116 | 2026-05-19 | 2026-06-06 | 2026-05-09 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/18: Permanent Po | 6/24: for checking | 6.9526 | 122.0655 | MW/FSO | 23
P707 | 2021Capsite_BrgyLunBur_Cagayan De Oro City (Capital) | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | UNITY | 18. RTB for Mobilization | na | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-02-21 | 2026-04-10 | 75 | 2026-04-27 | 2026-07-04 | 2026-04-02 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 6/15: MW dish installed | 8.4332 | 124.6516 | MW/FSO | 23
A567 | 2021CDNPH_BrgyNalDor_Zamboanga City | RFI'd | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | COMTEL | (05) Permitting | MW/FSO | 2026-04-05 | 2026-01-27 | 64 | 2026-09-02 | 2026-02-28 | 2026-02-03 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.1) TSSR for Submission | 7/20: RfId site 7/15 | 9/19: Awaiting tower | 6.9551 | 122.1108 | MW/FSO | 27
C831 | 2022T8_RgPM_BrgySanLun_Marawi City (Capital) | LGU Permitting | 03. For Awarding | NOKIA | ALLIANCE | 24. Backfilling | JISEDAI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-08-19 | 2026-08-15 | 76 | 2026-10-29 | 2026-08-08 | 2026-06-06 | ZAMBOANGA DEL SUR | MARAWI CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 7.9616 | 124.3087 | AN + LEOSAT | 33
P213 | 2022Capsite_BrgyNalSan_Arakan | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | TBD | (00) Not Started | AN + LEOSAT | 2026-08-19 | 2026-12-19 | 120 | 2026-05-30 | 2026-01-17 | 2026-04-29 | ZAMBOANGA DEL SUR | ARAKAN | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 10/17: Pending site | 7.8099 | 123.4194 | AN + LEOSAT | 23
E807 | 2021T8_RgPM_BrgyBalSan_Butuan City (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | LDIC | 18. RTB for Mobilization | TBD | (00) Not Started | Fiber Extension | 2026-03-26 | 2026-06-07 | 145 | 2026-05-28 | 2026-08-13 | 2026-03-05 | MISAMIS ORIENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | FEB | Q1 | (06.1) Brgy Applied | 6/20: RFI with Perm | 5/20: LOS check passed | 8.9468 | 125.5563 | Fiber Extension | 23
K449 | 2024CapSite_BrgyMalBal_Ozamiz City | TRFS | 14. LC Applied | NOKIA | FRONTIER | 19. Site Clearing | JISEDAI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-12-11 | 2026-05-18 | 147 | 2026-01-21 | 2026-03-31 | 2026-08-29 | MISAMIS ORIENTAL | OZAMIZ CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | MAR | Q1 | MAY | Q2 | (04) For Re-award | 7/20: RfId site 7/15 | 9/19: Awaiting tower | 8.116 | 123.8714 | Fiber Extension | 25
T834 | 2020M2SC2_BrgyDorKaw_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 19. Site Clearing | TBD | (02) Survey | AN + LEOSAT | 2026-12-22 | 2026-09-11 | 73 | 2026-12-06 | 2026-07-25 | 2026-10-09 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 6.8922 | 122.1169 | AN + LEOSAT | 33
P414 | 2020T8_RgPM_BrgyNalCab_Cagayan De Oro City (Capital) | RTB'd | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | HT | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-11-17 | 2026-08-15 | 13 | 2026-04-15 | 2026-05-17 | 2026-10-09 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 7/02: FOC splicing ongoing | 8.4496 | 124.658 | AN + LEOSAT | 24
T624 | 2021Capsite_BrgyTagCab_Pagadian City (Capital) | TRFS | 03. For Awarding | NOKIA | PHILTOWER | 20. Excavation | ZTE | (05) Permitting | Fiber Extension | 2026-11-28 | 2026-03-20 | 127 | 2026-05-30 | 2026-09-18 | 2026-12-28 | LANAO DEL NORTE | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | JAN | Q1 | (03) PSH | 6/30: Fiber link verified | 9/19: Awaiting tower | 7.8073 | 123.4303 | Fiber Extension | 23
L149 | 2021M2SC2_BrgyLibCab_Davao City | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | FADI | (02) Survey | MW/FSO | 2026-01-02 | 2026-05-25 | 76 | 2026-10-28 | 2026-10-24 | 2026-12-04 | AGUSAN DEL NORTE | DAVAO CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 9/19: Awaiting tower | 7.2023 | 125.4303 | MW/FSO | 27
P557 | 2023M2SC2_BrgyKawLun_Iligan City | RTB'd | 06. With Issue | NOKIA | FRONTIER | 18. RTB for Mobilization | FADI | (00) Not Started | MW/FSO | 2026-08-31 | 2026-12-28 | 97 | 2026-07-17 | 2026-12-06 | 2026-11-30 | LANAO DEL NORTE | ILIGAN CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | OCT | Q4 | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 9/19: Awaiting tower | 8.2049 | 124.2711 | MW/FSO | 25
F891 | 2023CapSite_BrgySanCab_Zamboanga City | LGU Permitting | 36. TRFS | ERICSSON | UNITY | 23. Concrete Pouring | TBD | (00) Not Started | AN + LEOSAT | 2026-05-16 | 2026-06-23 | 101 | 2026-11-29 | 2026-02-11 | 2026-06-18 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 6/15: MW dish installed | 6.9407 | 122.0998 | AN + LEOSAT | 24
P500 | 2020T8_RgPM_BrgyLibSan_Cagayan De Oro City (Capital) | LGU Permitting | 28. sRFI/TRS Ready | ERICSSON | ISON | 26. ODU Pad / Electrical | ZTE | (05) Permitting | Fiber Extension | 2026-11-21 | 2026-12-27 | 25 | 2026-08-16 | 2026-03-27 | 2026-12-22 | ZAMBOANGA DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 6/15: MW dish installed | 8.4836 | 124.6576 | Fiber Extension | 24
F442 | 2021Capsite_BrgyCabBal_Surigao City (Capital) | LGU Permitting | 06. With Issue | ERICSSON | FRONTIER | 24. Backfilling | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-09-12 | 2026-10-26 | 36 | 2026-04-29 | 2026-08-25 | 2026-11-23 | ZAMBOANGA DEL SUR | SURIGAO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/21: FOC cut 7/10 | 12/10: no pole yet | 9.7812 | 125.4627 | MW | 25
E694 | 2021T8_RgPM_BrgySanDor_Zamboanga City | RFI'd | 32. Ongoing Integration | NOKIA | FRONTIER | 23. Concrete Pouring | HUAXIN | (05) Permitting | MW/FSO | 2026-04-12 | 2026-07-16 | 123 | 2026-02-24 | 2026-05-02 | 2026-07-15 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 10/17: Pending site | 6.9063 | 122.0795 | MW/FSO | 27
T406 | 2020CDNPH_BrgyLibNal_Davao City | LGU Permitting | 06. With Issue | NOKIA | UNITY | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | MW/FSO | 2026-04-23 | 2026-11-22 | 48 | 2026-11-14 | 2026-05-09 | 2026-12-14 | MISAMIS ORIENTAL | DAVAO CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 7/02: FOC splicing ongoing | 7.1616 | 125.4834 | MW/FSO | 24
E808 | 2020M2SC2_BrgyLibKaw_Balingasag | s-RFI | 27. sRFI Pending Pole | ERICSSON | LDIC | 22. Rebar Installation | FADI | (01) Precon/ Eng'g Hold | MW | 2026-03-09 | 2026-10-04 | 93 | 2026-09-29 | 2026-09-14 | 2026-05-20 | MISAMIS ORIENTAL | BALINGASAG | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 10/17: Pending site | 8.7764 | 124.7356 | MW | 24
E765 | 2020CDNPH_BrgyDorSan_Ozamiz City | TSSR | 36. TRFS | ERICSSON | LDIC | 26. ODU Pad / Electrical | FADI | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-02-16 | 2026-07-22 | 3 | 2026-05-16 | 2026-10-02 | 2026-03-05 | SURIGAO DEL NORTE | OZAMIZ CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/30: Fiber link verified | 10/17: Pending site | 8.1235 | 123.8685 | MW/FSO | 33
T963 | 2020CDNPH_BrgyNalLun_Valencia City | For Awarding | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 24. Backfilling | HT | (06) RTB (FOC/AN/Pending) | MW | 2026-11-28 | 2026-02-02 | 118 | 2026-12-25 | 2026-06-04 | 2026-11-29 | MISAMIS ORIENTAL | VALENCIA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 7.9334 | 125.0742 | MW | 24
K119 | 2021CapSite_BrgyCabBag_Ozamiz City | For Awarding | 07. Site Survey | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (05) Permitting | MW | 2026-08-01 | 2026-12-02 | 25 | 2026-09-08 | 2026-11-12 | 2026-07-28 | ZAMBOANGA DEL SUR | OZAMIZ CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 01 Precon/ Eng'g Hold | 8.1446 | 123.8753 | MW | 23
D876 | 2020CDNPH_BrgyNalKaw_Zamboanga City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | ZTE | (05) Permitting | Fiber Extension | 2026-12-06 | 2026-04-19 | 5 | 2026-01-26 | 2026-06-20 | 2026-05-05 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | Self-Build - BTS | Yes | MAR | Q1 | JUN | Q2 | (02) Ongoing Survey | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 6.9378 | 122.0609 | Fiber Extension | 23
Q222 | 2022Capsite_BrgySigBag_Ipil (Capital) | TRFS | 14. LC Applied | ERICSSON | LDIC | 20. Excavation | TBD | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-03-31 | 2026-02-26 | 6 | 2026-03-09 | 2026-01-08 | 2026-07-03 | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | Yes | MAR | Q1 | MAR | Q1 | (02) Ongoing Survey | 6/18: Permanent Po | 6/24: for checking | 7.807 | 122.5857 | MW/FSO | 25
O432 | 2020T8_RgPM_BrgyBurSan_Zamboanga City | TRS Ready | 03. For Awarding | ERICSSON | ALLIANCE | 24. Backfilling | ZTE | (05) Permitting | MW | 2026-11-11 | 2026-01-23 | 133 | 2026-06-04 | 2026-08-23 | 2026-11-26 | SULU | ZAMBOANGA CITY | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 06 RTB (FOC/ AN/ ... | 6.9322 | 122.0489 | MW | 25
B503 | 2020M2SC2_BrgySanKaw_Lamitan City (Capital) | Awarded | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | na | (02) Survey | AN + LEOSAT | 2026-11-02 | 2026-09-29 | 75 | 2026-08-21 | 2026-09-16 | 2026-11-06 | DINAGAT ISLANDS | LAMITAN CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/12: Awaiting transmission hookup | 10/17: Pending site | 6.6124 | 122.1231 | AN + LEOSAT | 27
P565 | 2023Capsite_BrgyDorLun_Zamboanga City | For Awarding | 27. sRFI Pending Pole | ERICSSON | ALLIANCE | 23. Concrete Pouring | FADI | (00) Not Started | MW/FSO | 2026-08-07 | 2026-06-10 | 65 | 2026-07-11 | 2026-03-20 | 2026-12-18 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 5/20: LOS check passed | 6.9289 | 122.0532 | MW/FSO | 27
O757 | 2021CDNPH_BrgyCabMal_Zamboanga City | TRFS | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (00) Not Started | MW/FSO | 2026-11-04 | 2026-06-09 | 90 | 2026-02-23 | 2026-10-23 | 2026-09-17 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | JAN | Q1 | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 6.951 | 122.0859 | MW/FSO | 33
L377 | 2022CapSite_BrgyLibLun_Zamboanga City | TRFS | 03. For Awarding | NOKIA | EDOTCO | 18. RTB for Mobilization | na | (00) Not Started | MW/FSO | 2026-01-15 | 2026-04-03 | 69 | 2026-12-26 | 2026-06-08 | 2026-06-23 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | FEB | Q1 | (01) For Awarding | 6/20: RFI with Perm | 3/31: Brgy Permit S | 6.9094 | 122.0521 | MW/FSO | 25
B146 | 2020CapSite_BrgyBurCab_Zamboanga City | RTB'd | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 22. Rebar Installation | TBD | (02) Survey | MW/FSO | 2026-06-16 | 2026-10-18 | 21 | 2026-01-27 | 2026-03-21 | 2026-03-22 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 10/17: Pending site | 6.953 | 122.0989 | MW/FSO | 33
K622 | 2023M2SC2_BrgyTagLun_Cagayan De Oro City (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 22. Rebar Installation | COMTEL | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-01-24 | 2026-04-23 | 101 | 2026-11-03 | 2026-01-29 | 2026-01-04 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | FEB | Q1 | (01.1) TBD | 6/20: RFI with Perm | 7/02: FOC splicing ongoing | 8.4693 | 124.6147 | MW/FSO | 27
E336 | 2020CapSite_BrgyDorBur_Malaybalay City (Capital) | TSSR | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-02-06 | 2026-07-23 | 10 | 2026-08-12 | 2026-01-10 | 2026-08-24 | COTABATO (NORTH COTABATO) | MALAYBALAY CITY (CAPITAL) | SOCCSKSARGEN | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/20: RFI with Perm | 06 RTB (FOC/ AN/ ... | 8.1484 | 125.1008 | MW/FSO | 24
G297 | 2023CapSite_BrgyMalKaw_Isabela City | TRFS | 28. sRFI/TRS Ready | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | HT | (00) Not Started | AN + LEOSAT | 2026-02-24 | 2026-05-05 | 111 | 2026-10-29 | 2026-07-25 | 2026-09-26 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | FEB | Q1 | MAR | Q1 | (06.2) Brgy Secured | 7/18: Power energized | 5/20: LOS check passed | 6.7099 | 122.0083 | AN + LEOSAT | 33
P173 | 2024CapSite_BrgyNalSan_General Luna | LGU Permitting | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-03-16 | 2026-05-12 | 50 | 2026-03-30 | 2026-11-05 | 2026-03-20 | AGUSAN DEL SUR | GENERAL LUNA | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 9.8114 | 126.1676 | Fiber Extension | 24
P578 | 2023T8_RgPM_BrgyNalLib_Malaybalay City (Capital) | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | COMTEL | (05) Permitting | MW/FSO | 2026-05-21 | 2026-10-30 | 14 | 2026-06-30 | 2026-09-17 | 2026-02-07 | ZAMBOANGA DEL SUR | MALAYBALAY CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/20: RFI with Perm | 9/19: Awaiting tower | 8.1717 | 125.1093 | MW/FSO | 33
B661 | 2024CapSite_BrgyLibCab_Zamboanga City | For Awarding | 32. Ongoing Integration | ERICSSON | PHILTOWER | 18. RTB for Mobilization | NOKIA | (05) Permitting | MW | 2026-06-14 | 2026-11-06 | 121 | 2026-09-14 | 2026-03-19 | 2026-02-01 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 9/19: Awaiting tower | 6.9142 | 122.0406 | MW | 33
B517 | 2020Capsite_BrgyLunBur_Lamitan City (Capital) | RFI'd | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | TBD | (02) Survey | MW/FSO | 2026-05-25 | 2026-07-18 | 104 | 2026-06-23 | 2026-12-14 | 2026-11-03 | BUKIDNON | LAMITAN CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/20: RfId site 7/15 | 10/17: Pending site | 6.6724 | 122.1547 | MW/FSO | 27
E259 | 2021T8_RgPM_BrgyKawSan_Zamboanga City | s-RFI | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | FADI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-06-08 | 2026-10-14 | 96 | 2026-11-26 | 2026-06-18 | 2026-03-07 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/18: Power energized | 9/19: Awaiting tower | 6.8821 | 122.1119 | Fiber Extension | 33
A372 | 2021CDNPH_BrgyLunKaw_Valencia City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | TBD | (00) Not Started | MW/FSO | 2026-02-21 | 2026-09-17 | 138 | 2026-09-27 | 2026-01-20 | 2026-12-05 | ZAMBOANGA DEL SUR | VALENCIA CITY | Zamboanga Peninsula | N | Self-Build - BTS | Yes | FEB | Q1 | MAR | Q1 | (01) For Awarding | 7/20: RfId site 7/15 | 06 RTB (FOC/ AN/ ... | 7.9182 | 125.1023 | MW/FSO | 27
O790 | 2021T8_RgPM_BrgyBurDor_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | JISEDAI | (05) Permitting | MW/FSO | 2026-08-18 | 2026-04-30 | 136 | 2026-05-03 | 2026-06-08 | 2026-08-29 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 8.4149 | 124.6121 | MW/FSO | 33
P289 | 2024M2SC2_BrgyCabBal_Isabela City | RTB'd | 14. LC Applied | ERICSSON | ALLIANCE | 20. Excavation | HUAXIN | (00) Not Started | AN + LEOSAT | 2026-07-10 | 2026-10-11 | 26 | 2026-12-31 | 2026-09-22 | 2026-03-05 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/20: RfId site 7/15 | 6/15: MW dish installed | 6.7285 | 121.9555 | AN + LEOSAT | 33
C851 | 2020M2SC2_BrgyLunDor_Cagayan De Oro City (Capital) | Awarded | 36. TRFS | ERICSSON | PHILTOWER | 23. Concrete Pouring | na | (02) Survey | MW | 2026-07-17 | 2026-02-11 | 95 | 2026-04-25 | 2026-01-15 | 2026-06-13 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (05.1) TSSR for Submission | 7/20: RfId site 7/15 | 7/02: FOC splicing ongoing | 8.4916 | 124.6433 | MW | 25
K713 | 2023Capsite_BrgyDorLib_Zamboanga City | For Awarding | 06. With Issue | ERICSSON | FRONTIER | 20. Excavation | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-02-26 | 2026-05-28 | 60 | 2026-06-04 | 2026-03-04 | 2026-01-25 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 6/15: MW dish installed | 6.9153 | 122.0691 | AN + LEOSAT | 25
K612 | 2020T8_RgPM_BrgyNalCab_Marawi City (Capital) | Awarded | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | HT | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-04-06 | 2026-12-07 | 21 | 2026-09-26 | 2026-07-04 | 2026-02-04 | MISAMIS ORIENTAL | MARAWI CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 6/20: RFI with Perm | 10/17: Pending site | 7.9879 | 124.2635 | AN + LEOSAT | 27
G895 | 2020M2SC2_BrgyNalBal_Davao City | TRFS | 14. LC Applied | ERICSSON | UNITY | 22. Rebar Installation | ZTE | (02) Survey | MW | 2026-12-03 | 2026-11-18 | 26 | 2026-10-25 | 2026-06-20 | 2026-03-10 | LANAO DEL SUR | DAVAO CITY | BARMM | Y | TowerCo (Macro) - BTS | Yes | AUG | Q3 | FEB | Q1 | (05.3) TSSR Approved | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 7.188 | 125.4695 | MW | 33
P702 | 2023M2SC2_BrgyNalBag_Ipil (Capital) | TRFS | 03. For Awarding | ERICSSON | UNITY | 23. Concrete Pouring | NOKIA | (02) Survey | MW | 2026-01-23 | 2026-04-13 | 10 | 2026-06-11 | 2026-06-08 | 2026-09-21 | MISAMIS OCCIDENTAL | IPIL (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | AUG | Q3 | JAN | Q1 | (03) PSH | 5/12: CR applied, AP | 12/10: no pole yet | 7.807 | 122.5771 | MW | 24
E366 | 2022CapSite_BrgyTagSan_Zamboanga City | For Awarding | 27. sRFI Pending Pole | ERICSSON | LDIC | 26. ODU Pad / Electrical | COMTEL | (05) Permitting | MW/FSO | 2026-04-06 | 2026-09-12 | 127 | 2026-07-08 | 2026-09-23 | 2026-05-17 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (04) For Re-award | 6/20: RFI with Perm | 9/19: Awaiting tower | 6.8896 | 122.0799 | MW/FSO | 23
L301 | 2020CDNPH_BrgySanKaw_Isabela City | LGU Permitting | 32. Ongoing Integration | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | FADI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-06-29 | 2026-08-17 | 10 | 2026-06-30 | 2026-11-11 | 2026-08-11 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 3/31: Brgy Permit S | 6.7171 | 121.9986 | AN + LEOSAT | 27
P768 | 2020Capsite_BrgyBagLib_Marawi City (Capital) | TSSR | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | HT | (02) Survey | AN + LEOSAT | 2026-10-18 | 2026-01-17 | 39 | 2026-12-14 | 2026-08-19 | 2026-07-09 | ZAMBOANGA DEL SUR | MARAWI CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/21: FOC cut 7/10 | 01 Precon/ Eng'g Hold | 7.9899 | 124.2951 | AN + LEOSAT | 25
G322 | 2021CDNPH_BrgySanMal_Isabela City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 24. Backfilling | ZTE | (02) Survey | MW/FSO | 2026-12-27 | 2026-08-17 | 54 | 2026-11-10 | 2026-05-27 | 2026-12-22 | BUKIDNON | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 6.7128 | 121.955 | MW/FSO | 25
O456 | 2022CapSite_BrgyNalKaw_Lamitan City (Capital) | For Awarding | 14. LC Applied | NOKIA | PHILTOWER | 22. Rebar Installation | TBD | (01) Precon/ Eng'g Hold | MW/FSO | 2026-09-18 | 2026-04-25 | 31 | 2026-04-13 | 2026-03-13 | 2026-05-02 | ZAMBOANGA DEL SUR | LAMITAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01) For Awarding | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 6.6186 | 122.0984 | MW/FSO | 27
L133 | 2020T8_RgPM_BrgySanTag_Isabela City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-03-06 | 2026-06-12 | 18 | 2026-08-19 | 2026-08-27 | 2026-12-15 | TAWI-TAWI | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 6.7432 | 121.9823 | Fiber Extension | 25
Q187 | 2023Capsite_BrgyCabMal_Ipil (Capital) | TRFS | 14. LC Applied | NOKIA | FRONTIER | 20. Excavation | TBD | (02) Survey | MW | 2026-06-27 | 2026-09-23 | 72 | 2026-02-10 | 2026-05-09 | 2026-04-11 | ZAMBOANGA DEL SUR | IPIL (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | SEP | Q3 | FEB | Q1 | (02) Ongoing Survey | 7/20: RfId site 7/15 | 12/10: no pole yet | 7.81 | 122.5662 | MW | 24
B515 | 2024Capsite_BrgyLibBag_Marawi City (Capital) | For Awarding | 18. RTB for Mobilization | NOKIA | UNITY | 24. Backfilling | HT | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-01-15 | 2026-02-11 | 11 | 2026-11-25 | 2026-10-23 | 2026-05-16 | BASILAN | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 6/24: for checking | 8.0169 | 124.3147 | Fiber Extension | 25
K911 | 2022T8_RgPM_BrgyNalTag_Cagayan De Oro City (Capital) | For Awarding | 18. RTB for Mobilization | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | FADI | (02) Survey | AN + LEOSAT | 2026-02-07 | 2026-12-19 | 15 | 2026-03-22 | 2026-08-14 | 2026-08-01 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 12/10: no pole yet | 8.4381 | 124.6039 | AN + LEOSAT | 23
O327 | 2023CDNPH_BrgyBagKaw_Isabela City | TRFS | 06. With Issue | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (05) Permitting | MW | 2026-03-14 | 2026-02-19 | 12 | 2026-05-29 | 2026-07-16 | 2026-11-12 | ZAMBOANGA SIBUGAY | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | MAY | Q2 | (05.3) TSSR Approved | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 6.7253 | 122.0031 | MW | 23
Q739 | 2021CDNPH_BrgySigBag_Balingasag | LGU Permitting | 32. Ongoing Integration | NOKIA | PHILTOWER | 22. Rebar Installation | COMTEL | (00) Not Started | Fiber Extension | 2026-07-21 | 2026-09-16 | 117 | 2026-05-04 | 2026-04-21 | 2026-10-26 | COTABATO (NORTH COTABATO) | BALINGASAG | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 01 Precon/ Eng'g Hold | 8.7705 | 124.7975 | Fiber Extension | 33
T689 | 2022M2SC2_BrgyCabMal_Iligan City | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 22. Rebar Installation | HT | (05) Permitting | MW/FSO | 2026-01-24 | 2026-07-25 | 13 | 2026-10-19 | 2026-10-15 | 2026-04-10 | ZAMBOANGA DEL SUR | ILIGAN CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | JUL | Q3 | N/A | N/A | (06.1) Brgy Applied | 7/20: RfId site 7/15 | 06 RTB (FOC/ AN/ ... | 8.236 | 124.258 | MW/FSO | 24
L287 | 2024T8_RgPM_BrgySanBag_Cagayan De Oro City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | FRONTIER | 22. Rebar Installation | na | (02) Survey | MW | 2026-04-12 | 2026-11-05 | 130 | 2026-07-25 | 2026-09-14 | 2026-01-21 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 8.4687 | 124.6496 | MW | 25
K153 | 2024T8_RgPM_BrgyBagKaw_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | HUAXIN | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-09-17 | 2026-09-18 | 136 | 2026-09-08 | 2026-12-29 | 2026-10-16 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | DEC | Q4 | N/A | N/A | (04) For Re-award | 7/18: Power energized | 3/31: Brgy Permit S | 8.4666 | 124.6717 | MW/FSO | 25
G598 | 2020CDNPH_BrgyLibDor_Cagayan De Oro City (Capital) | LGU Permitting | 27. sRFI Pending Pole | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-03-29 | 2026-09-26 | 97 | 2026-03-17 | 2026-12-15 | 2026-05-05 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 7/02: FOC splicing ongoing | 8.435 | 124.6254 | AN + LEOSAT | 27
F429 | 2023Capsite_BrgyBurLun_Zamboanga City | For Awarding | 03. For Awarding | NOKIA | ALLIANCE | 23. Concrete Pouring | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-10-15 | 2026-06-16 | 122 | 2026-09-27 | 2026-07-12 | 2026-06-10 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | TowerCo (Micro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 12/10: no pole yet | 6.9125 | 122.0418 | MW | 33
P889 | 2024CDNPH_BrgyDorLun_Cagayan De Oro City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 20. Excavation | HUAXIN | (02) Survey | MW | 2026-12-20 | 2026-12-27 | 125 | 2026-06-12 | 2026-09-03 | 2026-06-28 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 6/24: for checking | 8.4708 | 124.6377 | MW | 23
G839 | 2021CDNPH_BrgyTagMal_Isabela City | TSSR | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | HUAXIN | (05) Permitting | MW | 2026-04-14 | 2026-10-03 | 69 | 2026-10-15 | 2026-12-23 | 2026-05-20 | BASILAN | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/20: RfId site 7/15 | 3/31: Brgy Permit S | 6.6793 | 121.9892 | MW | 27
T927 | 2021T8_RgPM_BrgyNalLun_Isabela City | TRS Ready | 03. For Awarding | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | COMTEL | (00) Not Started | MW | 2026-01-03 | 2026-10-09 | 40 | 2026-07-28 | 2026-12-01 | 2026-09-01 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 5/20: LOS check passed | 6.6819 | 121.9739 | MW | 27
A930 | 2024CapSite_BrgyLunCab_Cagayan De Oro City (Capital) | TRFS | 06. With Issue | ERICSSON | PHILTOWER | 18. RTB for Mobilization | TBD | (00) Not Started | AN + LEOSAT | 2026-09-11 | 2026-04-06 | 74 | 2026-01-20 | 2026-01-05 | 2026-06-02 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | Yes | MAR | Q1 | MAY | Q2 | (02) Ongoing Survey | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 8.477 | 124.6644 | AN + LEOSAT | 25
T557 | 2023T8_RgPM_BrgyBagCab_Davao City | LGU Permitting | 07. Site Survey | ERICSSON | FRONTIER | 19. Site Clearing | HT | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-11-28 | 2026-05-12 | 47 | 2026-01-08 | 2026-06-22 | 2026-06-01 | ZAMBOANGA DEL SUR | DAVAO CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/18: Power energized | 9/19: Awaiting tower | 7.2044 | 125.4559 | AN + LEOSAT | 23
G528 | 2020CDNPH_BrgyBalNal_Gingoog City | RTB'd | 36. TRFS | ERICSSON | EDOTCO | 23. Concrete Pouring | HT | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-05-14 | 2026-07-16 | 60 | 2026-08-17 | 2026-05-17 | 2026-06-18 | ZAMBOANGA DEL SUR | GINGOOG CITY | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 8.8487 | 125.1304 | Fiber Extension | 27
O242 | 2020CapSite_BrgyDorTag_Zamboanga City | Awarded | 27. sRFI Pending Pole | ERICSSON | UNITY | 26. ODU Pad / Electrical | HUAXIN | (00) Not Started | MW/FSO | 2026-07-08 | 2026-11-11 | 56 | 2026-04-23 | 2026-03-10 | 2026-09-02 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.3) TSSR Approved | 7/20: RfId site 7/15 | 5/20: LOS check passed | 6.9515 | 122.0535 | MW/FSO | 25
L935 | 2024M2SC2_BrgySigNal_Isabela City | Awarded | 14. LC Applied | ERICSSON | UNITY | 24. Backfilling | ZTE | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-09-28 | 2026-12-27 | 92 | 2026-02-09 | 2026-10-16 | 2026-02-27 | BUKIDNON | ISABELA CITY | Northern Mindanao | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 6.6719 | 121.9413 | AN + LEOSAT | 33
C336 | 2023T8_RgPM_BrgySanNal_Zamboanga City | RTB'd | 14. LC Applied | NOKIA | PHILTOWER | 24. Backfilling | COMTEL | (00) Not Started | AN + LEOSAT | 2026-03-09 | 2026-09-20 | 106 | 2026-08-22 | 2026-10-16 | 2026-01-30 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/05: Integration complete | 9/19: Awaiting tower | 6.9021 | 122.1037 | AN + LEOSAT | 24
E837 | 2021CapSite_BrgyLibSan_Cagayan De Oro City (Capital) | RFI'd | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | na | (00) Not Started | Fiber Extension | 2026-08-30 | 2026-01-17 | 73 | 2026-07-29 | 2026-04-03 | 2026-03-11 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (03) PSH | 6/20: RFI with Perm | 01 Precon/ Eng'g Hold | 8.4752 | 124.6065 | Fiber Extension | 23
G385 | 2024CapSite_BrgyBagNal_Bongao (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-04-25 | 2026-01-02 | 5 | 2026-06-02 | 2026-08-26 | 2026-12-11 | ZAMBOANGA DEL NORTE | BONGAO (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | MAR | Q1 | JUN | Q2 | (05.3) TSSR Approved | 5/12: CR applied, AP | 6/24: for checking | 5.0666 | 119.7594 | MW | 33
K355 | 2022Capsite_BrgyLunBur_Cagayan De Oro City (Capital) | TRS Ready | 03. For Awarding | ERICSSON | ALLIANCE | 23. Concrete Pouring | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-02-04 | 2026-02-21 | 8 | 2026-08-17 | 2026-11-03 | 2026-12-11 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 6/15: MW dish installed | 8.4213 | 124.6203 | MW | 25
L223 | 2021CapSite_BrgyCabTag_Zamboanga City | For Awarding | 14. LC Applied | NOKIA | FRONTIER | 24. Backfilling | HT | (01) Precon/ Eng'g Hold | MW/FSO | 2026-03-15 | 2026-12-05 | 133 | 2026-04-24 | 2026-07-31 | 2026-06-03 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (01.1) TBD | 7/18: Power energized | 6/15: MW dish installed | 6.9409 | 122.0636 | MW/FSO | 24
C642 | 2024M2SC2_BrgyDorMal_Isabela City | Awarded | 30. RFI/TRS Ready | ERICSSON | ALLIANCE | 22. Rebar Installation | FADI | (05) Permitting | MW | 2026-06-03 | 2026-07-12 | 47 | 2026-10-03 | 2026-08-31 | 2026-05-04 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/20: RFI with Perm | 10/17: Pending site | 6.7271 | 121.9576 | MW | 27
A576 | 2023M2SC2_BrgyCabSig_Zamboanga City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | HT | (00) Not Started | AN + LEOSAT | 2026-07-09 | 2026-02-17 | 137 | 2026-04-08 | 2026-01-27 | 2026-05-18 | AGUSAN DEL NORTE | ZAMBOANGA CITY | Caraga | N | Self-Build - BTS | Yes | MAR | Q1 | JAN | Q1 | (03) PSH | 7/21: FOC cut 7/10 | 7/02: FOC splicing ongoing | 6.9022 | 122.0625 | AN + LEOSAT | 33
P602 | 2021T8_RgPM_BrgyDorLun_Claveria | RFI'd | 03. For Awarding | ERICSSON | EDOTCO | 19. Site Clearing | JISEDAI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-09-03 | 2026-05-05 | 52 | 2026-07-23 | 2026-05-03 | 2026-10-10 | MISAMIS ORIENTAL | CLAVERIA | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 06 RTB (FOC/ AN/ ... | 8.6414 | 124.8907 | Fiber Extension | 27
E369 | 2023T8_RgPM_BrgyDorSan_Dipolog City (Capital) | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | LDIC | 22. Rebar Installation | HT | (05) Permitting | Fiber Extension | 2026-10-16 | 2026-04-24 | 37 | 2026-01-09 | 2026-05-14 | 2026-10-11 | ZAMBOANGA DEL NORTE | DIPOLOG CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 8.6178 | 123.347 | Fiber Extension | 27
D389 | 2021T8_RgPM_BrgyDorCab_Cagayan De Oro City (Capital) | TRS Ready | 03. For Awarding | ERICSSON | ALLIANCE | 23. Concrete Pouring | COMTEL | (05) Permitting | MW | 2026-06-30 | 2026-03-28 | 35 | 2026-10-07 | 2026-09-08 | 2026-04-05 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/18: Power energized | 6/15: MW dish installed | 8.4897 | 124.5976 | MW | 24
T50 | 2023CapSite_BrgyBagNal_Lamitan City (Capital) | RTB'd | 03. For Awarding | ERICSSON | UNITY | 19. Site Clearing | JISEDAI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-07-11 | 2026-01-31 | 123 | 2026-12-04 | 2026-09-07 | 2026-01-09 | LANAO DEL SUR | LAMITAN CITY (CAPITAL) | BARMM | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 01 Precon/ Eng'g Hold | 6.6812 | 122.1333 | AN + LEOSAT | 24
E549 | 2020CDNPH_BrgyCabBur_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | na | (01) Precon/ Eng'g Hold | MW | 2026-04-09 | 2026-11-14 | 134 | 2026-05-10 | 2026-07-01 | 2026-05-17 | MISAMIS OCCIDENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 10/17: Pending site | 6.9508 | 122.0695 | MW | 27
O232 | 2020CDNPH_BrgyNalSig_Cagayan De Oro City (Capital) | s-RFI & TRS Ready | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 23. Concrete Pouring | na | (05) Permitting | Fiber Extension | 2026-11-23 | 2026-01-05 | 43 | 2026-02-12 | 2026-09-13 | 2026-08-11 | ZAMBOANGA DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 5/20: LOS check passed | 8.4381 | 124.5962 | Fiber Extension | 27
L942 | 2021CapSite_BrgyLunBur_Gingoog City | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-04-02 | 2026-06-11 | 4 | 2026-04-17 | 2026-10-28 | 2026-03-15 | MISAMIS ORIENTAL | GINGOOG CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 9/19: Awaiting tower | 8.8494 | 125.0741 | Fiber Extension | 24
Q855 | 2024M2SC2_BrgyKawBal_Cagayan De Oro City (Capital) | s-RFI | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 22. Rebar Installation | NOKIA | (00) Not Started | AN + LEOSAT | 2026-04-29 | 2026-02-08 | 87 | 2026-11-06 | 2026-11-11 | 2026-11-01 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 5/12: CR applied, AP | 6/24: for checking | 8.4302 | 124.6246 | AN + LEOSAT | 25
K234 | 2024CDNPH_BrgyBalSig_Cagayan De Oro City (Capital) | s-RFI & TRS Ready | 36. TRFS | NOKIA | UNITY | 19. Site Clearing | HUAXIN | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-12 | 2026-05-18 | 39 | 2026-07-14 | 2026-12-31 | 2026-11-21 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.4598 | 124.6644 | Fiber Extension | 23
E456 | 2022CDNPH_BrgySanBag_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 24. Backfilling | na | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-02-22 | 2026-01-14 | 22 | 2026-07-01 | 2026-10-11 | 2026-02-17 | SULU | ZAMBOANGA CITY | BARMM | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 9/19: Awaiting tower | 6.918 | 122.0643 | AN + LEOSAT | 27
G398 | 2024CapSite_BrgyLunLib_Gingoog City | TRS Ready | 03. For Awarding | ERICSSON | FRONTIER | 22. Rebar Installation | HUAXIN | (02) Survey | AN + LEOSAT | 2026-03-16 | 2026-02-02 | 42 | 2026-08-11 | 2026-05-22 | 2026-08-04 | BUKIDNON | GINGOOG CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 6/24: for checking | 8.8384 | 125.1254 | AN + LEOSAT | 24
O641 | 2024M2SC2_BrgyLibLun_Cagayan De Oro City (Capital) | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 19. Site Clearing | FADI | (02) Survey | AN + LEOSAT | 2026-06-18 | 2026-08-14 | 85 | 2026-08-09 | 2026-11-30 | 2026-11-01 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 12/10: no pole yet | 8.4532 | 124.6424 | AN + LEOSAT | 33
F182 | 2022M2SC2_BrgyTagBur_Ozamiz City | RFI'd | 03. For Awarding | NOKIA | ALLIANCE | 22. Rebar Installation | FADI | (02) Survey | AN + LEOSAT | 2026-07-06 | 2026-02-28 | 144 | 2026-04-13 | 2026-10-31 | 2026-10-07 | SULU | OZAMIZ CITY | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 8.1222 | 123.8527 | AN + LEOSAT | 33
D449 | 2020CDNPH_BrgySigBal_General Luna | For Awarding | 36. TRFS | ERICSSON | PHILTOWER | 20. Excavation | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-07-13 | 2026-02-07 | 114 | 2026-11-03 | 2026-09-03 | 2026-10-26 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/21: FOC cut 7/10 | 6/24: for checking | 9.7432 | 126.1377 | AN + LEOSAT | 25
L38 | 2024CDNPH_BrgyLibNal_El Salvador City | Awarded | 27. sRFI Pending Pole | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | HT | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-10-16 | 2026-11-27 | 102 | 2026-06-19 | 2026-08-09 | 2026-02-24 | LANAO DEL SUR | EL SALVADOR CITY | BARMM | Y | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (03) PSH | 6/28: For MOS. Pull | 6/24: for checking | 8.5848 | 124.4904 | Fiber Extension | 25
Q705 | 2021T8_RgPM_BrgyDorKaw_Iligan City | TRFS | 14. LC Applied | ERICSSON | ALLIANCE | 24. Backfilling | na | (01) Precon/ Eng'g Hold | MW/FSO | 2026-01-13 | 2026-09-05 | 26 | 2026-06-01 | 2026-08-01 | 2026-02-13 | BASILAN | ILIGAN CITY | BARMM | Y | TowerCo (Macro) - BTS | Yes | MAY | Q2 | JAN | Q1 | (05.3) TSSR Approved | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 8.2492 | 124.2444 | MW/FSO | 33
L495 | 2023CDNPH_BrgySanDor_Cagayan De Oro City (Capital) | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 19. Site Clearing | ZTE | (00) Not Started | MW/FSO | 2026-11-28 | 2026-02-25 | 42 | 2026-05-05 | 2026-09-22 | 2026-03-31 | TAWI-TAWI | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 8.4753 | 124.5989 | MW/FSO | 25
P415 | 2021Capsite_BrgyNalSig_Cagayan De Oro City (Capital) | Awarded | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (05) Permitting | AN + LEOSAT | 2026-07-19 | 2026-01-03 | 54 | 2026-04-16 | 2026-05-23 | 2026-12-27 | SULU | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | Y | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 12/10: no pole yet | 8.4634 | 124.6426 | AN + LEOSAT | 27
F202 | 2020M2SC2_BrgyTagNal_Claveria | Awarded | 03. For Awarding | NOKIA | EDOTCO | 22. Rebar Installation | FADI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-10-28 | 2026-02-28 | 89 | 2026-06-30 | 2026-08-23 | 2026-11-13 | ZAMBOANGA DEL SUR | CLAVERIA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (05.1) TSSR for Submission | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 8.6056 | 124.9303 | AN + LEOSAT | 24
F121 | 2022Capsite_BrgySanBag_Isabela City | TRFS | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 23. Concrete Pouring | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-08-05 | 2026-04-06 | 124 | 2026-11-22 | 2026-10-03 | 2026-12-22 | SURIGAO DEL NORTE | ISABELA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | MAY | Q2 | (05.3) TSSR Approved | 7/05: Integration complete | 7/02: FOC splicing ongoing | 6.6948 | 121.9341 | AN + LEOSAT | 23
F863 | 2024M2SC2_BrgyMalKaw_Iligan City | s-RFI | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | FADI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-07-29 | 2026-12-17 | 125 | 2026-08-01 | 2026-12-30 | 2026-08-16 | MISAMIS ORIENTAL | ILIGAN CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 7/02: FOC splicing ongoing | 8.204 | 124.235 | AN + LEOSAT | 24
E34 | 2021CDNPH_BrgyCabTag_Zamboanga City | TRFS | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 18. RTB for Mobilization | COMTEL | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-10-21 | 2026-02-28 | 68 | 2026-10-06 | 2026-07-07 | 2026-10-05 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | Yes | DEC | Q4 | MAY | Q2 | (01.1) TBD | 7/18: Power energized | 7/02: FOC splicing ongoing | 6.8825 | 122.0648 | Fiber Extension | 24
T770 | 2022Capsite_BrgyMalDor_Davao City | TSSR | 03. For Awarding | ERICSSON | LDIC | 19. Site Clearing | COMTEL | (00) Not Started | MW | 2026-04-18 | 2026-10-29 | 89 | 2026-12-30 | 2026-11-09 | 2026-11-20 | MISAMIS OCCIDENTAL | DAVAO CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 7.2174 | 125.4305 | MW | 25
P61 | 2022T8_RgPM_BrgyCabTag_Malaybalay City (Capital) | RFI'd | 32. Ongoing Integration | ERICSSON | EDOTCO | 22. Rebar Installation | HUAXIN | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-09-21 | 2026-12-14 | 24 | 2026-03-11 | 2026-07-30 | 2026-01-31 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 8.1716 | 125.1379 | MW/FSO | 23
F849 | 2023Capsite_BrgyDorBag_Zamboanga City | RTB'd | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | ZTE | (05) Permitting | MW/FSO | 2026-12-22 | 2026-07-08 | 116 | 2026-09-07 | 2026-06-17 | 2026-10-25 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (05.3) TSSR Approved | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 6.9013 | 122.0945 | MW/FSO | 27
F871 | 2024CapSite_BrgyBalLun_Butuan City (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 22. Rebar Installation | HUAXIN | (02) Survey | MW | 2026-10-17 | 2026-09-06 | 87 | 2026-12-16 | 2026-01-25 | 2026-01-24 | MISAMIS ORIENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Micro) - BTS | Yes | DEC | Q4 | MAR | Q1 | (03) PSH | 6/20: RFI with Perm | 06 RTB (FOC/ AN/ ... | 8.935 | 125.5109 | MW | 33
K1 | 2021M2SC2_BrgyBurBag_Labason | TRS Ready | 03. For Awarding | ERICSSON | LDIC | 22. Rebar Installation | ZTE | (02) Survey | MW/FSO | 2026-02-12 | 2026-07-10 | 42 | 2026-01-27 | 2026-07-22 | 2026-11-17 | ZAMBOANGA DEL SUR | LABASON | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 5/12: CR applied, AP | 10/17: Pending site | 8.0574 | 122.5238 | MW/FSO | 27
D489 | 2021CapSite_BrgyLibLun_Zamboanga City | s-RFI | 03. For Awarding | ERICSSON | FRONTIER | 22. Rebar Installation | ZTE | (05) Permitting | MW | 2026-09-02 | 2026-02-06 | 58 | 2026-07-16 | 2026-02-15 | 2026-02-22 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 12/10: no pole yet | 6.8948 | 122.1049 | MW | 25
P896 | 2021Capsite_BrgySanCab_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | NOKIA | PHILTOWER | 23. Concrete Pouring | HT | (01) Precon/ Eng'g Hold | MW | 2026-07-30 | 2026-11-12 | 113 | 2026-04-22 | 2026-02-14 | 2026-02-21 | TAWI-TAWI | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 9/19: Awaiting tower | 8.4381 | 124.6152 | MW | 33
F811 | 2021Capsite_BrgyTagNal_Cagayan De Oro City (Capital) | TRFS | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | HUAXIN | (00) Not Started | MW/FSO | 2026-04-16 | 2026-09-23 | 130 | 2026-04-07 | 2026-07-20 | 2026-06-01 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | JUL | Q3 | (01) For Awarding | 6/18: Permanent Po | 12/10: no pole yet | 8.4724 | 124.6396 | MW/FSO | 27
G116 | 2023Capsite_BrgyNalLib_Surigao City (Capital) | LGU Permitting | 03. For Awarding | NOKIA | LDIC | 19. Site Clearing | HT | (02) Survey | MW | 2026-07-18 | 2026-10-19 | 107 | 2026-07-07 | 2026-10-07 | 2026-12-16 | BUKIDNON | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 9/19: Awaiting tower | 9.767 | 125.521 | MW | 24
B15 | 2021CDNPH_BrgyMalSig_Malaybalay City (Capital) | LGU Permitting | 03. For Awarding | NOKIA | FRONTIER | 26. ODU Pad / Electrical | na | (05) Permitting | AN + LEOSAT | 2026-12-26 | 2026-07-25 | 21 | 2026-11-24 | 2026-10-02 | 2026-10-03 | COTABATO (NORTH COTABATO) | MALAYBALAY CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 01 Precon/ Eng'g Hold | 8.1971 | 125.1152 | AN + LEOSAT | 25
D998 | 2024Capsite_BrgyKawBal_Cagayan De Oro City (Capital) | RTB'd | 14. LC Applied | ERICSSON | UNITY | 26. ODU Pad / Electrical | JISEDAI | (00) Not Started | MW | 2026-02-14 | 2026-08-11 | 29 | 2026-08-21 | 2026-11-10 | 2026-11-08 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/18: Power energized | 3/31: Brgy Permit S | 8.4863 | 124.6206 | MW | 23
A725 | 2020Capsite_BrgyBagDor_Valencia City | LGU Permitting | 03. For Awarding | NOKIA | PHILTOWER | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | MW/FSO | 2026-03-06 | 2026-05-18 | 30 | 2026-01-16 | 2026-06-21 | 2026-08-08 | MISAMIS ORIENTAL | VALENCIA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | MAY | Q2 | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 10/17: Pending site | 7.8815 | 125.13 | MW/FSO | 24
B509 | 2024M2SC2_BrgyKawMal_Pagadian City (Capital) | TRS Ready | 18. RTB for Mobilization | NOKIA | FRONTIER | 20. Excavation | HUAXIN | (00) Not Started | Fiber Extension | 2026-04-27 | 2026-09-18 | 0 | 2026-01-23 | 2026-01-07 | 2026-05-06 | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 01 Precon/ Eng'g Hold | 7.8592 | 123.4293 | Fiber Extension | 23
P936 | 2021M2SC2_BrgyKawLun_El Salvador City | LGU Permitting | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | HT | (00) Not Started | Fiber Extension | 2026-04-02 | 2026-04-25 | 132 | 2026-01-24 | 2026-07-25 | 2026-02-05 | TAWI-TAWI | EL SALVADOR CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 8.5422 | 124.5351 | Fiber Extension | 33
K9 | 2021CDNPH_BrgyTagLib_Cagayan De Oro City (Capital) | RTB'd | 03. For Awarding | NOKIA | FRONTIER | 22. Rebar Installation | COMTEL | (01) Precon/ Eng'g Hold | MW | 2026-03-19 | 2026-01-04 | 104 | 2026-01-13 | 2026-04-30 | 2026-10-05 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 8.4247 | 124.6506 | MW | 23
O745 | 2020CDNPH_BrgyLunCab_Zamboanga City | LGU Permitting | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 19. Site Clearing | TBD | (02) Survey | Fiber Extension | 2026-01-23 | 2026-04-29 | 133 | 2026-07-31 | 2026-12-25 | 2026-07-10 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 6.9286 | 122.0525 | Fiber Extension | 24
G77 | 2024T8_RgPM_BrgyMalBal_Iligan City | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 18. RTB for Mobilization | HT | (05) Permitting | MW/FSO | 2026-06-12 | 2026-08-20 | 69 | 2026-04-30 | 2026-02-08 | 2026-04-14 | MISAMIS ORIENTAL | ILIGAN CITY | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 9/19: Awaiting tower | 8.2173 | 124.2572 | MW/FSO | 23
F417 | 2024CapSite_BrgyKawLun_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | ZTE | (00) Not Started | MW | 2026-12-18 | 2026-06-05 | 10 | 2026-04-21 | 2026-06-17 | 2026-03-17 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 12/10: no pole yet | 6.8844 | 122.1091 | MW | 25
E267 | 2020Capsite_BrgyBalDor_Cagayan De Oro City (Capital) | TSSR | 03. For Awarding | ERICSSON | PHILTOWER | 18. RTB for Mobilization | TBD | (00) Not Started | Fiber Extension | 2026-02-01 | 2026-04-24 | 33 | 2026-04-12 | 2026-07-25 | 2026-07-10 | COTABATO (NORTH COTABATO) | CAGAYAN DE ORO CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 8.4347 | 124.6347 | Fiber Extension | 25
A67 | 2023Capsite_BrgySigBag_Cagayan De Oro City (Capital) | TSSR | 32. Ongoing Integration | ERICSSON | FRONTIER | 23. Concrete Pouring | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-07-22 | 2026-09-12 | 7 | 2026-07-15 | 2026-12-16 | 2026-08-07 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 8.4181 | 124.6715 | AN + LEOSAT | 24
C36 | 2024T8_RgPM_BrgyLibLun_Zamboanga City | TRFS | 07. Site Survey | ERICSSON | PHILTOWER | 24. Backfilling | COMTEL | (00) Not Started | Fiber Extension | 2026-05-24 | 2026-07-16 | 35 | 2026-08-03 | 2026-04-13 | 2026-11-26 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAR | Q1 | (05.1) TSSR for Submission | 7/18: Power energized | 6/24: for checking | 6.9344 | 122.0913 | Fiber Extension | 27
G801 | 2023CDNPH_BrgyCabDor_Surigao City (Capital) | Awarded | 32. Ongoing Integration | NOKIA | PHILTOWER | 23. Concrete Pouring | HUAXIN | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-06-13 | 2026-11-02 | 56 | 2026-01-16 | 2026-05-24 | 2026-01-30 | MISAMIS ORIENTAL | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | SEP | Q3 | N/A | N/A | (02) Ongoing Survey | 6/30: Fiber link verified | 3/31: Brgy Permit S | 9.7416 | 125.5052 | Fiber Extension | 23
C103 | 2021Capsite_BrgyTagCab_Isabela City | LGU Permitting | 03. For Awarding | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (02) Survey | MW | 2026-04-01 | 2026-05-02 | 81 | 2026-12-24 | 2026-07-03 | 2026-10-30 | TAWI-TAWI | ISABELA CITY | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 9/19: Awaiting tower | 6.6974 | 121.9615 | MW | 24
D857 | 2024M2SC2_BrgyTagBag_Dipolog City (Capital) | LGU Permitting | 18. RTB for Mobilization | ERICSSON | FRONTIER | 20. Excavation | JISEDAI | (00) Not Started | AN + LEOSAT | 2026-01-01 | 2026-06-19 | 51 | 2026-03-08 | 2026-06-24 | 2026-04-01 | COTABATO (NORTH COTABATO) | DIPOLOG CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 7/02: FOC splicing ongoing | 8.5923 | 123.3383 | AN + LEOSAT | 23
P114 | 2022T8_RgPM_BrgySanKaw_Isabela City | TRFS | 36. TRFS | NOKIA | FRONTIER | 22. Rebar Installation | HT | (01) Precon/ Eng'g Hold | MW | 2026-08-12 | 2026-11-24 | 124 | 2026-11-29 | 2026-06-12 | 2026-03-31 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | NOV | Q4 | JUN | Q2 | (06.2) Brgy Secured | 6/18: Permanent Po | 9/19: Awaiting tower | 6.6764 | 121.9867 | MW | 24
D682 | 2021T8_RgPM_BrgyBalTag_Labason | Awarded | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 19. Site Clearing | FADI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-04-04 | 2026-11-05 | 81 | 2026-11-10 | 2026-04-24 | 2026-11-24 | MISAMIS ORIENTAL | LABASON | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/20: RfId site 7/15 | 5/20: LOS check passed | 8.0771 | 122.5008 | Fiber Extension | 23
D356 | 2021CDNPH_BrgyNalSan_Zamboanga City | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 20. Excavation | JISEDAI | (00) Not Started | MW/FSO | 2026-05-12 | 2026-02-25 | 0 | 2026-01-25 | 2026-07-17 | 2026-08-13 | SURIGAO DEL SUR | ZAMBOANGA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01) For Awarding | 7/21: FOC cut 7/10 | 06 RTB (FOC/ AN/ ... | 6.9343 | 122.092 | MW/FSO | 27
G360 | 2023T8_RgPM_BrgySanDor_Claveria | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | NOKIA | (02) Survey | Fiber Extension | 2026-06-13 | 2026-05-14 | 26 | 2026-02-07 | 2026-06-25 | 2026-03-29 | COTABATO (NORTH COTABATO) | CLAVERIA | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (05.1) TSSR for Submission | 6/30: Fiber link verified | 06 RTB (FOC/ AN/ ... | 8.5949 | 124.9016 | Fiber Extension | 24
B347 | 2024T8_RgPM_BrgyDorBur_Dipolog City (Capital) | For Awarding | 36. TRFS | ERICSSON | EDOTCO | 20. Excavation | FADI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-21 | 2026-06-19 | 52 | 2026-04-08 | 2026-07-29 | 2026-12-23 | MISAMIS ORIENTAL | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | NOV | Q4 | N/A | N/A | (04) For Re-award | 6/20: RFI with Perm | 6/24: for checking | 8.5595 | 123.3668 | Fiber Extension | 25
A403 | 2024T8_RgPM_BrgyDorBag_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-13 | 2026-02-19 | 6 | 2026-04-16 | 2026-03-29 | 2026-11-23 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 12/10: no pole yet | 8.4226 | 124.6494 | AN + LEOSAT | 27
K501 | 2020CDNPH_BrgyNalCab_Zamboanga City | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 23. Concrete Pouring | HT | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-01-23 | 2026-05-15 | 112 | 2026-08-27 | 2026-05-15 | 2026-04-26 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 10/17: Pending site | 6.8908 | 122.0481 | AN + LEOSAT | 25
B685 | 2024CDNPH_BrgyBalLib_General Luna | For Awarding | 27. sRFI Pending Pole | NOKIA | FRONTIER | 23. Concrete Pouring | na | (05) Permitting | AN + LEOSAT | 2026-10-21 | 2026-05-01 | 121 | 2026-06-03 | 2026-02-10 | 2026-07-22 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 9/19: Awaiting tower | 9.7513 | 126.1317 | AN + LEOSAT | 27
T636 | 2020Capsite_BrgySigDor_Bongao (Capital) | TSSR | 32. Ongoing Integration | ERICSSON | EDOTCO | 18. RTB for Mobilization | JISEDAI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-08-05 | 2026-02-10 | 111 | 2026-04-14 | 2026-11-18 | 2026-03-17 | LANAO DEL SUR | BONGAO (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/20: RFI with Perm | 6/24: for checking | 5.0282 | 119.7535 | Fiber Extension | 25
B398 | 2023T8_RgPM_BrgyCabKaw_General Luna | LGU Permitting | 32. Ongoing Integration | NOKIA | PHILTOWER | 18. RTB for Mobilization | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-02-27 | 2026-08-01 | 38 | 2026-03-17 | 2026-10-18 | 2026-10-29 | SULU | GENERAL LUNA | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 10/17: Pending site | 9.7847 | 126.1319 | AN + LEOSAT | 27
E889 | 2022T8_RgPM_BrgyBalTag_Dipolog City (Capital) | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | NOKIA | (01) Precon/ Eng'g Hold | MW/FSO | 2026-07-26 | 2026-03-15 | 102 | 2026-01-20 | 2026-07-22 | 2026-06-19 | SURIGAO DEL NORTE | DIPOLOG CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 6/24: for checking | 8.6048 | 123.3239 | MW/FSO | 23
F21 | 2022CDNPH_BrgyTagSig_Butuan City (Capital) | RTB'd | 07. Site Survey | ERICSSON | EDOTCO | 20. Excavation | TBD | (02) Survey | AN + LEOSAT | 2026-06-14 | 2026-05-18 | 106 | 2026-11-06 | 2026-11-27 | 2026-02-15 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 10/17: Pending site | 8.9107 | 125.5403 | AN + LEOSAT | 25
P529 | 2020CDNPH_BrgyCabBag_Ipil (Capital) | TRS Ready | 30. RFI/TRS Ready | ERICSSON | UNITY | 23. Concrete Pouring | TBD | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-03-30 | 2026-04-09 | 51 | 2026-01-30 | 2026-05-08 | 2026-01-17 | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 5/20: LOS check passed | 7.7577 | 122.62 | Fiber Extension | 23
K518 | 2020M2SC2_BrgyNalMal_Pagadian City (Capital) | Awarded | 06. With Issue | ERICSSON | PHILTOWER | 23. Concrete Pouring | TBD | (05) Permitting | MW/FSO | 2026-06-26 | 2026-03-25 | 66 | 2026-12-19 | 2026-02-16 | 2026-05-26 | SURIGAO DEL NORTE | PAGADIAN CITY (CAPITAL) | Caraga | Y | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (05.3) TSSR Approved | 7/18: Power energized | 6/15: MW dish installed | 7.8121 | 123.3972 | MW/FSO | 24
D878 | 2021Capsite_BrgyNalLun_Lamitan City (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 18. RTB for Mobilization | NOKIA | (05) Permitting | MW | 2026-11-28 | 2026-03-30 | 2 | 2026-04-25 | 2026-05-10 | 2026-11-08 | ZAMBOANGA DEL SUR | LAMITAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 01 Precon/ Eng'g Hold | 6.6637 | 122.1659 | MW | 23
E224 | 2022M2SC2_BrgyNalCab_Cagayan De Oro City (Capital) | RTB'd | 07. Site Survey | NOKIA | FRONTIER | 24. Backfilling | HT | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-06-02 | 2026-12-17 | 27 | 2026-09-04 | 2026-02-02 | 2026-06-22 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 8.481 | 124.6454 | MW/FSO | 25
T306 | 2021Capsite_BrgyCabLun_Cagayan De Oro City (Capital) | For Awarding | 28. sRFI/TRS Ready | NOKIA | FRONTIER | 22. Rebar Installation | TBD | (00) Not Started | AN + LEOSAT | 2026-06-01 | 2026-05-13 | 107 | 2026-07-27 | 2026-07-18 | 2026-01-19 | AGUSAN DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | Self-Build - BTS | Yes | JUN | Q2 | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 12/10: no pole yet | 8.4261 | 124.5991 | AN + LEOSAT | 27
T548 | 2022M2SC2_BrgyCabTag_Cagayan De Oro City (Capital) | For Awarding | 28. sRFI/TRS Ready | NOKIA | FRONTIER | 19. Site Clearing | COMTEL | (01) Precon/ Eng'g Hold | MW/FSO | 2026-10-14 | 2026-04-04 | 85 | 2026-12-02 | 2026-02-15 | 2026-04-24 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 10/17: Pending site | 8.4551 | 124.6498 | MW/FSO | 23
F381 | 2024CDNPH_BrgyTagDor_Cagayan De Oro City (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | ZTE | (05) Permitting | MW | 2026-09-14 | 2026-03-03 | 97 | 2026-09-29 | 2026-06-02 | 2026-07-31 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 6/15: MW dish installed | 8.4223 | 124.6124 | MW | 33
Q915 | 2021M2SC2_BrgyKawBur_Zamboanga City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | TBD | (02) Survey | Fiber Extension | 2026-01-03 | 2026-08-20 | 70 | 2026-04-18 | 2026-03-28 | 2026-10-23 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.1) TSSR for Submission | 6/18: Permanent Po | 10/17: Pending site | 6.8999 | 122.1181 | Fiber Extension | 27
G649 | 2023M2SC2_BrgyBalDor_Malaybalay City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 20. Excavation | HT | (00) Not Started | MW/FSO | 2026-09-29 | 2026-04-08 | 4 | 2026-12-13 | 2026-01-03 | 2026-11-17 | BUKIDNON | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/20: RfId site 7/15 | 12/10: no pole yet | 8.1412 | 125.1249 | MW/FSO | 24
B393 | 2024T8_RgPM_BrgyTagBag_Claveria | TRFS | 06. With Issue | ERICSSON | FRONTIER | 22. Rebar Installation | COMTEL | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-08-11 | 2026-12-18 | 34 | 2026-06-25 | 2026-09-08 | 2026-07-03 | ZAMBOANGA SIBUGAY | CLAVERIA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | MAR | Q1 | (05.1) TSSR for Submission | 5/12: CR applied, AP | 9/19: Awaiting tower | 8.5813 | 124.8671 | MW/FSO | 24
D230 | 2021Capsite_BrgyBurMal_El Salvador City | RTB'd | 14. LC Applied | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | NOKIA | (05) Permitting | MW/FSO | 2026-10-01 | 2026-11-16 | 12 | 2026-11-01 | 2026-01-25 | 2026-12-05 | COTABATO (NORTH COTABATO) | EL SALVADOR CITY | SOCCSKSARGEN | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/05: Integration complete | 6/24: for checking | 8.5271 | 124.5001 | MW/FSO | 25
B561 | 2023CDNPH_BrgyBurBag_Zamboanga City | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | ZTE | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-11-15 | 2026-11-07 | 35 | 2026-08-03 | 2026-02-23 | 2026-09-19 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | Self-Build - BTS | Yes | MAR | Q1 | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 6.9455 | 122.064 | MW/FSO | 27
D624 | 2022Capsite_BrgyCabLun_Zamboanga City | Awarded | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | na | (05) Permitting | MW | 2026-12-19 | 2026-09-04 | 84 | 2026-05-01 | 2026-01-02 | 2026-01-07 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (05.3) TSSR Approved | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 6.9405 | 122.0466 | MW | 23
C973 | 2024CapSite_BrgySanBur_Lamitan City (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 23. Concrete Pouring | HUAXIN | (02) Survey | AN + LEOSAT | 2026-01-26 | 2026-02-21 | 44 | 2026-01-21 | 2026-05-29 | 2026-07-04 | SURIGAO DEL NORTE | LAMITAN CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | APR | Q2 | (06.1) Brgy Applied | 6/18: Permanent Po | 12/10: no pole yet | 6.6707 | 122.097 | AN + LEOSAT | 23
A10 | 2021Capsite_BrgyKawSig_Zamboanga City | For Awarding | 36. TRFS | NOKIA | FRONTIER | 26. ODU Pad / Electrical | ZTE | (02) Survey | MW/FSO | 2026-04-04 | 2026-02-28 | 102 | 2026-07-24 | 2026-08-22 | 2026-05-20 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 01 Precon/ Eng'g Hold | 6.9496 | 122.0921 | MW/FSO | 24
B136 | 2021CapSite_BrgySanBal_Marawi City (Capital) | For Awarding | 32. Ongoing Integration | NOKIA | UNITY | 20. Excavation | FADI | (02) Survey | Fiber Extension | 2026-12-17 | 2026-03-08 | 123 | 2026-09-07 | 2026-02-27 | 2026-07-30 | BUKIDNON | MARAWI CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 9/19: Awaiting tower | 7.9736 | 124.2719 | Fiber Extension | 27
T538 | 2024T8_RgPM_BrgyLunNal_Valencia City | For Awarding | 03. For Awarding | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | ZTE | (05) Permitting | MW | 2026-09-04 | 2026-06-27 | 98 | 2026-03-18 | 2026-10-13 | 2026-11-10 | ZAMBOANGA DEL SUR | VALENCIA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 12/10: no pole yet | 7.9014 | 125.1039 | MW | 27
K891 | 2020Capsite_BrgySigDor_Zamboanga City | RFI'd | 36. TRFS | ERICSSON | FRONTIER | 22. Rebar Installation | NOKIA | (06) RTB (FOC/AN/Pending) | MW | 2026-10-09 | 2026-11-26 | 96 | 2026-07-26 | 2026-05-01 | 2026-02-10 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 06 RTB (FOC/ AN/ ... | 6.9517 | 122.0464 | MW | 24
K324 | 2023CapSite_BrgyBurNal_Butuan City (Capital) | Awarded | 36. TRFS | ERICSSON | FRONTIER | 19. Site Clearing | na | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-02-16 | 2026-11-06 | 77 | 2026-09-18 | 2026-10-15 | 2026-04-16 | BUKIDNON | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | MAR | Q1 | N/A | N/A | (02) Ongoing Survey | 6/18: Permanent Po | 9/19: Awaiting tower | 8.9727 | 125.5152 | Fiber Extension | 23
D865 | 2022M2SC2_BrgyCabLib_Cagayan De Oro City (Capital) | s-RFI | 03. For Awarding | ERICSSON | UNITY | 19. Site Clearing | ZTE | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-06-24 | 2026-07-01 | 74 | 2026-10-08 | 2026-09-25 | 2026-07-11 | COTABATO (NORTH COTABATO) | CAGAYAN DE ORO CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (02) Ongoing Survey | 7/20: RfId site 7/15 | 5/20: LOS check passed | 8.4463 | 124.6689 | Fiber Extension | 24
O761 | 2020M2SC2_BrgyTagLib_Zamboanga City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-04-08 | 2026-06-23 | 27 | 2026-08-01 | 2026-01-24 | 2026-11-21 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | Self-Build - BTS | Yes | MAR | Q1 | MAY | Q2 | (05.1) TSSR for Submission | 6/28: For MOS. Pull | 5/20: LOS check passed | 6.9031 | 122.0699 | AN + LEOSAT | 27
Q980 | 2021T8_RgPM_BrgyDorMal_Bongao (Capital) | TSSR | 14. LC Applied | NOKIA | EDOTCO | 18. RTB for Mobilization | COMTEL | (06) RTB (FOC/AN/Pending) | MW | 2026-12-21 | 2026-10-24 | 44 | 2026-03-07 | 2026-02-23 | 2026-07-18 | ZAMBOANGA DEL SUR | BONGAO (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 01 Precon/ Eng'g Hold | 5.0803 | 119.7965 | MW | 23
G624 | 2022Capsite_BrgyBalKaw_Cagayan De Oro City (Capital) | RFI'd | 36. TRFS | ERICSSON | ALLIANCE | 20. Excavation | FADI | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-12-26 | 2026-10-08 | 80 | 2026-12-31 | 2026-10-11 | 2026-11-20 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 8.4661 | 124.6557 | MW/FSO | 33
T136 | 2024Capsite_BrgyCabBur_Pagadian City (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | ALLIANCE | 24. Backfilling | COMTEL | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-12-12 | 2026-10-01 | 73 | 2026-08-05 | 2026-01-07 | 2026-09-25 | ZAMBOANGA SIBUGAY | PAGADIAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | JAN | Q1 | APR | Q2 | (05.3) TSSR Approved | 7/21: FOC cut 7/10 | 6/24: for checking | 7.7947 | 123.4527 | AN + LEOSAT | 24
E769 | 2022Capsite_BrgyNalTag_Zamboanga City | LGU Permitting | 03. For Awarding | ERICSSON | UNITY | 22. Rebar Installation | JISEDAI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-07-03 | 2026-08-20 | 26 | 2026-11-12 | 2026-12-12 | 2026-10-15 | ZAMBOANGA DEL NORTE | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 5/20: LOS check passed | 6.8861 | 122.1144 | Fiber Extension | 27
O295 | 2023CapSite_BrgyBalSig_Iligan City | TSSR | 32. Ongoing Integration | NOKIA | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-04-26 | 2026-11-21 | 94 | 2026-10-29 | 2026-10-07 | 2026-11-05 | ZAMBOANGA DEL NORTE | ILIGAN CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (05.3) TSSR Approved | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 8.2008 | 124.2385 | AN + LEOSAT | 27
C986 | 2024Capsite_BrgySanBal_Zamboanga City | RFI'd | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 22. Rebar Installation | TBD | (01) Precon/ Eng'g Hold | MW/FSO | 2026-01-03 | 2026-06-19 | 119 | 2026-12-30 | 2026-03-21 | 2026-01-21 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 10/17: Pending site | 6.9287 | 122.1032 | MW/FSO | 25
T309 | 2024M2SC2_BrgyCabKaw_Malaybalay City (Capital) | For Awarding | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 20. Excavation | na | (00) Not Started | MW | 2026-08-01 | 2026-10-06 | 137 | 2026-07-26 | 2026-02-17 | 2026-06-28 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 6/15: MW dish installed | 8.1718 | 125.1023 | MW | 25
P634 | 2023T8_RgPM_BrgyCabNal_Cagayan De Oro City (Capital) | For Awarding | 06. With Issue | ERICSSON | UNITY | 23. Concrete Pouring | JISEDAI | (06) RTB (FOC/AN/Pending) | MW | 2026-01-21 | 2026-12-16 | 82 | 2026-07-15 | 2026-02-28 | 2026-07-17 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | DEC | Q4 | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 10/17: Pending site | 8.4446 | 124.6206 | MW | 24
P384 | 2024T8_RgPM_BrgyDorSig_Zamboanga City | TSSR | 14. LC Applied | ERICSSON | LDIC | 20. Excavation | HT | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-02-19 | 2026-03-27 | 137 | 2026-10-01 | 2026-01-04 | 2026-11-17 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (05.3) TSSR Approved | 6/30: Fiber link verified | 12/10: no pole yet | 6.8837 | 122.0938 | Fiber Extension | 23
G856 | 2021CapSite_BrgyCabBur_Malaybalay City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | UNITY | 20. Excavation | NOKIA | (05) Permitting | MW/FSO | 2026-01-20 | 2026-02-14 | 18 | 2026-01-28 | 2026-04-02 | 2026-05-09 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 9/19: Awaiting tower | 8.1846 | 125.1657 | MW/FSO | 33
G462 | 2023M2SC2_BrgyKawMal_Zamboanga City | TRS Ready | 07. Site Survey | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | ZTE | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-12-25 | 2026-02-07 | 91 | 2026-09-15 | 2026-02-24 | 2026-05-29 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 6.8919 | 122.1126 | Fiber Extension | 33
G405 | 2023CapSite_BrgyBagCab_Cagayan De Oro City (Capital) | TRS Ready | 36. TRFS | ERICSSON | UNITY | 18. RTB for Mobilization | na | (02) Survey | MW | 2026-06-02 | 2026-12-13 | 95 | 2026-01-06 | 2026-10-11 | 2026-10-12 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/30: Fiber link verified | 9/19: Awaiting tower | 8.4232 | 124.6248 | MW | 23
L970 | 2022CapSite_BrgyLunBur_Isabela City | RFI'd | 14. LC Applied | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | na | (01) Precon/ Eng'g Hold | MW | 2026-04-05 | 2026-04-24 | 64 | 2026-04-10 | 2026-02-28 | 2026-04-03 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 6.6678 | 121.952 | MW | 25
L473 | 2020T8_RgPM_BrgyTagNal_Lamitan City (Capital) | s-RFI & TRS Ready | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | COMTEL | (02) Survey | MW/FSO | 2026-03-07 | 2026-12-10 | 60 | 2026-02-21 | 2026-05-26 | 2026-11-14 | AGUSAN DEL NORTE | LAMITAN CITY (CAPITAL) | Caraga | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 01 Precon/ Eng'g Hold | 6.6351 | 122.1497 | MW/FSO | 27
E711 | 2021T8_RgPM_BrgyLibSig_Butuan City (Capital) | s-RFI | 18. RTB for Mobilization | ERICSSON | EDOTCO | 20. Excavation | NOKIA | (02) Survey | MW | 2026-04-24 | 2026-12-31 | 111 | 2026-05-22 | 2026-07-04 | 2026-03-10 | SULU | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 6/24: for checking | 8.9617 | 125.562 | MW | 25
E499 | 2020T8_RgPM_BrgyBagNal_Butuan City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | LDIC | 20. Excavation | na | (01) Precon/ Eng'g Hold | MW/FSO | 2026-11-17 | 2026-02-09 | 19 | 2026-01-10 | 2026-09-17 | 2026-11-20 | AGUSAN DEL SUR | BUTUAN CITY (CAPITAL) | Caraga | Y | Self-Build - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 6/24: for checking | 8.9536 | 125.5458 | MW/FSO | 24
A565 | 2024CDNPH_BrgyCabDor_Malaybalay City (Capital) | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-09-14 | 2026-09-19 | 23 | 2026-07-23 | 2026-07-06 | 2026-09-15 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | JAN | Q1 | MAY | Q2 | (06.1) Brgy Applied | 6/28: For MOS. Pull | 6/24: for checking | 8.1957 | 125.1414 | AN + LEOSAT | 25
C776 | 2021T8_RgPM_BrgyDorBag_Surigao City (Capital) | Awarded | 18. RTB for Mobilization | NOKIA | EDOTCO | 26. ODU Pad / Electrical | TBD | (05) Permitting | MW/FSO | 2026-01-21 | 2026-04-23 | 124 | 2026-04-29 | 2026-02-02 | 2026-05-16 | AGUSAN DEL NORTE | SURIGAO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/20: RFI with Perm | 3/31: Brgy Permit S | 9.7671 | 125.4918 | MW/FSO | 23
F398 | 2023M2SC2_BrgyMalSig_Zamboanga City | LGU Permitting | 36. TRFS | ERICSSON | UNITY | 24. Backfilling | HUAXIN | (02) Survey | MW | 2026-07-12 | 2026-12-01 | 96 | 2026-07-07 | 2026-10-28 | 2026-12-01 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 6/24: for checking | 6.9374 | 122.0466 | MW | 24
G362 | 2023CDNPH_BrgySigDor_Davao City | Awarded | 03. For Awarding | NOKIA | LDIC | 23. Concrete Pouring | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-09-21 | 2026-11-26 | 71 | 2026-04-19 | 2026-03-18 | 2026-04-06 | BASILAN | DAVAO CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/20: RFI with Perm | 5/20: LOS check passed | 7.2036 | 125.4352 | Fiber Extension | 23
G831 | 2020CDNPH_BrgyDorNal_Ipil (Capital) | TRFS | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 20. Excavation | FADI | (00) Not Started | MW | 2026-01-23 | 2026-03-07 | 146 | 2026-10-31 | 2026-03-24 | 2026-03-10 | MISAMIS ORIENTAL | IPIL (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | MAR | Q1 | (04) For Re-award | 7/05: Integration complete | 6/15: MW dish installed | 7.7688 | 122.5994 | MW | 24
E945 | 2024Capsite_BrgyBalLib_Isabela City | RTB'd | 03. For Awarding | ERICSSON | EDOTCO | 20. Excavation | COMTEL | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-09-04 | 2026-03-29 | 56 | 2026-07-30 | 2026-11-04 | 2026-03-15 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.6949 | 121.9982 | AN + LEOSAT | 27
T351 | 2024M2SC2_BrgyLibSan_Iligan City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-03-18 | 2026-11-07 | 24 | 2026-04-01 | 2026-09-01 | 2026-11-11 | MISAMIS ORIENTAL | ILIGAN CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | JUL | Q3 | (01) For Awarding | 6/18: Permanent Po | 10/17: Pending site | 8.2327 | 124.2842 | AN + LEOSAT | 25
B494 | 2024Capsite_BrgyCabMal_Dipolog City (Capital) | RTB'd | 30. RFI/TRS Ready | NOKIA | PHILTOWER | 18. RTB for Mobilization | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-28 | 2026-09-04 | 97 | 2026-06-29 | 2026-10-29 | 2026-12-23 | AGUSAN DEL SUR | DIPOLOG CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 5/12: CR applied, AP | 10/17: Pending site | 8.5529 | 123.3518 | AN + LEOSAT | 23
B291 | 2024T8_RgPM_BrgyBalTag_Cagayan De Oro City (Capital) | RTB'd | 30. RFI/TRS Ready | ERICSSON | UNITY | 18. RTB for Mobilization | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-09-24 | 2026-01-04 | 96 | 2026-12-02 | 2026-04-16 | 2026-12-19 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 5/12: CR applied, AP | 6/24: for checking | 8.4268 | 124.6598 | Fiber Extension | 24
E268 | 2023T8_RgPM_BrgyLibKaw_Zamboanga City | TRFS | 27. sRFI Pending Pole | ERICSSON | ALLIANCE | 23. Concrete Pouring | na | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-02 | 2026-07-09 | 143 | 2026-10-12 | 2026-09-05 | 2026-05-10 | TAWI-TAWI | ZAMBOANGA CITY | BARMM | N | Self-Build - BTS | Yes | JAN | Q1 | JUN | Q2 | (01.1) TBD | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 6.9496 | 122.1086 | AN + LEOSAT | 25
T122 | 2023Capsite_BrgySigBur_Pagadian City (Capital) | TRFS | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 23. Concrete Pouring | HT | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-03-24 | 2026-07-19 | 1 | 2026-02-16 | 2026-03-16 | 2026-08-30 | TAWI-TAWI | PAGADIAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | MAY | Q2 | (05.2) TSSR for Approval | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 7.7917 | 123.4363 | Fiber Extension | 33
Q39 | 2023M2SC2_BrgyLibNal_Cagayan De Oro City (Capital) | TRS Ready | 14. LC Applied | NOKIA | FRONTIER | 18. RTB for Mobilization | TBD | (05) Permitting | AN + LEOSAT | 2026-01-06 | 2026-04-14 | 132 | 2026-05-27 | 2026-04-10 | 2026-01-18 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 8.4335 | 124.6695 | AN + LEOSAT | 23
A369 | 2020Capsite_BrgyBagSan_Zamboanga City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-09-23 | 2026-01-08 | 17 | 2026-02-16 | 2026-10-09 | 2026-05-26 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | TowerCo (Micro) - BTS | Yes | MAR | Q1 | MAY | Q2 | (04) For Re-award | 6/18: Permanent Po | 6/15: MW dish installed | 6.8854 | 122.0568 | MW | 27
E232 | 2021T8_RgPM_BrgyDorBal_Cagayan De Oro City (Capital) | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 24. Backfilling | ZTE | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-09-15 | 2026-05-31 | 87 | 2026-03-01 | 2026-09-20 | 2026-05-12 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 8.4657 | 124.6242 | Fiber Extension | 24
K789 | 2022Capsite_BrgySigDor_Butuan City (Capital) | For Awarding | 14. LC Applied | NOKIA | LDIC | 23. Concrete Pouring | ZTE | (02) Survey | Fiber Extension | 2026-07-15 | 2026-11-21 | 56 | 2026-12-13 | 2026-12-26 | 2026-04-28 | BASILAN | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 8.9263 | 125.5373 | Fiber Extension | 23
E255 | 2020CDNPH_BrgyBalNal_Iligan City | TRS Ready | 03. For Awarding | ERICSSON | PHILTOWER | 20. Excavation | COMTEL | (02) Survey | MW/FSO | 2026-04-22 | 2026-10-21 | 68 | 2026-04-04 | 2026-12-16 | 2026-04-08 | COTABATO (NORTH COTABATO) | ILIGAN CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 6/15: MW dish installed | 8.2521 | 124.241 | MW/FSO | 23
D208 | 2024Capsite_BrgyKawBag_Zamboanga City | TSSR | 06. With Issue | ERICSSON | LDIC | 26. ODU Pad / Electrical | COMTEL | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-10-05 | 2026-01-22 | 123 | 2026-07-10 | 2026-11-14 | 2026-06-11 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | N | Self-Build - BTS | Yes | SEP | Q3 | N/A | N/A | (05.3) TSSR Approved | 5/12: CR applied, AP | 12/10: no pole yet | 6.9499 | 122.0748 | Fiber Extension | 33
G228 | 2021T8_RgPM_BrgyMalCab_Iligan City | For Awarding | 36. TRFS | ERICSSON | EDOTCO | 19. Site Clearing | na | (02) Survey | AN + LEOSAT | 2026-12-18 | 2026-03-31 | 117 | 2026-03-03 | 2026-12-24 | 2026-09-23 | AGUSAN DEL SUR | ILIGAN CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 9/19: Awaiting tower | 8.1975 | 124.245 | AN + LEOSAT | 27
Q104 | 2022CDNPH_BrgyLibTag_Zamboanga City | LGU Permitting | 03. For Awarding | NOKIA | FRONTIER | 22. Rebar Installation | COMTEL | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-07-07 | 2026-04-05 | 127 | 2026-08-06 | 2026-04-18 | 2026-08-03 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 06 RTB (FOC/ AN/ ... | 6.9337 | 122.0472 | MW/FSO | 33
Q135 | 2021T8_RgPM_BrgySanBur_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | MW | 2026-03-18 | 2026-08-31 | 2 | 2026-04-01 | 2026-08-04 | 2026-09-13 | TAWI-TAWI | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 8.4472 | 124.6365 | MW | 24
E576 | 2020T8_RgPM_BrgyBalSan_Cagayan De Oro City (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 22. Rebar Installation | COMTEL | (00) Not Started | AN + LEOSAT | 2026-06-21 | 2026-05-14 | 92 | 2026-07-04 | 2026-10-14 | 2026-10-13 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | MAY | Q2 | (06.2) Brgy Secured | 7/18: Power energized | 9/19: Awaiting tower | 8.4142 | 124.5992 | AN + LEOSAT | 25
Q204 | 2024T8_RgPM_BrgyNalSig_Zamboanga City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (05) Permitting | AN + LEOSAT | 2026-02-10 | 2026-07-15 | 73 | 2026-08-26 | 2026-11-20 | 2026-03-16 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 01 Precon/ Eng'g Hold | 6.9297 | 122.0885 | AN + LEOSAT | 23
B82 | 2022Capsite_BrgyLunKaw_Isabela City | For Awarding | 14. LC Applied | ERICSSON | UNITY | 24. Backfilling | FADI | (02) Survey | AN + LEOSAT | 2026-07-05 | 2026-10-28 | 133 | 2026-08-19 | 2026-07-31 | 2026-03-27 | LANAO DEL NORTE | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01) For Awarding | 7/18: Power energized | 6/24: for checking | 6.6885 | 121.9718 | AN + LEOSAT | 24
O718 | 2021CapSite_BrgyBagBal_Zamboanga City | Awarded | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | na | (00) Not Started | Fiber Extension | 2026-07-23 | 2026-09-26 | 21 | 2026-02-23 | 2026-05-15 | 2026-11-13 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/05: Integration complete | 10/17: Pending site | 6.8979 | 122.0927 | Fiber Extension | 24
D756 | 2023CDNPH_BrgyNalBag_Claveria | TRFS | 06. With Issue | NOKIA | ALLIANCE | 19. Site Clearing | NOKIA | (02) Survey | MW/FSO | 2026-09-01 | 2026-08-28 | 138 | 2026-05-20 | 2026-10-08 | 2026-08-16 | MISAMIS ORIENTAL | CLAVERIA | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | MAR | Q1 | (06.2) Brgy Secured | 5/12: CR applied, AP | 3/31: Brgy Permit S | 8.6493 | 124.8822 | MW/FSO | 27
T899 | 2023T8_RgPM_BrgyCabNal_Isabela City | TSSR | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 20. Excavation | ZTE | (05) Permitting | MW/FSO | 2026-07-07 | 2026-07-31 | 66 | 2026-03-21 | 2026-06-05 | 2026-01-06 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 6.6684 | 121.9489 | MW/FSO | 23
K548 | 2023CapSite_BrgySigDor_Lamitan City (Capital) | s-RFI | 07. Site Survey | ERICSSON | ALLIANCE | 18. RTB for Mobilization | HUAXIN | (06) RTB (FOC/AN/Pending) | MW | 2026-01-04 | 2026-10-08 | 95 | 2026-04-07 | 2026-07-30 | 2026-10-15 | BUKIDNON | LAMITAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (02) Ongoing Survey | 5/12: CR applied, AP | 6/24: for checking | 6.6464 | 122.1381 | MW | 33
G226 | 2020CDNPH_BrgyBalNal_Pagadian City (Capital) | For Awarding | 27. sRFI Pending Pole | NOKIA | ALLIANCE | 24. Backfilling | HUAXIN | (02) Survey | MW/FSO | 2026-07-31 | 2026-04-07 | 17 | 2026-04-04 | 2026-03-11 | 2026-05-29 | BASILAN | PAGADIAN CITY (CAPITAL) | BARMM | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 7.8353 | 123.4349 | MW/FSO | 25
D329 | 2021CapSite_BrgyMalCab_Cagayan De Oro City (Capital) | s-RFI & TRS Ready | 18. RTB for Mobilization | ERICSSON | EDOTCO | 22. Rebar Installation | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-01-05 | 2026-04-30 | 23 | 2026-03-19 | 2026-01-08 | 2026-09-10 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/18: Power energized | 9/19: Awaiting tower | 8.4668 | 124.6492 | AN + LEOSAT | 23
F475 | 2022CapSite_BrgySanBag_Surigao City (Capital) | Awarded | 14. LC Applied | ERICSSON | ALLIANCE | 19. Site Clearing | na | (05) Permitting | MW | 2026-04-09 | 2026-05-09 | 97 | 2026-01-07 | 2026-03-04 | 2026-05-08 | LANAO DEL NORTE | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 5/20: LOS check passed | 9.7491 | 125.5107 | MW | 23
B534 | 2023Capsite_BrgyBalNal_Davao City | RFI'd | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-05-10 | 2026-09-04 | 76 | 2026-04-12 | 2026-07-04 | 2026-01-27 | BASILAN | DAVAO CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (02) Ongoing Survey | 6/30: Fiber link verified | 12/10: no pole yet | 7.1684 | 125.4426 | Fiber Extension | 25
A172 | 2024CDNPH_BrgySanBal_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | EDOTCO | 24. Backfilling | COMTEL | (06) RTB (FOC/AN/Pending) | MW | 2026-07-10 | 2026-02-15 | 63 | 2026-03-22 | 2026-09-13 | 2026-02-16 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 12/10: no pole yet | 6.9478 | 122.1162 | MW | 24
A62 | 2021CDNPH_BrgyBurCab_Arakan | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 22. Rebar Installation | na | (02) Survey | AN + LEOSAT | 2026-04-09 | 2026-01-11 | 96 | 2026-07-03 | 2026-03-10 | 2026-05-09 | SULU | ARAKAN | BARMM | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 6/15: MW dish installed | 5.9834 | 121.0018 | AN + LEOSAT | 33
K195 | 2021T8_RgPM_BrgyCabKaw_Dipolog City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | na | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-09-29 | 2026-03-21 | 115 | 2026-06-01 | 2026-05-15 | 2026-10-05 | MISAMIS ORIENTAL | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 9/19: Awaiting tower | 8.6047 | 123.304 | Fiber Extension | 23
C905 | 2024CapSite_BrgyKawLib_Marawi City (Capital) | RFI'd | 14. LC Applied | ERICSSON | UNITY | 26. ODU Pad / Electrical | na | (05) Permitting | MW | 2026-09-26 | 2026-12-16 | 127 | 2026-10-10 | 2026-03-20 | 2026-11-10 | ZAMBOANGA DEL SUR | MARAWI CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 7.9731 | 124.2545 | MW | 24
T69 | 2021CapSite_BrgyBagMal_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 19. Site Clearing | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-12-03 | 2026-09-08 | 134 | 2026-11-16 | 2026-12-26 | 2026-10-30 | ZAMBOANGA DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 5/20: LOS check passed | 8.4715 | 124.6496 | AN + LEOSAT | 27
D672 | 2020M2SC2_BrgyDorNal_Isabela City | TRFS | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | HT | (00) Not Started | MW/FSO | 2026-09-28 | 2026-01-21 | 18 | 2026-06-05 | 2026-02-09 | 2026-04-21 | TAWI-TAWI | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | FEB | Q1 | (01) For Awarding | 7/05: Integration complete | 6/24: for checking | 6.6727 | 121.98 | MW/FSO | 24
D539 | 2024Capsite_BrgyNalBag_Zamboanga City | TRS Ready | 14. LC Applied | ERICSSON | ALLIANCE | 24. Backfilling | HT | (05) Permitting | AN + LEOSAT | 2026-02-23 | 2026-03-27 | 46 | 2026-10-09 | 2026-07-25 | 2026-09-16 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/05: Integration complete | 6/15: MW dish installed | 6.8964 | 122.1134 | AN + LEOSAT | 25
F564 | 2022CDNPH_BrgyBalNal_Isabela City | For Awarding | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | na | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-10-09 | 2026-05-11 | 92 | 2026-08-20 | 2026-08-18 | 2026-07-23 | LANAO DEL SUR | ISABELA CITY | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 3/31: Brgy Permit S | 6.6955 | 121.9677 | AN + LEOSAT | 33
E7 | 2021CDNPH_BrgyLunKaw_Isabela City | Awarded | 14. LC Applied | ERICSSON | LDIC | 24. Backfilling | na | (06) RTB (FOC/AN/Pending) | MW | 2026-02-18 | 2026-01-20 | 117 | 2026-07-02 | 2026-03-21 | 2026-03-12 | DAVAO DEL SUR | ISABELA CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 12/10: no pole yet | 6.7266 | 121.9884 | MW | 25
E95 | 2023T8_RgPM_BrgyLibLun_Cagayan De Oro City (Capital) | TRFS | 03. For Awarding | ERICSSON | ALLIANCE | 20. Excavation | COMTEL | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-11-01 | 2026-11-25 | 76 | 2026-01-20 | 2026-10-23 | 2026-07-15 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | Y | TowerCo (Macro) - BTS | Yes | JAN | Q1 | APR | Q2 | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 06 RTB (FOC/ AN/ ... | 8.4228 | 124.6251 | Fiber Extension | 27
G427 | 2021CapSite_BrgyBurNal_Cagayan De Oro City (Capital) | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 24. Backfilling | NOKIA | (02) Survey | MW | 2026-06-17 | 2026-09-15 | 56 | 2026-03-20 | 2026-01-26 | 2026-12-11 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 12/10: no pole yet | 8.4883 | 124.6589 | MW | 24
B228 | 2022M2SC2_BrgySigBal_General Luna | s-RFI & TRS Ready | 18. RTB for Mobilization | ERICSSON | FRONTIER | 23. Concrete Pouring | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-05-15 | 2026-02-13 | 102 | 2026-09-14 | 2026-08-11 | 2026-12-24 | COTABATO (NORTH COTABATO) | GENERAL LUNA | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 9.7899 | 126.1776 | AN + LEOSAT | 23
Q201 | 2024T8_RgPM_BrgyBurCab_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | FADI | (02) Survey | Fiber Extension | 2026-02-27 | 2026-12-10 | 105 | 2026-08-05 | 2026-07-07 | 2026-06-28 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 3/31: Brgy Permit S | 6.9174 | 122.0917 | Fiber Extension | 27
C359 | 2023T8_RgPM_BrgyLibBag_Valencia City | TRFS | 30. RFI/TRS Ready | ERICSSON | LDIC | 20. Excavation | JISEDAI | (02) Survey | MW | 2026-02-13 | 2026-02-27 | 13 | 2026-05-05 | 2026-11-14 | 2026-03-17 | TAWI-TAWI | VALENCIA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | JUN | Q2 | (06.1) Brgy Applied | 7/05: Integration complete | 5/20: LOS check passed | 7.9429 | 125.065 | MW | 25
K24 | 2021CDNPH_BrgyBurCab_Surigao City (Capital) | Awarded | 06. With Issue | ERICSSON | PHILTOWER | 18. RTB for Mobilization | HUAXIN | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-11-15 | 2026-03-14 | 4 | 2026-07-12 | 2026-10-26 | 2026-12-06 | TAWI-TAWI | SURIGAO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/20: RFI with Perm | 6/15: MW dish installed | 9.7799 | 125.4924 | AN + LEOSAT | 24
O633 | 2020CDNPH_BrgyDorNal_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 22. Rebar Installation | HT | (00) Not Started | Fiber Extension | 2026-05-30 | 2026-11-29 | 98 | 2026-04-29 | 2026-07-14 | 2026-09-18 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 06 RTB (FOC/ AN/ ... | 6.8853 | 122.1138 | Fiber Extension | 25
B191 | 2024Capsite_BrgyDorCab_Iligan City | TRS Ready | 18. RTB for Mobilization | ERICSSON | FRONTIER | 24. Backfilling | HUAXIN | (02) Survey | AN + LEOSAT | 2026-07-21 | 2026-03-22 | 4 | 2026-06-27 | 2026-12-17 | 2026-06-30 | SURIGAO DEL NORTE | ILIGAN CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 5/20: LOS check passed | 8.2551 | 124.2438 | AN + LEOSAT | 23
P64 | 2023CDNPH_BrgyMalCab_Davao City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | TBD | (00) Not Started | AN + LEOSAT | 2026-09-24 | 2026-12-14 | 58 | 2026-08-02 | 2026-05-04 | 2026-10-21 | ZAMBOANGA SIBUGAY | DAVAO CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | JUN | Q2 | (02) Ongoing Survey | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 7.1914 | 125.489 | AN + LEOSAT | 27
L135 | 2021Capsite_BrgyLibCab_Balingasag | TSSR | 06. With Issue | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-03-16 | 2026-12-02 | 144 | 2026-03-22 | 2026-06-12 | 2026-02-04 | COTABATO (NORTH COTABATO) | BALINGASAG | SOCCSKSARGEN | N | TowerCo (Micro) - BTS | Yes | MAY | Q2 | N/A | N/A | (05.3) TSSR Approved | 6/28: For MOS. Pull | 01 Precon/ Eng'g Hold | 8.7203 | 124.7796 | AN + LEOSAT | 27
C745 | 2022CapSite_BrgyBalSig_Zamboanga City | Awarded | 07. Site Survey | ERICSSON | UNITY | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | MW | 2026-02-24 | 2026-03-09 | 47 | 2026-01-14 | 2026-11-10 | 2026-11-12 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | Self-Build - BTS | Yes | DEC | Q4 | N/A | N/A | (03) PSH | 6/12: Awaiting transmission hookup | 3/31: Brgy Permit S | 6.9398 | 122.0493 | MW | 33
T27 | 2020CDNPH_BrgyBurDor_Zamboanga City | RTB'd | 03. For Awarding | NOKIA | ALLIANCE | 23. Concrete Pouring | HT | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-09-09 | 2026-08-31 | 35 | 2026-03-25 | 2026-04-09 | 2026-04-26 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 10/17: Pending site | 6.9124 | 122.087 | AN + LEOSAT | 25
O688 | 2021Capsite_BrgySanBag_Zamboanga City | For Awarding | 07. Site Survey | NOKIA | PHILTOWER | 22. Rebar Installation | COMTEL | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-07-27 | 2026-01-22 | 97 | 2026-06-10 | 2026-07-21 | 2026-11-10 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 6/24: for checking | 6.952 | 122.0793 | AN + LEOSAT | 33
P40 | 2020T8_RgPM_BrgyDorSig_Dipolog City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | PHILTOWER | 23. Concrete Pouring | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-09-22 | 2026-11-19 | 12 | 2026-04-08 | 2026-05-30 | 2026-08-14 | MISAMIS ORIENTAL | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 7/02: FOC splicing ongoing | 8.5793 | 123.3787 | AN + LEOSAT | 27
E628 | 2024CapSite_BrgyBagDor_Cagayan De Oro City (Capital) | LGU Permitting | 03. For Awarding | ERICSSON | UNITY | 19. Site Clearing | TBD | (06) RTB (FOC/AN/Pending) | MW | 2026-07-21 | 2026-07-31 | 82 | 2026-08-19 | 2026-01-13 | 2026-04-02 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | Yes | JUN | Q2 | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 6/24: for checking | 8.4875 | 124.6529 | MW | 24
B257 | 2021CDNPH_BrgyBurSig_Bongao (Capital) | RTB'd | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | HT | (00) Not Started | AN + LEOSAT | 2026-09-19 | 2026-11-10 | 40 | 2026-07-13 | 2026-10-09 | 2026-07-14 | SURIGAO DEL NORTE | BONGAO (CAPITAL) | Caraga | Y | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (05.1) TSSR for Submission | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 5.0341 | 119.8096 | AN + LEOSAT | 33
C167 | 2021Capsite_BrgySigBur_Dipolog City (Capital) | For Awarding | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | COMTEL | (02) Survey | MW | 2026-03-02 | 2026-03-09 | 51 | 2026-01-02 | 2026-11-15 | 2026-05-10 | SURIGAO DEL NORTE | DIPOLOG CITY (CAPITAL) | Caraga | Y | TowerCo (Micro) - BTS | Yes | DEC | Q4 | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 8.6261 | 123.3365 | MW | 24
Q904 | 2021M2SC2_BrgyLunLib_Iligan City | Awarded | 32. Ongoing Integration | ERICSSON | PHILTOWER | 19. Site Clearing | NOKIA | (01) Precon/ Eng'g Hold | MW/FSO | 2026-11-14 | 2026-11-18 | 142 | 2026-04-17 | 2026-01-26 | 2026-04-05 | LANAO DEL SUR | ILIGAN CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.1987 | 124.2382 | MW/FSO | 33
T592 | 2022T8_RgPM_BrgyKawSan_Zamboanga City | TRFS | 36. TRFS | ERICSSON | PHILTOWER | 20. Excavation | TBD | (02) Survey | MW | 2026-08-22 | 2026-10-24 | 92 | 2026-01-19 | 2026-02-17 | 2026-06-03 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | JUL | Q3 | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 6/24: for checking | 6.9374 | 122.0989 | MW | 25
L67 | 2023CDNPH_BrgyBagSan_Ipil (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 24. Backfilling | JISEDAI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-25 | 2026-10-20 | 135 | 2026-02-14 | 2026-09-05 | 2026-12-19 | SURIGAO DEL NORTE | IPIL (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 6/15: MW dish installed | 7.765 | 122.6014 | Fiber Extension | 25
Q639 | 2021CDNPH_BrgyLibSig_Lamitan City (Capital) | TRS Ready | 07. Site Survey | NOKIA | UNITY | 23. Concrete Pouring | COMTEL | (01) Precon/ Eng'g Hold | MW | 2026-12-29 | 2026-05-29 | 49 | 2026-01-01 | 2026-03-02 | 2026-01-13 | LANAO DEL NORTE | LAMITAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 6/24: for checking | 6.6789 | 122.1502 | MW | 27
G424 | 2022CapSite_BrgyKawCab_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | HUAXIN | (02) Survey | Fiber Extension | 2026-06-07 | 2026-06-03 | 129 | 2026-10-09 | 2026-06-15 | 2026-01-04 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 6.9562 | 122.0896 | Fiber Extension | 25
A853 | 2021Capsite_BrgyKawSig_General Luna | RTB'd | 18. RTB for Mobilization | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | TBD | (05) Permitting | MW | 2026-11-18 | 2026-08-24 | 137 | 2026-06-21 | 2026-08-25 | 2026-07-31 | SULU | GENERAL LUNA | BARMM | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 12/10: no pole yet | 9.7589 | 126.1657 | MW | 33
F569 | 2020T8_RgPM_BrgyLunLib_Cagayan De Oro City (Capital) | RFI'd | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 20. Excavation | HUAXIN | (00) Not Started | MW/FSO | 2026-07-12 | 2026-11-17 | 136 | 2026-03-26 | 2026-10-20 | 2026-11-07 | AGUSAN DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 8.4374 | 124.6195 | MW/FSO | 33
O879 | 2020CDNPH_BrgyTagBal_Gingoog City | RFI'd | 30. RFI/TRS Ready | ERICSSON | LDIC | 22. Rebar Installation | COMTEL | (02) Survey | MW | 2026-09-26 | 2026-06-04 | 44 | 2026-02-27 | 2026-07-11 | 2026-01-20 | MISAMIS ORIENTAL | GINGOOG CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/30: Fiber link verified | 3/31: Brgy Permit S | 8.8349 | 125.1416 | MW | 24
L158 | 2022Capsite_BrgyDorBur_Zamboanga City | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | ZTE | (06) RTB (FOC/AN/Pending) | MW | 2026-04-16 | 2026-01-19 | 117 | 2026-07-18 | 2026-09-25 | 2026-03-01 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 01 Precon/ Eng'g Hold | 6.9334 | 122.1157 | MW | 23
B342 | 2020M2SC2_BrgySanCab_Valencia City | TRS Ready | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 22. Rebar Installation | JISEDAI | (02) Survey | MW | 2026-04-09 | 2026-05-27 | 70 | 2026-09-30 | 2026-06-13 | 2026-08-14 | SURIGAO DEL NORTE | VALENCIA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 7.9067 | 125.1097 | MW | 33
Q574 | 2020T8_RgPM_BrgyLunCab_Zamboanga City | For Awarding | 03. For Awarding | NOKIA | FRONTIER | 20. Excavation | HUAXIN | (06) RTB (FOC/AN/Pending) | MW | 2026-03-29 | 2026-02-06 | 79 | 2026-11-10 | 2026-06-23 | 2026-10-04 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 7/02: FOC splicing ongoing | 6.9072 | 122.0482 | MW | 24
A89 | 2023M2SC2_BrgyBagBur_Butuan City (Capital) | s-RFI & TRS Ready | 27. sRFI Pending Pole | NOKIA | FRONTIER | 22. Rebar Installation | JISEDAI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-08-27 | 2026-10-18 | 33 | 2026-02-17 | 2026-12-24 | 2026-08-28 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 5/20: LOS check passed | 8.9357 | 125.539 | Fiber Extension | 27
K238 | 2021Capsite_BrgyLibTag_Marawi City (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HT | (02) Survey | AN + LEOSAT | 2026-09-07 | 2026-01-16 | 16 | 2026-09-01 | 2026-02-27 | 2026-06-29 | SULU | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | Yes | AUG | Q3 | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 6/24: for checking | 8.0057 | 124.2967 | AN + LEOSAT | 25
Q131 | 2020T8_RgPM_BrgyBalBur_Cagayan De Oro City (Capital) | TRFS | 06. With Issue | ERICSSON | PHILTOWER | 19. Site Clearing | HUAXIN | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-07-25 | 2026-10-30 | 105 | 2026-05-03 | 2026-11-14 | 2026-05-05 | AGUSAN DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | FEB | Q1 | (03) PSH | 6/28: For MOS. Pull | 10/17: Pending site | 8.4476 | 124.6517 | AN + LEOSAT | 25
O606 | 2023M2SC2_BrgyLibKaw_Cagayan De Oro City (Capital) | LGU Permitting | 06. With Issue | ERICSSON | UNITY | 19. Site Clearing | COMTEL | (00) Not Started | AN + LEOSAT | 2026-06-16 | 2026-10-12 | 24 | 2026-08-16 | 2026-04-01 | 2026-06-07 | DAVAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 12/10: no pole yet | 8.4815 | 124.6148 | AN + LEOSAT | 33
G336 | 2020M2SC2_BrgySanLun_Valencia City | RFI'd | 18. RTB for Mobilization | NOKIA | LDIC | 26. ODU Pad / Electrical | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-08-20 | 2026-09-30 | 74 | 2026-07-19 | 2026-11-12 | 2026-10-23 | MISAMIS ORIENTAL | VALENCIA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 9/19: Awaiting tower | 7.9342 | 125.1189 | MW | 25
T312 | 2022M2SC2_BrgySanLib_Claveria | Awarded | 06. With Issue | NOKIA | ISON | 23. Concrete Pouring | TBD | (02) Survey | Fiber Extension | 2026-07-09 | 2026-10-09 | 13 | 2026-01-01 | 2026-12-27 | 2026-10-14 | ZAMBOANGA SIBUGAY | CLAVERIA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/18: Permanent Po | 6/24: for checking | 8.6151 | 124.8551 | Fiber Extension | 27
O605 | 2022M2SC2_BrgyBurBal_Gingoog City | TSSR | 03. For Awarding | ERICSSON | PHILTOWER | 20. Excavation | TBD | (05) Permitting | MW | 2026-04-07 | 2026-10-12 | 98 | 2026-07-04 | 2026-08-02 | 2026-03-20 | AGUSAN DEL NORTE | GINGOOG CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/30: Fiber link verified | 3/31: Brgy Permit S | 8.7927 | 125.1167 | MW | 23
O907 | 2023M2SC2_BrgyBagSan_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | LDIC | 18. RTB for Mobilization | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-08-21 | 2026-09-18 | 108 | 2026-10-10 | 2026-08-19 | 2026-07-16 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 6.8974 | 122.099 | MW | 33
O243 | 2022T8_RgPM_BrgyBalCab_Isabela City | TSSR | 18. RTB for Mobilization | ERICSSON | EDOTCO | 24. Backfilling | COMTEL | (02) Survey | Fiber Extension | 2026-10-25 | 2026-09-04 | 20 | 2026-03-14 | 2026-09-27 | 2026-05-24 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.677 | 121.954 | Fiber Extension | 27
K646 | 2024CapSite_BrgySigLib_Bongao (Capital) | TRFS | 03. For Awarding | NOKIA | FRONTIER | 22. Rebar Installation | na | (00) Not Started | AN + LEOSAT | 2026-08-21 | 2026-09-20 | 120 | 2026-10-21 | 2026-06-19 | 2026-08-04 | ZAMBOANGA DEL SUR | BONGAO (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | JAN | Q1 | (05.1) TSSR for Submission | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 5.0322 | 119.7997 | AN + LEOSAT | 24
O312 | 2022T8_RgPM_BrgyMalNal_Zamboanga City | RTB'd | 36. TRFS | NOKIA | FRONTIER | 19. Site Clearing | HUAXIN | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-05-27 | 2026-09-06 | 21 | 2026-03-06 | 2026-09-16 | 2026-02-09 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 5/20: LOS check passed | 6.9366 | 122.0626 | Fiber Extension | 23
A760 | 2024CapSite_BrgyBagLib_Cagayan De Oro City (Capital) | s-RFI | 36. TRFS | ERICSSON | FRONTIER | 20. Excavation | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-04-03 | 2026-09-28 | 8 | 2026-06-25 | 2026-02-13 | 2026-03-16 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 9/19: Awaiting tower | 8.4745 | 124.5945 | AN + LEOSAT | 33
G244 | 2021M2SC2_BrgyLunLib_General Luna | TRFS | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | ZTE | (00) Not Started | MW | 2026-08-26 | 2026-07-24 | 121 | 2026-06-04 | 2026-09-01 | 2026-09-30 | AGUSAN DEL NORTE | GENERAL LUNA | Caraga | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | JAN | Q1 | (04) For Re-award | 6/30: Fiber link verified | 06 RTB (FOC/ AN/ ... | 9.8079 | 126.124 | MW | 25
L892 | 2020M2SC2_BrgyTagDor_Cagayan De Oro City (Capital) | s-RFI & TRS Ready | 07. Site Survey | ERICSSON | EDOTCO | 26. ODU Pad / Electrical | NOKIA | (00) Not Started | MW/FSO | 2026-08-10 | 2026-11-09 | 69 | 2026-06-21 | 2026-05-19 | 2026-05-17 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 9/19: Awaiting tower | 8.4836 | 124.6511 | MW/FSO | 33
O248 | 2021T8_RgPM_BrgyCabKaw_Cagayan De Oro City (Capital) | RFI'd | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | NOKIA | (00) Not Started | Fiber Extension | 2026-07-30 | 2026-02-20 | 134 | 2026-02-23 | 2026-12-17 | 2026-08-17 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 01 Precon/ Eng'g Hold | 8.4834 | 124.6513 | Fiber Extension | 24
Q95 | 2024CapSite_BrgyNalLun_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | TBD | (05) Permitting | MW | 2026-02-26 | 2026-12-23 | 47 | 2026-05-10 | 2026-05-31 | 2026-08-28 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/18: Permanent Po | 10/17: Pending site | 8.4591 | 124.6109 | MW | 25
T789 | 2022CDNPH_BrgyBagSan_El Salvador City | TRFS | 07. Site Survey | ERICSSON | FRONTIER | 22. Rebar Installation | NOKIA | (02) Survey | MW/FSO | 2026-04-02 | 2026-08-14 | 17 | 2026-09-09 | 2026-04-13 | 2026-11-09 | MISAMIS ORIENTAL | EL SALVADOR CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | JAN | Q1 | (06.1) Brgy Applied | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 8.5866 | 124.5408 | MW/FSO | 23
G224 | 2020T8_RgPM_BrgyDorBur_Zamboanga City | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (05) Permitting | Fiber Extension | 2026-09-12 | 2026-03-18 | 0 | 2026-01-20 | 2026-12-07 | 2026-07-19 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 6.9044 | 122.0922 | Fiber Extension | 33
L725 | 2023M2SC2_BrgyBalSig_Balingasag | Awarded | 18. RTB for Mobilization | NOKIA | FRONTIER | 23. Concrete Pouring | COMTEL | (00) Not Started | MW/FSO | 2026-06-20 | 2026-12-16 | 77 | 2026-07-25 | 2026-01-29 | 2026-11-20 | MISAMIS ORIENTAL | BALINGASAG | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 8.7802 | 124.7643 | MW/FSO | 27
K779 | 2021CDNPH_BrgyBagCab_Lamitan City (Capital) | LGU Permitting | 06. With Issue | ERICSSON | UNITY | 22. Rebar Installation | FADI | (00) Not Started | MW/FSO | 2026-09-07 | 2026-02-13 | 112 | 2026-04-08 | 2026-03-13 | 2026-01-19 | TAWI-TAWI | LAMITAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 6.6865 | 122.1714 | MW/FSO | 24
B812 | 2022T8_RgPM_BrgyDorCab_Isabela City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | HT | (00) Not Started | AN + LEOSAT | 2026-03-02 | 2026-04-19 | 133 | 2026-08-23 | 2026-12-14 | 2026-10-02 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | N | Self-Build - BTS | Yes | FEB | Q1 | MAR | Q1 | (02) Ongoing Survey | 6/20: RFI with Perm | 6/24: for checking | 6.6891 | 121.9753 | AN + LEOSAT | 33
K670 | 2023CapSite_BrgyLibMal_Zamboanga City | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | NOKIA | (02) Survey | Fiber Extension | 2026-08-22 | 2026-11-09 | 43 | 2026-10-30 | 2026-02-02 | 2026-02-24 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | Yes | MAY | Q2 | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 7/02: FOC splicing ongoing | 6.8824 | 122.0591 | Fiber Extension | 27
D437 | 2023CDNPH_BrgyKawSan_Marawi City (Capital) | For Awarding | 03. For Awarding | ERICSSON | ALLIANCE | 18. RTB for Mobilization | JISEDAI | (00) Not Started | MW | 2026-06-21 | 2026-02-02 | 30 | 2026-05-21 | 2026-03-14 | 2026-08-01 | MISAMIS ORIENTAL | MARAWI CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 10/17: Pending site | 8.0096 | 124.3058 | MW | 33
A137 | 2024CapSite_BrgyBalBag_Butuan City (Capital) | TRS Ready | 36. TRFS | ERICSSON | FRONTIER | 19. Site Clearing | TBD | (00) Not Started | MW/FSO | 2026-08-02 | 2026-12-22 | 121 | 2026-12-21 | 2026-03-06 | 2026-04-16 | MISAMIS OCCIDENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 8.9771 | 125.567 | MW/FSO | 24
Q709 | 2024CapSite_BrgyBagBur_Cagayan De Oro City (Capital) | For Awarding | 36. TRFS | NOKIA | EDOTCO | 26. ODU Pad / Electrical | HUAXIN | (02) Survey | AN + LEOSAT | 2026-01-03 | 2026-10-13 | 60 | 2026-04-09 | 2026-03-02 | 2026-09-29 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | Y | Self-Build - BTS | Yes | SEP | Q3 | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 12/10: no pole yet | 8.4871 | 124.6483 | AN + LEOSAT | 33
D476 | 2022Capsite_BrgyMalLun_Malaybalay City (Capital) | Awarded | 14. LC Applied | ERICSSON | UNITY | 23. Concrete Pouring | COMTEL | (01) Precon/ Eng'g Hold | MW | 2026-12-10 | 2026-01-23 | 13 | 2026-11-27 | 2026-07-06 | 2026-05-26 | TAWI-TAWI | MALAYBALAY CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/30: Fiber link verified | 12/10: no pole yet | 8.1693 | 125.1482 | MW | 25
K45 | 2020CapSite_BrgyCabBag_Marawi City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | PHILTOWER | 19. Site Clearing | ZTE | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-10-31 | 2026-10-24 | 83 | 2026-08-03 | 2026-04-12 | 2026-12-13 | BASILAN | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 8.0037 | 124.2916 | AN + LEOSAT | 25
O423 | 2023Capsite_BrgyLunSan_Cagayan De Oro City (Capital) | TRS Ready | 03. For Awarding | NOKIA | PHILTOWER | 23. Concrete Pouring | TBD | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-04-02 | 2026-07-18 | 95 | 2026-03-11 | 2026-08-23 | 2026-04-10 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 8.4763 | 124.669 | AN + LEOSAT | 27
O583 | 2022CapSite_BrgyBagSan_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 18. RTB for Mobilization | HT | (01) Precon/ Eng'g Hold | MW/FSO | 2026-11-06 | 2026-03-22 | 43 | 2026-10-23 | 2026-10-11 | 2026-04-28 | DAVAO DEL SUR | ZAMBOANGA CITY | Davao Region | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 6/15: MW dish installed | 6.9049 | 122.0532 | MW/FSO | 25
Q485 | 2022M2SC2_BrgyMalBur_Iligan City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | JISEDAI | (06) RTB (FOC/AN/Pending) | MW | 2026-10-21 | 2026-01-03 | 106 | 2026-01-23 | 2026-01-21 | 2026-08-29 | AGUSAN DEL NORTE | ILIGAN CITY | Caraga | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.2426 | 124.2202 | MW | 23
P714 | 2023CapSite_BrgyDorLun_Dipolog City (Capital) | TRFS | 14. LC Applied | NOKIA | UNITY | 26. ODU Pad / Electrical | FADI | (01) Precon/ Eng'g Hold | MW | 2026-07-03 | 2026-06-01 | 61 | 2026-11-28 | 2026-02-16 | 2026-01-09 | ZAMBOANGA DEL SUR | DIPOLOG CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | APR | Q2 | (05.3) TSSR Approved | 7/05: Integration complete | 5/20: LOS check passed | 8.5624 | 123.3414 | MW | 23
Q25 | 2023M2SC2_BrgySigBag_Butuan City (Capital) | LGU Permitting | 18. RTB for Mobilization | ERICSSON | ALLIANCE | 22. Rebar Installation | COMTEL | (00) Not Started | Fiber Extension | 2026-07-17 | 2026-12-20 | 85 | 2026-09-29 | 2026-01-17 | 2026-06-01 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 12/10: no pole yet | 8.9377 | 125.5349 | Fiber Extension | 33
D807 | 2024CapSite_BrgyKawBur_Marawi City (Capital) | TSSR | 18. RTB for Mobilization | NOKIA | EDOTCO | 26. ODU Pad / Electrical | HT | (00) Not Started | Fiber Extension | 2026-07-16 | 2026-07-07 | 119 | 2026-11-13 | 2026-01-21 | 2026-07-07 | MISAMIS ORIENTAL | MARAWI CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (03) PSH | 5/12: CR applied, AP | 3/31: Brgy Permit S | 8.0045 | 124.2537 | Fiber Extension | 23
P210 | 2022Capsite_BrgyLunCab_Pagadian City (Capital) | TSSR | 18. RTB for Mobilization | ERICSSON | UNITY | 18. RTB for Mobilization | JISEDAI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-06-30 | 2026-05-17 | 128 | 2026-12-15 | 2026-08-05 | 2026-05-22 | MISAMIS ORIENTAL | PAGADIAN CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/30: Fiber link verified | 9/19: Awaiting tower | 7.8324 | 123.4174 | MW/FSO | 23
B482 | 2024T8_RgPM_BrgyTagDor_Butuan City (Capital) | Awarded | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | ZTE | (00) Not Started | AN + LEOSAT | 2026-04-02 | 2026-05-28 | 19 | 2026-02-25 | 2026-03-26 | 2026-05-22 | ZAMBOANGA DEL NORTE | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/21: FOC cut 7/10 | 3/31: Brgy Permit S | 8.9339 | 125.5574 | AN + LEOSAT | 24
T24 | 2023CDNPH_BrgyNalCab_Claveria | Awarded | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | NOKIA | (02) Survey | MW | 2026-02-02 | 2026-01-12 | 59 | 2026-09-24 | 2026-11-27 | 2026-06-21 | LANAO DEL SUR | CLAVERIA | BARMM | N | Self-Build - BTS | Yes | MAY | Q2 | N/A | N/A | (05.3) TSSR Approved | 6/30: Fiber link verified | 10/17: Pending site | 8.5857 | 124.8654 | MW | 24
Q682 | 2024T8_RgPM_BrgyDorSig_Marawi City (Capital) | RFI'd | 07. Site Survey | NOKIA | FRONTIER | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | MW/FSO | 2026-04-27 | 2026-09-05 | 95 | 2026-05-28 | 2026-01-25 | 2026-03-17 | TAWI-TAWI | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 7.9858 | 124.2474 | MW/FSO | 23
O549 | 2021CDNPH_BrgyBagBur_Zamboanga City | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 19. Site Clearing | HT | (06) RTB (FOC/AN/Pending) | MW | 2026-08-14 | 2026-05-14 | 94 | 2026-04-05 | 2026-04-16 | 2026-10-15 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 9/19: Awaiting tower | 6.956 | 122.0882 | MW | 24
K553 | 2024Capsite_BrgyTagSan_Davao City | RFI'd | 03. For Awarding | ERICSSON | EDOTCO | 18. RTB for Mobilization | TBD | (05) Permitting | MW/FSO | 2026-03-21 | 2026-01-03 | 139 | 2026-09-17 | 2026-06-19 | 2026-11-28 | MISAMIS ORIENTAL | DAVAO CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 10/17: Pending site | 7.2037 | 125.4545 | MW/FSO | 23
Q683 | 2024Capsite_BrgyBurDor_Cagayan De Oro City (Capital) | For Awarding | 36. TRFS | ERICSSON | UNITY | 19. Site Clearing | TBD | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-06-07 | 2026-01-13 | 102 | 2026-11-13 | 2026-04-23 | 2026-08-17 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/20: RfId site 7/15 | 9/19: Awaiting tower | 8.46 | 124.6205 | Fiber Extension | 27
L228 | 2021CDNPH_BrgyMalSan_Isabela City | TRFS | 03. For Awarding | ERICSSON | EDOTCO | 23. Concrete Pouring | JISEDAI | (05) Permitting | MW/FSO | 2026-11-05 | 2026-11-06 | 130 | 2026-01-29 | 2026-12-08 | 2026-07-04 | SULU | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | JUL | Q3 | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 10/17: Pending site | 6.7268 | 121.9565 | MW/FSO | 24
A292 | 2022CDNPH_BrgyTagDor_Cagayan De Oro City (Capital) | RFI'd | 14. LC Applied | ERICSSON | UNITY | 23. Concrete Pouring | FADI | (05) Permitting | MW/FSO | 2026-03-25 | 2026-08-06 | 106 | 2026-03-13 | 2026-10-28 | 2026-11-03 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 8.4318 | 124.6066 | MW/FSO | 23
F68 | 2023T8_RgPM_BrgySanMal_Butuan City (Capital) | TSSR | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | COMTEL | (06) RTB (FOC/AN/Pending) | MW | 2026-04-13 | 2026-04-06 | 97 | 2026-05-29 | 2026-10-11 | 2026-09-09 | ZAMBOANGA SIBUGAY | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/12: Awaiting transmission hookup | 5/20: LOS check passed | 8.913 | 125.541 | MW | 23
K230 | 2020CapSite_BrgyBagTag_Cagayan De Oro City (Capital) | TRFS | 18. RTB for Mobilization | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (05) Permitting | MW | 2026-09-09 | 2026-12-19 | 62 | 2026-01-15 | 2026-03-03 | 2026-05-22 | AGUSAN DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | MAR | Q1 | (01) For Awarding | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.4475 | 124.6349 | MW | 33
G890 | 2023CDNPH_BrgyBurSan_Cagayan De Oro City (Capital) | s-RFI | 14. LC Applied | NOKIA | UNITY | 19. Site Clearing | HUAXIN | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-03-16 | 2026-06-13 | 118 | 2026-12-21 | 2026-03-11 | 2026-07-02 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 7/02: FOC splicing ongoing | 8.4216 | 124.6096 | Fiber Extension | 27
F50 | 2022CDNPH_BrgyCabNal_Cagayan De Oro City (Capital) | LGU Permitting | 36. TRFS | NOKIA | FRONTIER | 26. ODU Pad / Electrical | TBD | (00) Not Started | MW | 2026-10-06 | 2026-06-15 | 80 | 2026-12-17 | 2026-06-04 | 2026-05-19 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 9/19: Awaiting tower | 8.4313 | 124.6185 | MW | 27
A141 | 2022T8_RgPM_BrgyKawDor_Isabela City | For Awarding | 32. Ongoing Integration | ERICSSON | LDIC | 20. Excavation | ZTE | (01) Precon/ Eng'g Hold | MW | 2026-09-15 | 2026-04-24 | 48 | 2026-10-14 | 2026-11-11 | 2026-12-20 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 01 Precon/ Eng'g Hold | 6.693 | 121.9486 | MW | 33
G472 | 2020CapSite_BrgyBagMal_Pagadian City (Capital) | For Awarding | 32. Ongoing Integration | ERICSSON | FRONTIER | 22. Rebar Installation | TBD | (05) Permitting | MW/FSO | 2026-03-30 | 2026-12-30 | 77 | 2026-01-15 | 2026-03-02 | 2026-04-24 | MISAMIS ORIENTAL | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 6/15: MW dish installed | 7.8459 | 123.4394 | MW/FSO | 33
B436 | 2020CapSite_BrgyMalDor_Cagayan De Oro City (Capital) | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | na | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-08-29 | 2026-03-02 | 64 | 2026-01-23 | 2026-02-03 | 2026-06-04 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAY | Q2 | (01) For Awarding | 6/28: For MOS. Pull | 3/31: Brgy Permit S | 8.4939 | 124.6578 | Fiber Extension | 33
D602 | 2021Capsite_BrgyNalKaw_Malaybalay City (Capital) | s-RFI | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-06-30 | 2026-03-24 | 128 | 2026-11-10 | 2026-05-04 | 2026-09-16 | BUKIDNON | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 8.196 | 125.0885 | MW/FSO | 25
D733 | 2022Capsite_BrgyBagCab_Isabela City | For Awarding | 03. For Awarding | ERICSSON | LDIC | 24. Backfilling | COMTEL | (02) Survey | MW | 2026-08-14 | 2026-12-11 | 27 | 2026-04-03 | 2026-07-01 | 2026-07-14 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 12/10: no pole yet | 6.7176 | 121.9668 | MW | 23
F127 | 2020M2SC2_BrgyCabBag_Cagayan De Oro City (Capital) | RTB'd | 30. RFI/TRS Ready | ERICSSON | UNITY | 24. Backfilling | NOKIA | (00) Not Started | MW/FSO | 2026-09-10 | 2026-03-01 | 98 | 2026-05-26 | 2026-08-22 | 2026-11-04 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 6/20: RFI with Perm | 5/20: LOS check passed | 8.4866 | 124.641 | MW/FSO | 25
G298 | 2021M2SC2_BrgySanDor_Lamitan City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | COMTEL | (00) Not Started | AN + LEOSAT | 2026-08-13 | 2026-09-25 | 21 | 2026-03-03 | 2026-03-15 | 2026-07-22 | MISAMIS ORIENTAL | LAMITAN CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | Yes | NOV | Q4 | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 12/10: no pole yet | 6.6597 | 122.17 | AN + LEOSAT | 24
C67 | 2021CDNPH_BrgyKawLun_General Luna | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | COMTEL | (02) Survey | MW/FSO | 2026-11-26 | 2026-07-24 | 91 | 2026-09-01 | 2026-12-08 | 2026-11-05 | DAVAO DEL SUR | GENERAL LUNA | Davao Region | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 9/19: Awaiting tower | 9.7974 | 126.1415 | MW/FSO | 33
K510 | 2021Capsite_BrgyMalSan_Zamboanga City | RFI'd | 14. LC Applied | ERICSSON | PHILTOWER | 19. Site Clearing | TBD | (05) Permitting | MW/FSO | 2026-03-20 | 2026-06-05 | 24 | 2026-02-09 | 2026-12-05 | 2026-09-24 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 5/12: CR applied, AP | 9/19: Awaiting tower | 6.9547 | 122.1146 | MW/FSO | 23
E556 | 2024CDNPH_BrgyCabMal_Valencia City | TSSR | 14. LC Applied | ERICSSON | LDIC | 19. Site Clearing | FADI | (05) Permitting | MW/FSO | 2026-07-12 | 2026-08-15 | 117 | 2026-01-19 | 2026-01-17 | 2026-04-01 | ZAMBOANGA SIBUGAY | VALENCIA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (03) PSH | 6/12: Awaiting transmission hookup | 10/17: Pending site | 7.8973 | 125.0974 | MW/FSO | 23
E733 | 2023M2SC2_BrgySigSan_Zamboanga City | RTB'd | 14. LC Applied | NOKIA | UNITY | 24. Backfilling | COMTEL | (05) Permitting | MW | 2026-09-17 | 2026-01-29 | 100 | 2026-05-15 | 2026-09-11 | 2026-10-30 | AGUSAN DEL SUR | ZAMBOANGA CITY | Caraga | N | Self-Build - BTS | Yes | FEB | Q1 | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 12/10: no pole yet | 6.904 | 122.1119 | MW | 24
A29 | 2020T8_RgPM_BrgyBagKaw_Malaybalay City (Capital) | For Awarding | 07. Site Survey | NOKIA | FRONTIER | 26. ODU Pad / Electrical | HT | (05) Permitting | Fiber Extension | 2026-08-08 | 2026-06-26 | 91 | 2026-07-30 | 2026-06-29 | 2026-01-29 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 8.1833 | 125.1178 | Fiber Extension | 27
O68 | 2020CDNPH_BrgyKawBag_Marawi City (Capital) | For Awarding | 18. RTB for Mobilization | NOKIA | FRONTIER | 23. Concrete Pouring | FADI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-05-17 | 2026-01-11 | 120 | 2026-10-29 | 2026-01-12 | 2026-06-12 | BASILAN | MARAWI CITY (CAPITAL) | BARMM | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 6/24: for checking | 8.0242 | 124.2789 | AN + LEOSAT | 23
B708 | 2022Capsite_BrgyDorCab_Isabela City | RFI'd | 32. Ongoing Integration | ERICSSON | PHILTOWER | 22. Rebar Installation | FADI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-11-22 | 2026-02-08 | 137 | 2026-04-20 | 2026-05-28 | 2026-05-16 | ZAMBOANGA DEL NORTE | ISABELA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (05.2) TSSR for Approval | 7/05: Integration complete | 3/31: Brgy Permit S | 6.6676 | 122.003 | AN + LEOSAT | 27
O981 | 2024CapSite_BrgySanLib_Cagayan De Oro City (Capital) | RTB'd | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | na | (05) Permitting | AN + LEOSAT | 2026-04-18 | 2026-06-27 | 19 | 2026-11-30 | 2026-06-04 | 2026-09-16 | DINAGAT ISLANDS | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/18: Power energized | 6/15: MW dish installed | 8.4296 | 124.633 | AN + LEOSAT | 23
E640 | 2023T8_RgPM_BrgyNalCab_Cagayan De Oro City (Capital) | TRFS | 14. LC Applied | ERICSSON | PHILTOWER | 24. Backfilling | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-20 | 2026-12-05 | 119 | 2026-05-18 | 2026-11-23 | 2026-09-30 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | JUL | Q3 | (05.3) TSSR Approved | 7/18: Power energized | 10/17: Pending site | 8.4901 | 124.6053 | AN + LEOSAT | 25
D374 | 2021M2SC2_BrgyLunBag_General Luna | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 18. RTB for Mobilization | ZTE | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-05-17 | 2026-05-27 | 41 | 2026-05-12 | 2026-12-18 | 2026-11-04 | SURIGAO DEL SUR | GENERAL LUNA | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 9/19: Awaiting tower | 9.8193 | 126.1588 | AN + LEOSAT | 33
P848 | 2023CDNPH_BrgyDorCab_Zamboanga City | LGU Permitting | 03. For Awarding | ERICSSON | PHILTOWER | 19. Site Clearing | JISEDAI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-03-11 | 2026-01-15 | 66 | 2026-05-23 | 2026-12-04 | 2026-10-09 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 3/31: Brgy Permit S | 6.882 | 122.0442 | MW/FSO | 27
B322 | 2022T8_RgPM_BrgySanBal_Iligan City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-10-20 | 2026-09-14 | 30 | 2026-09-25 | 2026-12-07 | 2026-10-25 | COTABATO (NORTH COTABATO) | ILIGAN CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | JAN | Q1 | (04) For Re-award | 7/20: RfId site 7/15 | 6/15: MW dish installed | 8.2416 | 124.2671 | Fiber Extension | 25
P827 | 2022CDNPH_BrgyLibBur_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | EDOTCO | 20. Excavation | TBD | (00) Not Started | MW | 2026-04-20 | 2026-05-21 | 112 | 2026-07-29 | 2026-05-11 | 2026-10-29 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | Y | TowerCo (Micro) - BTS | Yes | AUG | Q3 | N/A | N/A | (01.1) TBD | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.9506 | 122.0729 | MW | 23
L434 | 2021M2SC2_BrgyTagBag_Pagadian City (Capital) | For Awarding | 03. For Awarding | ERICSSON | UNITY | 18. RTB for Mobilization | HUAXIN | (00) Not Started | Fiber Extension | 2026-12-06 | 2026-01-28 | 61 | 2026-05-10 | 2026-10-10 | 2026-07-16 | LANAO DEL SUR | PAGADIAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (01.1) TBD | 7/18: Power energized | 01 Precon/ Eng'g Hold | 7.794 | 123.44 | Fiber Extension | 33
D879 | 2023M2SC2_BrgyMalBal_Valencia City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | JISEDAI | (02) Survey | MW | 2026-03-24 | 2026-08-13 | 81 | 2026-11-26 | 2026-07-28 | 2026-01-18 | SURIGAO DEL NORTE | VALENCIA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | MAY | Q2 | (01) For Awarding | 6/30: Fiber link verified | 6/24: for checking | 7.9226 | 125.1323 | MW | 25
G949 | 2023CDNPH_BrgySanBag_Ozamiz City | LGU Permitting | 14. LC Applied | NOKIA | FRONTIER | 23. Concrete Pouring | na | (02) Survey | AN + LEOSAT | 2026-12-22 | 2026-01-15 | 13 | 2026-11-25 | 2026-11-25 | 2026-04-05 | BUKIDNON | OZAMIZ CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 12/10: no pole yet | 8.1701 | 123.8536 | AN + LEOSAT | 33
T313 | 2024CDNPH_BrgySanSig_Zamboanga City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-06-13 | 2026-08-20 | 122 | 2026-03-10 | 2026-05-14 | 2026-03-30 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 5/12: CR applied, AP | 12/10: no pole yet | 6.9566 | 122.0988 | AN + LEOSAT | 23
G377 | 2023Capsite_BrgyBalLib_Surigao City (Capital) | TRFS | 03. For Awarding | ERICSSON | EDOTCO | 24. Backfilling | JISEDAI | (00) Not Started | AN + LEOSAT | 2026-04-12 | 2026-05-15 | 43 | 2026-01-26 | 2026-07-25 | 2026-11-13 | CAMIGUIN | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | Yes | FEB | Q1 | FEB | Q1 | (03) PSH | 7/21: FOC cut 7/10 | 10/17: Pending site | 9.7523 | 125.4867 | AN + LEOSAT | 23
Q121 | 2024CapSite_BrgyBalDor_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | JISEDAI | (02) Survey | MW/FSO | 2026-09-11 | 2026-07-15 | 33 | 2026-08-09 | 2026-04-16 | 2026-11-04 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 6/24: for checking | 6.9079 | 122.046 | MW/FSO | 25
P150 | 2022CapSite_BrgyTagLun_Zamboanga City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | COMTEL | (00) Not Started | Fiber Extension | 2026-08-29 | 2026-03-10 | 82 | 2026-12-21 | 2026-07-23 | 2026-12-18 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | APR | Q2 | (02) Ongoing Survey | 6/20: RFI with Perm | 7/02: FOC splicing ongoing | 6.8857 | 122.1025 | Fiber Extension | 23
B571 | 2020CapSite_BrgyKawLun_General Luna | s-RFI | 03. For Awarding | ERICSSON | ISON | 26. ODU Pad / Electrical | NOKIA | (00) Not Started | MW/FSO | 2026-09-16 | 2026-11-14 | 97 | 2026-06-04 | 2026-07-22 | 2026-12-10 | MISAMIS ORIENTAL | GENERAL LUNA | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.2) TSSR for Approval | 6/30: Fiber link verified | 5/20: LOS check passed | 9.7874 | 126.1618 | MW/FSO | 24
E174 | 2023T8_RgPM_BrgyKawDor_Dipolog City (Capital) | TRS Ready | 18. RTB for Mobilization | ERICSSON | FRONTIER | 24. Backfilling | FADI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-03-01 | 2026-06-10 | 11 | 2026-03-07 | 2026-09-13 | 2026-05-24 | COTABATO (NORTH COTABATO) | DIPOLOG CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (02) Ongoing Survey | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 8.5667 | 123.321 | MW/FSO | 33
Q850 | 2024CDNPH_BrgyKawBal_Cagayan De Oro City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | UNITY | 23. Concrete Pouring | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-01-28 | 2026-04-07 | 38 | 2026-01-28 | 2026-04-28 | 2026-04-04 | SURIGAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 01 Precon/ Eng'g Hold | 8.4452 | 124.6423 | AN + LEOSAT | 23
K42 | 2022M2SC2_BrgyBurCab_Pagadian City (Capital) | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | TBD | (00) Not Started | MW/FSO | 2026-02-17 | 2026-04-15 | 72 | 2026-04-03 | 2026-03-28 | 2026-09-18 | BASILAN | PAGADIAN CITY (CAPITAL) | BARMM | N | Self-Build - BTS | Yes | MAY | Q2 | N/A | N/A | (05.2) TSSR for Approval | 7/05: Integration complete | 3/31: Brgy Permit S | 7.8203 | 123.3984 | MW/FSO | 23
A539 | 2021T8_RgPM_BrgyBalSan_Isabela City | RTB'd | 18. RTB for Mobilization | ERICSSON | UNITY | 22. Rebar Installation | NOKIA | (02) Survey | Fiber Extension | 2026-07-21 | 2026-07-11 | 27 | 2026-06-15 | 2026-03-20 | 2026-01-15 | SURIGAO DEL NORTE | ISABELA CITY | Caraga | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 9/19: Awaiting tower | 6.718 | 121.9739 | Fiber Extension | 24
E609 | 2022CapSite_BrgyMalNal_Valencia City | TRFS | 14. LC Applied | ERICSSON | EDOTCO | 26. ODU Pad / Electrical | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-11-26 | 2026-05-25 | 82 | 2026-01-29 | 2026-02-06 | 2026-10-08 | CAMIGUIN | VALENCIA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | APR | Q2 | (02) Ongoing Survey | 7/05: Integration complete | 5/20: LOS check passed | 7.9177 | 125.1037 | Fiber Extension | 33
P887 | 2020M2SC2_BrgyMalLun_Cagayan De Oro City (Capital) | s-RFI | 03. For Awarding | ERICSSON | ALLIANCE | 22. Rebar Installation | TBD | (00) Not Started | MW/FSO | 2026-09-09 | 2026-08-10 | 79 | 2026-12-17 | 2026-11-05 | 2026-03-09 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (04) For Re-award | 5/12: CR applied, AP | 9/19: Awaiting tower | 8.4747 | 124.6387 | MW/FSO | 27
G488 | 2024CDNPH_BrgyLibBal_Iligan City | For Awarding | 14. LC Applied | ERICSSON | ALLIANCE | 24. Backfilling | TBD | (05) Permitting | AN + LEOSAT | 2026-02-17 | 2026-01-21 | 131 | 2026-06-24 | 2026-08-26 | 2026-12-13 | AGUSAN DEL NORTE | ILIGAN CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 10/17: Pending site | 8.2441 | 124.211 | AN + LEOSAT | 24
B298 | 2023M2SC2_BrgySanDor_Dipolog City (Capital) | For Awarding | 27. sRFI Pending Pole | ERICSSON | ISON | 26. ODU Pad / Electrical | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-06-01 | 2026-10-19 | 12 | 2026-10-10 | 2026-02-09 | 2026-01-24 | SURIGAO DEL NORTE | DIPOLOG CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 9/19: Awaiting tower | 8.6227 | 123.3088 | AN + LEOSAT | 24
E364 | 2024CDNPH_BrgySanCab_Cagayan De Oro City (Capital) | Awarded | 14. LC Applied | ERICSSON | UNITY | 23. Concrete Pouring | TBD | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-01-24 | 2026-02-12 | 106 | 2026-12-27 | 2026-06-02 | 2026-06-10 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | Yes | NOV | Q4 | N/A | N/A | (05.1) TSSR for Submission | 6/28: For MOS. Pull | 6/24: for checking | 8.4772 | 124.616 | AN + LEOSAT | 33
F990 | 2021Capsite_BrgyBagSan_Butuan City (Capital) | For Awarding | 32. Ongoing Integration | ERICSSON | PHILTOWER | 19. Site Clearing | NOKIA | (05) Permitting | Fiber Extension | 2026-01-07 | 2026-03-29 | 122 | 2026-08-24 | 2026-12-21 | 2026-07-27 | BUKIDNON | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 6/24: for checking | 8.9144 | 125.5618 | Fiber Extension | 24
Q370 | 2022M2SC2_BrgySanBag_Cagayan De Oro City (Capital) | For Awarding | 32. Ongoing Integration | ERICSSON | FRONTIER | 18. RTB for Mobilization | NOKIA | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-04-18 | 2026-09-04 | 37 | 2026-11-29 | 2026-05-04 | 2026-08-12 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 3/31: Brgy Permit S | 8.4492 | 124.6235 | Fiber Extension | 33
K433 | 2020CapSite_BrgyBagSig_Cagayan De Oro City (Capital) | RTB'd | 14. LC Applied | ERICSSON | PHILTOWER | 18. RTB for Mobilization | COMTEL | (06) RTB (FOC/AN/Pending) | MW | 2026-04-14 | 2026-05-31 | 145 | 2026-07-20 | 2026-01-27 | 2026-06-20 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (01.1) TBD | 7/18: Power energized | 10/17: Pending site | 8.4671 | 124.6298 | MW | 24
K755 | 2024T8_RgPM_BrgyBurCab_Pagadian City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | PHILTOWER | 23. Concrete Pouring | na | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-29 | 2026-02-01 | 135 | 2026-01-10 | 2026-08-05 | 2026-10-23 | MISAMIS ORIENTAL | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/18: Power energized | 3/31: Brgy Permit S | 7.8284 | 123.4079 | AN + LEOSAT | 33
K120 | 2024M2SC2_BrgyNalKaw_Bongao (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 22. Rebar Installation | JISEDAI | (05) Permitting | MW/FSO | 2026-08-13 | 2026-04-29 | 129 | 2026-04-23 | 2026-10-28 | 2026-12-17 | ZAMBOANGA DEL SUR | BONGAO (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | Yes | MAR | Q1 | JAN | Q1 | (04) For Re-award | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 5.0435 | 119.7963 | MW/FSO | 33
E741 | 2023M2SC2_BrgyNalSig_Pagadian City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | ALLIANCE | 18. RTB for Mobilization | TBD | (06) RTB (FOC/AN/Pending) | MW | 2026-05-25 | 2026-12-20 | 22 | 2026-12-08 | 2026-09-05 | 2026-03-08 | AGUSAN DEL NORTE | PAGADIAN CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 6/15: MW dish installed | 7.8294 | 123.4738 | MW | 27
K311 | 2021Capsite_BrgyCabMal_Iligan City | s-RFI | 32. Ongoing Integration | ERICSSON | LDIC | 22. Rebar Installation | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-02 | 2026-06-22 | 110 | 2026-02-28 | 2026-11-13 | 2026-04-27 | ZAMBOANGA DEL SUR | ILIGAN CITY | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 8.1995 | 124.2594 | Fiber Extension | 23
F788 | 2024CapSite_BrgyTagBag_Cagayan De Oro City (Capital) | s-RFI | 06. With Issue | ERICSSON | EDOTCO | 23. Concrete Pouring | COMTEL | (00) Not Started | Fiber Extension | 2026-11-09 | 2026-11-09 | 26 | 2026-10-15 | 2026-01-22 | 2026-09-17 | ZAMBOANGA SIBUGAY | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 8.4873 | 124.6555 | Fiber Extension | 33
C746 | 2023CDNPH_BrgySigCab_Gingoog City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 22. Rebar Installation | HT | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-04-14 | 2026-08-13 | 106 | 2026-01-04 | 2026-05-06 | 2026-08-31 | MISAMIS ORIENTAL | GINGOOG CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.8394 | 125.093 | Fiber Extension | 25
P425 | 2021CDNPH_BrgyBagCab_Zamboanga City | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | FADI | (05) Permitting | AN + LEOSAT | 2026-09-22 | 2026-12-16 | 92 | 2026-01-16 | 2026-08-15 | 2026-03-16 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 12/10: no pole yet | 6.9574 | 122.0833 | AN + LEOSAT | 27
P169 | 2020M2SC2_BrgyBalMal_Zamboanga City | s-RFI & TRS Ready | 06. With Issue | NOKIA | FRONTIER | 26. ODU Pad / Electrical | na | (02) Survey | AN + LEOSAT | 2026-07-25 | 2026-12-15 | 141 | 2026-06-05 | 2026-06-10 | 2026-06-26 | SURIGAO DEL SUR | ZAMBOANGA CITY | Caraga | Y | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 6.9258 | 122.0489 | AN + LEOSAT | 27
G457 | 2024Capsite_BrgyLibSig_Isabela City | TRFS | 03. For Awarding | ERICSSON | LDIC | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-02-13 | 2026-01-19 | 137 | 2026-06-21 | 2026-07-19 | 2026-03-06 | SURIGAO DEL NORTE | ISABELA CITY | Caraga | N | TowerCo (Micro) - BTS | Yes | JUN | Q2 | JAN | Q1 | (05.3) TSSR Approved | 6/30: Fiber link verified | 6/24: for checking | 6.6645 | 121.9788 | MW/FSO | 23
L349 | 2020Capsite_BrgyMalCab_Zamboanga City | s-RFI | 14. LC Applied | ERICSSON | ALLIANCE | 22. Rebar Installation | FADI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-01-31 | 2026-07-10 | 66 | 2026-11-18 | 2026-09-17 | 2026-07-01 | BASILAN | ZAMBOANGA CITY | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 9/19: Awaiting tower | 6.9244 | 122.1148 | Fiber Extension | 24
Q755 | 2023CapSite_BrgyKawLun_Ozamiz City | Awarded | 14. LC Applied | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | TBD | (05) Permitting | MW | 2026-02-23 | 2026-06-17 | 132 | 2026-10-26 | 2026-04-09 | 2026-07-04 | BUKIDNON | OZAMIZ CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (03) PSH | 6/20: RFI with Perm | 3/31: Brgy Permit S | 8.1325 | 123.8618 | MW | 24
B64 | 2021M2SC2_BrgyDorLun_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | FADI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-05-16 | 2026-10-27 | 127 | 2026-11-22 | 2026-08-05 | 2026-08-14 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 5/20: LOS check passed | 8.4865 | 124.6194 | AN + LEOSAT | 33
L131 | 2023M2SC2_BrgyBagBur_Cagayan De Oro City (Capital) | TRS Ready | 03. For Awarding | ERICSSON | PHILTOWER | 19. Site Clearing | TBD | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-03-02 | 2026-11-05 | 104 | 2026-02-26 | 2026-03-03 | 2026-07-09 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (05.1) TSSR for Submission | 7/20: RfId site 7/15 | 10/17: Pending site | 8.4472 | 124.6436 | MW/FSO | 27
F311 | 2023CDNPH_BrgyMalBag_Zamboanga City | RTB'd | 14. LC Applied | NOKIA | PHILTOWER | 22. Rebar Installation | HUAXIN | (01) Precon/ Eng'g Hold | MW | 2026-09-08 | 2026-01-02 | 31 | 2026-10-08 | 2026-06-28 | 2026-02-04 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (02) Ongoing Survey | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 6.9224 | 122.0519 | MW | 33
F801 | 2023M2SC2_BrgyBurLib_Cagayan De Oro City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 23. Concrete Pouring | COMTEL | (05) Permitting | MW | 2026-06-16 | 2026-02-15 | 104 | 2026-07-18 | 2026-04-30 | 2026-07-22 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 6/15: MW dish installed | 8.4319 | 124.6587 | MW | 25
E662 | 2021CapSite_BrgyBurMal_Valencia City | RTB'd | 14. LC Applied | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | na | (00) Not Started | MW | 2026-11-13 | 2026-10-05 | 147 | 2026-01-28 | 2026-10-19 | 2026-09-25 | ZAMBOANGA DEL SUR | VALENCIA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 9/19: Awaiting tower | 7.8819 | 125.0687 | MW | 24
L185 | 2022CapSite_BrgySigLun_Zamboanga City | For Awarding | 27. sRFI Pending Pole | NOKIA | PHILTOWER | 18. RTB for Mobilization | na | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-07-25 | 2026-10-29 | 11 | 2026-09-09 | 2026-01-12 | 2026-06-24 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 6/24: for checking | 6.9454 | 122.1072 | MW/FSO | 33
E94 | 2020CapSite_BrgyCabBag_Gingoog City | TRFS | 07. Site Survey | ERICSSON | FRONTIER | 18. RTB for Mobilization | ZTE | (01) Precon/ Eng'g Hold | MW/FSO | 2026-07-28 | 2026-12-14 | 43 | 2026-01-31 | 2026-11-11 | 2026-06-16 | ZAMBOANGA DEL NORTE | GINGOOG CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | MAR | Q1 | (02) Ongoing Survey | 5/12: CR applied, AP | 5/20: LOS check passed | 8.8492 | 125.1377 | MW/FSO | 33
C423 | 2022CDNPH_BrgyBalSan_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (05) Permitting | AN + LEOSAT | 2026-02-28 | 2026-05-18 | 15 | 2026-06-12 | 2026-08-26 | 2026-10-11 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 6/24: for checking | 8.4937 | 124.6288 | AN + LEOSAT | 27
A276 | 2024T8_RgPM_BrgyNalSan_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | NOKIA | PHILTOWER | 20. Excavation | HUAXIN | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-08-17 | 2026-02-12 | 128 | 2026-04-15 | 2026-03-14 | 2026-07-11 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | N/A | N/A | (04) For Re-award | 6/20: RFI with Perm | 10/17: Pending site | 8.4582 | 124.6152 | AN + LEOSAT | 25
L463 | 2020CapSite_BrgyDorLib_Dipolog City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | HUAXIN | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-12-15 | 2026-07-14 | 89 | 2026-11-20 | 2026-04-19 | 2026-10-27 | BUKIDNON | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (01.1) TBD | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.5539 | 123.3082 | MW/FSO | 25
E92 | 2020M2SC2_BrgyBagBur_General Luna | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 24. Backfilling | HT | (02) Survey | MW/FSO | 2026-12-29 | 2026-08-20 | 69 | 2026-05-06 | 2026-12-06 | 2026-06-14 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 9.8008 | 126.1548 | MW/FSO | 33
O137 | 2024CapSite_BrgyDorMal_Isabela City | TSSR | 03. For Awarding | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | COMTEL | (05) Permitting | Fiber Extension | 2026-11-29 | 2026-11-30 | 19 | 2026-10-03 | 2026-01-16 | 2026-12-10 | LANAO DEL NORTE | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.6906 | 121.9414 | Fiber Extension | 25
F397 | 2020Capsite_BrgySanDor_Ipil (Capital) | For Awarding | 32. Ongoing Integration | ERICSSON | PHILTOWER | 20. Excavation | NOKIA | (02) Survey | MW/FSO | 2026-04-09 | 2026-02-16 | 77 | 2026-04-24 | 2026-04-30 | 2026-09-10 | TAWI-TAWI | IPIL (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 5/20: LOS check passed | 7.7935 | 122.5533 | MW/FSO | 25
D8 | 2023Capsite_BrgySanTag_Balingasag | TSSR | 28. sRFI/TRS Ready | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | TBD | (00) Not Started | MW | 2026-02-03 | 2026-03-07 | 66 | 2026-10-19 | 2026-04-27 | 2026-09-25 | BASILAN | BALINGASAG | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 6/24: for checking | 8.7557 | 124.8053 | MW | 27
O695 | 2024T8_RgPM_BrgyTagNal_Valencia City | For Awarding | 36. TRFS | ERICSSON | EDOTCO | 26. ODU Pad / Electrical | NOKIA | (02) Survey | AN + LEOSAT | 2026-07-28 | 2026-05-21 | 31 | 2026-12-15 | 2026-09-23 | 2026-08-27 | ZAMBOANGA DEL SUR | VALENCIA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (01) For Awarding | 7/18: Power energized | 7/02: FOC splicing ongoing | 7.8918 | 125.0903 | AN + LEOSAT | 27
A285 | 2024M2SC2_BrgyDorKaw_Zamboanga City | LGU Permitting | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 19. Site Clearing | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-02-08 | 2026-05-08 | 50 | 2026-03-26 | 2026-06-18 | 2026-06-09 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | Y | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 7/02: FOC splicing ongoing | 6.9307 | 122.0635 | AN + LEOSAT | 25
P642 | 2022CDNPH_BrgyLunSan_Butuan City (Capital) | RTB'd | 03. For Awarding | ERICSSON | EDOTCO | 18. RTB for Mobilization | NOKIA | (02) Survey | MW | 2026-02-07 | 2026-11-04 | 112 | 2026-02-18 | 2026-11-17 | 2026-08-17 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/18: Permanent Po | 10/17: Pending site | 8.9542 | 125.5458 | MW | 33
F912 | 2021CapSite_BrgyMalDor_Zamboanga City | LGU Permitting | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | ZTE | (00) Not Started | Fiber Extension | 2026-10-14 | 2026-01-27 | 75 | 2026-07-15 | 2026-07-25 | 2026-02-19 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 6.9106 | 122.0643 | Fiber Extension | 24
A465 | 2023M2SC2_BrgySigBal_Isabela City | For Awarding | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | NOKIA | (05) Permitting | MW/FSO | 2026-10-28 | 2026-04-09 | 27 | 2026-02-22 | 2026-01-07 | 2026-11-01 | ZAMBOANGA SIBUGAY | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 3/31: Brgy Permit S | 6.6984 | 121.9315 | MW/FSO | 33
C653 | 2022T8_RgPM_BrgyKawBal_Lamitan City (Capital) | For Awarding | 36. TRFS | NOKIA | PHILTOWER | 20. Excavation | TBD | (00) Not Started | Fiber Extension | 2026-03-07 | 2026-06-09 | 149 | 2026-08-12 | 2026-09-20 | 2026-11-30 | MISAMIS ORIENTAL | LAMITAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 10/17: Pending site | 6.6297 | 122.111 | Fiber Extension | 33
K317 | 2022T8_RgPM_BrgyTagKaw_Dipolog City (Capital) | TSSR | 03. For Awarding | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | TBD | (00) Not Started | MW | 2026-09-17 | 2026-10-14 | 13 | 2026-08-05 | 2026-06-26 | 2026-04-11 | MISAMIS ORIENTAL | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/12: Awaiting transmission hookup | 12/10: no pole yet | 8.6077 | 123.3352 | MW | 24
O709 | 2024M2SC2_BrgyBurKaw_Cagayan De Oro City (Capital) | TRFS | 27. sRFI Pending Pole | NOKIA | FRONTIER | 22. Rebar Installation | TBD | (00) Not Started | AN + LEOSAT | 2026-01-22 | 2026-09-11 | 56 | 2026-01-02 | 2026-11-24 | 2026-04-25 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | JUL | Q3 | (02) Ongoing Survey | 6/18: Permanent Po | 12/10: no pole yet | 8.4814 | 124.6026 | AN + LEOSAT | 27
P976 | 2023CDNPH_BrgyLunBal_Zamboanga City | s-RFI | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | HT | (00) Not Started | Fiber Extension | 2026-03-14 | 2026-05-29 | 112 | 2026-04-10 | 2026-11-20 | 2026-10-27 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 5/12: CR applied, AP | 5/20: LOS check passed | 6.94 | 122.1092 | Fiber Extension | 33
D907 | 2021CDNPH_BrgyKawCab_Zamboanga City | LGU Permitting | 06. With Issue | ERICSSON | FRONTIER | 20. Excavation | HUAXIN | (00) Not Started | Fiber Extension | 2026-12-13 | 2026-03-12 | 97 | 2026-12-02 | 2026-02-26 | 2026-06-23 | DAVAO DEL SUR | ZAMBOANGA CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/28: For MOS. Pull | 10/17: Pending site | 6.9184 | 122.0677 | Fiber Extension | 25
C964 | 2024T8_RgPM_BrgyBalBur_Cagayan De Oro City (Capital) | s-RFI | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | JISEDAI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-12-22 | 2026-07-11 | 81 | 2026-11-03 | 2026-08-08 | 2026-11-22 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/20: RfId site 7/15 | 6/24: for checking | 8.4386 | 124.636 | AN + LEOSAT | 25
E809 | 2022Capsite_BrgyLunMal_Isabela City | For Awarding | 36. TRFS | ERICSSON | LDIC | 24. Backfilling | COMTEL | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-08-29 | 2026-12-06 | 16 | 2026-03-27 | 2026-09-18 | 2026-07-18 | BUKIDNON | ISABELA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 6.6782 | 121.9796 | Fiber Extension | 27
O383 | 2023T8_RgPM_BrgyBurDor_Iligan City | Awarded | 03. For Awarding | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-04-14 | 2026-08-20 | 60 | 2026-07-22 | 2026-04-22 | 2026-06-06 | ZAMBOANGA DEL NORTE | ILIGAN CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/20: RfId site 7/15 | 06 RTB (FOC/ AN/ ... | 8.2553 | 124.2739 | MW | 27
L87 | 2020Capsite_BrgyTagDor_Labason | TRFS | 14. LC Applied | ERICSSON | PHILTOWER | 23. Concrete Pouring | na | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-08-07 | 2026-08-19 | 119 | 2026-08-10 | 2026-07-29 | 2026-07-08 | MISAMIS ORIENTAL | LABASON | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | APR | Q2 | (04) For Re-award | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.0379 | 122.5198 | MW/FSO | 27
E661 | 2022CapSite_BrgySanTag_Zamboanga City | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | EDOTCO | 19. Site Clearing | ZTE | (00) Not Started | MW/FSO | 2026-01-20 | 2026-10-07 | 51 | 2026-06-20 | 2026-04-11 | 2026-12-12 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 3/31: Brgy Permit S | 6.9025 | 122.1099 | MW/FSO | 23
E196 | 2021T8_RgPM_BrgySigBur_Ipil (Capital) | s-RFI & TRS Ready | 27. sRFI Pending Pole | ERICSSON | ALLIANCE | 22. Rebar Installation | HT | (05) Permitting | AN + LEOSAT | 2026-10-24 | 2026-12-02 | 3 | 2026-08-30 | 2026-12-01 | 2026-09-20 | SULU | IPIL (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (03) PSH | 6/20: RFI with Perm | 12/10: no pole yet | 7.7472 | 122.5513 | AN + LEOSAT | 23
D529 | 2024T8_RgPM_BrgySigDor_Pagadian City (Capital) | For Awarding | 03. For Awarding | ERICSSON | ALLIANCE | 22. Rebar Installation | JISEDAI | (05) Permitting | AN + LEOSAT | 2026-04-18 | 2026-08-13 | 115 | 2026-10-13 | 2026-01-16 | 2026-07-11 | ZAMBOANGA SIBUGAY | PAGADIAN CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 7.7872 | 123.4376 | AN + LEOSAT | 25
K830 | 2022CDNPH_BrgyLunBal_Cagayan De Oro City (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | na | (02) Survey | MW/FSO | 2026-10-28 | 2026-01-12 | 145 | 2026-01-17 | 2026-03-13 | 2026-03-20 | AGUSAN DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Caraga | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 7/02: FOC splicing ongoing | 8.4167 | 124.6385 | MW/FSO | 33
G391 | 2023Capsite_BrgySanCab_Isabela City | LGU Permitting | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 22. Rebar Installation | COMTEL | (02) Survey | Fiber Extension | 2026-03-29 | 2026-02-23 | 141 | 2026-04-01 | 2026-01-17 | 2026-12-19 | MISAMIS ORIENTAL | ISABELA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 01 Precon/ Eng'g Hold | 6.6965 | 121.9783 | Fiber Extension | 23
G291 | 2021Capsite_BrgyTagNal_Zamboanga City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 24. Backfilling | NOKIA | (01) Precon/ Eng'g Hold | MW/FSO | 2026-07-30 | 2026-07-20 | 40 | 2026-02-26 | 2026-03-08 | 2026-10-02 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 5/20: LOS check passed | 6.9539 | 122.0831 | MW/FSO | 33
D134 | 2022Capsite_BrgyBalBur_Cagayan De Oro City (Capital) | TRS Ready | 36. TRFS | ERICSSON | PHILTOWER | 22. Rebar Installation | JISEDAI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-05-22 | 2026-04-14 | 1 | 2026-03-15 | 2026-08-17 | 2026-02-02 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | Yes | JUN | Q2 | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 6/24: for checking | 8.4577 | 124.6718 | AN + LEOSAT | 24
K472 | 2024M2SC2_BrgyMalBur_Dipolog City (Capital) | TSSR | 36. TRFS | ERICSSON | PHILTOWER | 23. Concrete Pouring | HT | (02) Survey | AN + LEOSAT | 2026-11-10 | 2026-03-31 | 106 | 2026-05-08 | 2026-04-02 | 2026-11-13 | BUKIDNON | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 9/19: Awaiting tower | 8.5863 | 123.3623 | AN + LEOSAT | 25
Q98 | 2020M2SC2_BrgyLunBag_Balingasag | s-RFI | 03. For Awarding | NOKIA | FRONTIER | 19. Site Clearing | JISEDAI | (05) Permitting | AN + LEOSAT | 2026-10-11 | 2026-03-04 | 94 | 2026-02-09 | 2026-02-23 | 2026-09-16 | LANAO DEL NORTE | BALINGASAG | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/18: Power energized | 12/10: no pole yet | 8.7354 | 124.7512 | AN + LEOSAT | 23
K28 | 2023CapSite_BrgyBalKaw_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | HUAXIN | (00) Not Started | MW | 2026-06-17 | 2026-12-10 | 118 | 2026-09-06 | 2026-08-25 | 2026-02-04 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 7/02: FOC splicing ongoing | 8.476 | 124.6506 | MW | 25
K841 | 2021CDNPH_BrgyBagMal_Pagadian City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | FADI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-12-10 | 2026-01-06 | 69 | 2026-03-20 | 2026-08-14 | 2026-07-03 | MISAMIS ORIENTAL | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 10/17: Pending site | 7.809 | 123.4342 | Fiber Extension | 24
K714 | 2024CapSite_BrgyNalSig_Bongao (Capital) | RTB'd | 14. LC Applied | ERICSSON | UNITY | 23. Concrete Pouring | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-01-25 | 2026-07-13 | 51 | 2026-05-08 | 2026-07-11 | 2026-05-03 | MISAMIS ORIENTAL | BONGAO (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 7/21: FOC cut 7/10 | 7/02: FOC splicing ongoing | 5.053 | 119.7642 | Fiber Extension | 24
D697 | 2021CapSite_BrgySanNal_Zamboanga City | LGU Permitting | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | ZTE | (02) Survey | MW/FSO | 2026-10-15 | 2026-11-17 | 48 | 2026-11-16 | 2026-04-17 | 2026-10-05 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 3/31: Brgy Permit S | 6.9216 | 122.092 | MW/FSO | 25
C16 | 2022M2SC2_BrgyMalBal_Zamboanga City | s-RFI | 14. LC Applied | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-01-23 | 2026-02-04 | 55 | 2026-07-30 | 2026-06-04 | 2026-11-03 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 01 Precon/ Eng'g Hold | 6.9492 | 122.1035 | MW/FSO | 23
Q176 | 2020CDNPH_BrgyLibKaw_Surigao City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HT | (05) Permitting | Fiber Extension | 2026-06-21 | 2026-01-10 | 149 | 2026-08-18 | 2026-07-15 | 2026-09-19 | MISAMIS ORIENTAL | SURIGAO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 3/31: Brgy Permit S | 9.7891 | 125.4633 | Fiber Extension | 25
A632 | 2022CapSite_BrgyLunBur_Pagadian City (Capital) | TRFS | 03. For Awarding | ERICSSON | PHILTOWER | 19. Site Clearing | TBD | (02) Survey | AN + LEOSAT | 2026-06-01 | 2026-04-14 | 38 | 2026-07-12 | 2026-04-15 | 2026-11-25 | LANAO DEL SUR | PAGADIAN CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | Yes | MAR | Q1 | JAN | Q1 | (05.3) TSSR Approved | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 7.8268 | 123.4327 | AN + LEOSAT | 33
O899 | 2021CDNPH_BrgyTagKaw_Isabela City | TRFS | 36. TRFS | NOKIA | ALLIANCE | 23. Concrete Pouring | HUAXIN | (00) Not Started | MW | 2026-06-19 | 2026-06-25 | 62 | 2026-04-16 | 2026-10-04 | 2026-01-28 | SURIGAO DEL NORTE | ISABELA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | JUN | Q2 | (04) For Re-award | 7/05: Integration complete | 6/24: for checking | 6.6784 | 122.007 | MW | 33
G534 | 2021CDNPH_BrgyDorNal_Pagadian City (Capital) | TRFS | 03. For Awarding | ERICSSON | LDIC | 19. Site Clearing | JISEDAI | (00) Not Started | MW | 2026-04-15 | 2026-03-06 | 23 | 2026-03-30 | 2026-10-31 | 2026-10-09 | BUKIDNON | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | APR | Q2 | (02) Ongoing Survey | 7/20: RfId site 7/15 | 7/02: FOC splicing ongoing | 7.8385 | 123.4744 | MW | 33
C739 | 2021Capsite_BrgyBalBag_Cagayan De Oro City (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 23. Concrete Pouring | JISEDAI | (02) Survey | AN + LEOSAT | 2026-02-10 | 2026-07-04 | 101 | 2026-07-13 | 2026-03-27 | 2026-08-30 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | APR | Q2 | (05.2) TSSR for Approval | 6/30: Fiber link verified | 6/15: MW dish installed | 8.4731 | 124.6306 | AN + LEOSAT | 33
P494 | 2023CapSite_BrgyBalSan_General Luna | Awarded | 30. RFI/TRS Ready | NOKIA | PHILTOWER | 24. Backfilling | TBD | (02) Survey | AN + LEOSAT | 2026-08-26 | 2026-06-06 | 116 | 2026-05-26 | 2026-07-12 | 2026-10-15 | LANAO DEL SUR | GENERAL LUNA | BARMM | N | TowerCo (Micro) - BTS | Yes | MAY | Q2 | N/A | N/A | (05.3) TSSR Approved | 7/21: FOC cut 7/10 | 5/20: LOS check passed | 9.7715 | 126.1333 | AN + LEOSAT | 33
C939 | 2020Capsite_BrgyMalCab_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 23. Concrete Pouring | FADI | (02) Survey | AN + LEOSAT | 2026-09-08 | 2026-06-07 | 150 | 2026-02-06 | 2026-07-29 | 2026-01-20 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 01 Precon/ Eng'g Hold | 6.9204 | 122.044 | AN + LEOSAT | 24
E790 | 2024CDNPH_BrgyBurDor_Zamboanga City | TSSR | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 23. Concrete Pouring | JISEDAI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-01-18 | 2026-07-05 | 7 | 2026-12-24 | 2026-12-07 | 2026-11-27 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/30: Fiber link verified | 5/20: LOS check passed | 6.911 | 122.0424 | AN + LEOSAT | 23
D617 | 2021T8_RgPM_BrgyMalSan_Ozamiz City | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | ZTE | (06) RTB (FOC/AN/Pending) | MW | 2026-08-05 | 2026-03-26 | 109 | 2026-05-10 | 2026-12-21 | 2026-06-04 | MISAMIS ORIENTAL | OZAMIZ CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | JAN | Q1 | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 6/15: MW dish installed | 8.1246 | 123.8745 | MW | 23
G771 | 2020CapSite_BrgyNalLib_Cagayan De Oro City (Capital) | LGU Permitting | 07. Site Survey | ERICSSON | FRONTIER | 20. Excavation | FADI | (02) Survey | Fiber Extension | 2026-03-28 | 2026-09-09 | 0 | 2026-02-19 | 2026-02-05 | 2026-12-23 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 06 RTB (FOC/ AN/ ... | 8.4431 | 124.6295 | Fiber Extension | 27
C384 | 2021Capsite_BrgyLunDor_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | NOKIA | EDOTCO | 23. Concrete Pouring | JISEDAI | (01) Precon/ Eng'g Hold | MW | 2026-01-31 | 2026-04-04 | 49 | 2026-05-13 | 2026-07-29 | 2026-08-14 | ZAMBOANGA DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/20: RfId site 7/15 | 01 Precon/ Eng'g Hold | 8.4506 | 124.5956 | MW | 25
B387 | 2022CapSite_BrgySanKaw_Marawi City (Capital) | TRFS | 03. For Awarding | NOKIA | FRONTIER | 23. Concrete Pouring | ZTE | (00) Not Started | Fiber Extension | 2026-05-17 | 2026-01-04 | 149 | 2026-01-22 | 2026-02-19 | 2026-04-19 | ZAMBOANGA DEL SUR | MARAWI CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | FEB | Q1 | (06.2) Brgy Secured | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 8.0384 | 124.2692 | Fiber Extension | 24
E955 | 2023M2SC2_BrgySigKaw_Iligan City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 22. Rebar Installation | HT | (01) Precon/ Eng'g Hold | MW/FSO | 2026-12-07 | 2026-07-24 | 96 | 2026-11-09 | 2026-01-30 | 2026-07-02 | ZAMBOANGA DEL NORTE | ILIGAN CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/21: FOC cut 7/10 | 7/02: FOC splicing ongoing | 8.2443 | 124.2469 | MW/FSO | 24
C27 | 2020T8_RgPM_BrgyCabTag_Gingoog City | For Awarding | 14. LC Applied | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | COMTEL | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-12-05 | 2026-04-07 | 0 | 2026-11-23 | 2026-06-14 | 2026-01-09 | ZAMBOANGA DEL SUR | GINGOOG CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 12/10: no pole yet | 8.8475 | 125.1299 | AN + LEOSAT | 25
T455 | 2024Capsite_BrgyDorBal_Arakan | For Awarding | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 23. Concrete Pouring | ZTE | (05) Permitting | MW/FSO | 2026-11-07 | 2026-04-10 | 36 | 2026-09-24 | 2026-10-20 | 2026-09-16 | AGUSAN DEL SUR | ARAKAN | Caraga | Y | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01) For Awarding | 5/12: CR applied, AP | 10/17: Pending site | 8.4811 | 125.8035 | MW/FSO | 25
L896 | 2021M2SC2_BrgyDorSan_Zamboanga City | For Awarding | 32. Ongoing Integration | NOKIA | FRONTIER | 20. Excavation | TBD | (00) Not Started | Fiber Extension | 2026-08-11 | 2026-01-15 | 41 | 2026-06-17 | 2026-07-16 | 2026-05-24 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 6/24: for checking | 6.8953 | 122.0913 | Fiber Extension | 33
T140 | 2023T8_RgPM_BrgySanBur_Arakan | TRFS | 27. sRFI Pending Pole | ERICSSON | EDOTCO | 18. RTB for Mobilization | ZTE | (02) Survey | AN + LEOSAT | 2026-07-15 | 2026-12-01 | 143 | 2026-08-12 | 2026-04-30 | 2026-04-25 | MISAMIS ORIENTAL | ARAKAN | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | JUN | Q2 | (02) Ongoing Survey | 5/12: CR applied, AP | 6/15: MW dish installed | 8.4434 | 124.6442 | AN + LEOSAT | 24
Q960 | 2020Capsite_BrgyLibKaw_Zamboanga City | Awarded | 06. With Issue | ERICSSON | EDOTCO | 24. Backfilling | NOKIA | (02) Survey | Fiber Extension | 2026-10-30 | 2026-10-02 | 48 | 2026-07-18 | 2026-08-05 | 2026-06-13 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 6.9482 | 122.0803 | Fiber Extension | 24
G10 | 2023T8_RgPM_BrgyKawBag_Isabela City | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | TBD | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-03-16 | 2026-12-07 | 8 | 2026-11-03 | 2026-06-13 | 2026-06-08 | LANAO DEL SUR | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/20: RFI with Perm | 3/31: Brgy Permit S | 6.6942 | 122.0037 | MW/FSO | 25
T849 | 2023Capsite_BrgyTagBur_Lamitan City (Capital) | TRFS | 18. RTB for Mobilization | ERICSSON | EDOTCO | 22. Rebar Installation | TBD | (01) Precon/ Eng'g Hold | MW | 2026-12-25 | 2026-01-27 | 45 | 2026-09-07 | 2026-07-20 | 2026-06-03 | BASILAN | LAMITAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | MAY | Q2 | (06.2) Brgy Secured | 6/18: Permanent Po | 6/24: for checking | 6.6513 | 122.1215 | MW | 25
T485 | 2023CDNPH_BrgyBalSan_Dipolog City (Capital) | s-RFI | 07. Site Survey | ERICSSON | UNITY | 20. Excavation | na | (05) Permitting | Fiber Extension | 2026-03-09 | 2026-06-15 | 148 | 2026-01-28 | 2026-12-30 | 2026-06-05 | DAVAO DEL SUR | DIPOLOG CITY (CAPITAL) | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 6/18: Permanent Po | 12/10: no pole yet | 8.6179 | 123.3392 | Fiber Extension | 23
C215 | 2021Capsite_BrgyBurNal_Butuan City (Capital) | For Awarding | 14. LC Applied | ERICSSON | UNITY | 24. Backfilling | ZTE | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-08-07 | 2026-12-14 | 43 | 2026-01-29 | 2026-02-19 | 2026-07-02 | MISAMIS ORIENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/21: FOC cut 7/10 | 6/24: for checking | 8.9461 | 125.5489 | AN + LEOSAT | 33
F608 | 2021M2SC2_BrgyNalBur_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | FADI | (05) Permitting | MW/FSO | 2026-12-19 | 2026-11-02 | 44 | 2026-12-01 | 2026-07-12 | 2026-12-21 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 5/20: LOS check passed | 6.9215 | 122.0501 | MW/FSO | 27
E648 | 2022M2SC2_BrgyMalSan_Gingoog City | TRFS | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-10-28 | 2026-10-21 | 146 | 2026-09-03 | 2026-05-21 | 2026-12-22 | BUKIDNON | GINGOOG CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | MAR | Q1 | (06.1) Brgy Applied | 5/12: CR applied, AP | 01 Precon/ Eng'g Hold | 8.7943 | 125.0693 | Fiber Extension | 33
T720 | 2022M2SC2_BrgyLibBag_Zamboanga City | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | na | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-12-25 | 2026-01-11 | 100 | 2026-10-12 | 2026-10-02 | 2026-09-29 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 6/15: MW dish installed | 6.9329 | 122.0559 | AN + LEOSAT | 24
P668 | 2021CapSite_BrgyNalSan_Isabela City | s-RFI | 28. sRFI/TRS Ready | NOKIA | UNITY | 19. Site Clearing | na | (05) Permitting | MW/FSO | 2026-03-04 | 2026-01-21 | 32 | 2026-10-22 | 2026-04-16 | 2026-12-01 | LANAO DEL SUR | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (03) PSH | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 6.6791 | 121.9601 | MW/FSO | 23
B519 | 2022CDNPH_BrgyCabBag_Lamitan City (Capital) | RFI'd | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | na | (02) Survey | AN + LEOSAT | 2026-03-13 | 2026-10-23 | 125 | 2026-12-22 | 2026-06-10 | 2026-09-25 | MISAMIS ORIENTAL | LAMITAN CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/18: Power energized | 3/31: Brgy Permit S | 6.6674 | 122.1028 | AN + LEOSAT | 25
A243 | 2021CapSite_BrgyBagTag_Zamboanga City | Awarded | 03. For Awarding | ERICSSON | PHILTOWER | 20. Excavation | HT | (02) Survey | MW | 2026-11-15 | 2026-08-05 | 19 | 2026-10-09 | 2026-05-11 | 2026-05-14 | MISAMIS OCCIDENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 10/17: Pending site | 6.8998 | 122.1039 | MW | 27
G963 | 2024Capsite_BrgyLunSan_Zamboanga City | LGU Permitting | 03. For Awarding | ERICSSON | UNITY | 24. Backfilling | na | (06) RTB (FOC/AN/Pending) | MW | 2026-08-03 | 2026-03-20 | 80 | 2026-08-11 | 2026-07-14 | 2026-01-14 | ZAMBOANGA DEL NORTE | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 9/19: Awaiting tower | 6.939 | 122.0775 | MW | 24
L417 | 2022CapSite_BrgyNalSan_Zamboanga City | Awarded | 03. For Awarding | ERICSSON | ALLIANCE | 20. Excavation | JISEDAI | (02) Survey | Fiber Extension | 2026-02-20 | 2026-07-13 | 56 | 2026-07-13 | 2026-02-23 | 2026-03-05 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | DEC | Q4 | N/A | N/A | (05.3) TSSR Approved | 7/05: Integration complete | 3/31: Brgy Permit S | 6.9197 | 122.0559 | Fiber Extension | 27
K98 | 2022T8_RgPM_BrgyBurLib_Cagayan De Oro City (Capital) | TRFS | 32. Ongoing Integration | NOKIA | FRONTIER | 19. Site Clearing | NOKIA | (01) Precon/ Eng'g Hold | MW/FSO | 2026-07-19 | 2026-04-03 | 88 | 2026-12-14 | 2026-09-30 | 2026-10-10 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | JUN | Q2 | (05.3) TSSR Approved | 6/30: Fiber link verified | 3/31: Brgy Permit S | 8.4271 | 124.6586 | MW/FSO | 33
L731 | 2021Capsite_BrgyBagBal_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | LDIC | 26. ODU Pad / Electrical | HT | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-12-28 | 2026-08-23 | 46 | 2026-08-13 | 2026-07-01 | 2026-08-28 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 12/10: no pole yet | 6.8832 | 122.0425 | AN + LEOSAT | 23
D313 | 2022CapSite_BrgyBalKaw_Cagayan De Oro City (Capital) | TRFS | 36. TRFS | ERICSSON | FRONTIER | 20. Excavation | ZTE | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-02-13 | 2026-05-27 | 141 | 2026-09-10 | 2026-01-06 | 2026-08-06 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | JUN | Q2 | (05.1) TSSR for Submission | 6/30: Fiber link verified | 01 Precon/ Eng'g Hold | 8.4601 | 124.6048 | Fiber Extension | 33
T694 | 2020T8_RgPM_BrgyBalMal_Zamboanga City | Awarded | 14. LC Applied | ERICSSON | UNITY | 26. ODU Pad / Electrical | na | (02) Survey | MW | 2026-12-05 | 2026-09-28 | 10 | 2026-11-07 | 2026-08-18 | 2026-03-28 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 5/12: CR applied, AP | 6/24: for checking | 6.9318 | 122.0421 | MW | 25
C527 | 2020CDNPH_BrgyBalDor_Zamboanga City | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | HT | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-05-29 | 2026-06-03 | 123 | 2026-05-31 | 2026-05-16 | 2026-04-20 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | Y | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 3/31: Brgy Permit S | 6.9272 | 122.0435 | Fiber Extension | 23
T528 | 2023CapSite_BrgyLibDor_El Salvador City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | HT | (02) Survey | MW/FSO | 2026-02-24 | 2026-01-03 | 89 | 2026-04-06 | 2026-07-25 | 2026-07-01 | ZAMBOANGA DEL NORTE | EL SALVADOR CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | DEC | Q4 | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.5446 | 124.4913 | MW/FSO | 33
C421 | 2023CapSite_BrgyMalBag_Zamboanga City | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 22. Rebar Installation | HUAXIN | (02) Survey | AN + LEOSAT | 2026-04-04 | 2026-10-02 | 68 | 2026-02-25 | 2026-08-13 | 2026-12-03 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 7/02: FOC splicing ongoing | 6.9581 | 122.0869 | AN + LEOSAT | 27
O204 | 2021CapSite_BrgyTagMal_General Luna | LGU Permitting | 03. For Awarding | ERICSSON | PHILTOWER | 22. Rebar Installation | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-09-03 | 2026-12-07 | 68 | 2026-03-02 | 2026-08-04 | 2026-09-08 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 6/15: MW dish installed | 9.7879 | 126.1173 | MW | 23
P800 | 2024M2SC2_BrgyBurSig_Pagadian City (Capital) | s-RFI | 07. Site Survey | ERICSSON | FRONTIER | 19. Site Clearing | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-06-26 | 2026-09-14 | 3 | 2026-12-17 | 2026-05-02 | 2026-01-27 | BUKIDNON | PAGADIAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 10/17: Pending site | 7.8433 | 123.4499 | MW | 23
K297 | 2023CDNPH_BrgySanBal_Isabela City | TRFS | 03. For Awarding | NOKIA | FRONTIER | 24. Backfilling | TBD | (01) Precon/ Eng'g Hold | MW/FSO | 2026-02-28 | 2026-05-15 | 63 | 2026-12-08 | 2026-08-08 | 2026-04-12 | LANAO DEL NORTE | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | JUN | Q2 | (06.1) Brgy Applied | 6/28: For MOS. Pull | 10/17: Pending site | 6.6868 | 121.938 | MW/FSO | 25
Q645 | 2021Capsite_BrgySanBag_Iligan City | LGU Permitting | 03. For Awarding | ERICSSON | FRONTIER | 20. Excavation | TBD | (05) Permitting | Fiber Extension | 2026-11-12 | 2026-04-13 | 23 | 2026-01-27 | 2026-07-14 | 2026-07-28 | MISAMIS ORIENTAL | ILIGAN CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/30: Fiber link verified | 3/31: Brgy Permit S | 8.2239 | 124.2846 | Fiber Extension | 25
G491 | 2024CapSite_BrgyBalNal_Davao City | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 22. Rebar Installation | HUAXIN | (02) Survey | AN + LEOSAT | 2026-05-07 | 2026-06-13 | 12 | 2026-04-04 | 2026-01-21 | 2026-01-01 | MISAMIS ORIENTAL | DAVAO CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | JAN | Q1 | JAN | Q1 | (02) Ongoing Survey | 6/30: Fiber link verified | 06 RTB (FOC/ AN/ ... | 7.2201 | 125.4289 | AN + LEOSAT | 27
B442 | 2022Capsite_BrgyDorKaw_Butuan City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | NOKIA | (06) RTB (FOC/AN/Pending) | MW | 2026-06-19 | 2026-07-04 | 92 | 2026-10-29 | 2026-09-28 | 2026-11-06 | ZAMBOANGA SIBUGAY | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 6/15: MW dish installed | 8.9739 | 125.5487 | MW | 27
B134 | 2020T8_RgPM_BrgyMalLib_Zamboanga City | s-RFI & TRS Ready | 14. LC Applied | ERICSSON | UNITY | 19. Site Clearing | ZTE | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-06-04 | 2026-08-31 | 51 | 2026-10-01 | 2026-03-20 | 2026-01-23 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 6/15: MW dish installed | 6.945 | 122.1046 | MW/FSO | 23
P874 | 2022T8_RgPM_BrgyKawDor_Pagadian City (Capital) | s-RFI | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | na | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-03-27 | 2026-11-03 | 70 | 2026-12-23 | 2026-03-08 | 2026-05-29 | ZAMBOANGA DEL NORTE | PAGADIAN CITY (CAPITAL) | Zamboanga Peninsula | Y | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 7.8003 | 123.4498 | Fiber Extension | 24
G507 | 2024T8_RgPM_BrgySanBag_Davao City | Awarded | 03. For Awarding | NOKIA | FRONTIER | 18. RTB for Mobilization | FADI | (05) Permitting | MW/FSO | 2026-04-16 | 2026-04-05 | 0 | 2026-03-23 | 2026-10-20 | 2026-04-22 | ZAMBOANGA DEL SUR | DAVAO CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 5/12: CR applied, AP | 6/24: for checking | 7.1719 | 125.4732 | MW/FSO | 33
O738 | 2022T8_RgPM_BrgyTagLun_Surigao City (Capital) | RTB'd | 14. LC Applied | ERICSSON | PHILTOWER | 20. Excavation | JISEDAI | (00) Not Started | MW | 2026-05-30 | 2026-01-21 | 37 | 2026-05-23 | 2026-03-10 | 2026-05-19 | AGUSAN DEL SUR | SURIGAO CITY (CAPITAL) | Caraga | Y | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 9.7674 | 125.4863 | MW | 23
T356 | 2022T8_RgPM_BrgyKawSan_Zamboanga City | Awarded | 03. For Awarding | ERICSSON | PHILTOWER | 24. Backfilling | HUAXIN | (02) Survey | Fiber Extension | 2026-11-17 | 2026-01-06 | 91 | 2026-04-23 | 2026-05-24 | 2026-04-01 | DAVAO DEL SUR | ZAMBOANGA CITY | Davao Region | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/28: For MOS. Pull | 06 RTB (FOC/ AN/ ... | 6.9286 | 122.0574 | Fiber Extension | 27
P598 | 2023CapSite_BrgyNalTag_Davao City | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 22. Rebar Installation | JISEDAI | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-03-21 | 2026-08-17 | 59 | 2026-08-11 | 2026-07-08 | 2026-03-17 | MISAMIS OCCIDENTAL | DAVAO CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 7.1815 | 125.424 | AN + LEOSAT | 23
C194 | 2023T8_RgPM_BrgyBurBag_Butuan City (Capital) | s-RFI | 32. Ongoing Integration | ERICSSON | FRONTIER | 20. Excavation | FADI | (06) RTB (FOC/AN/Pending) | MW | 2026-02-05 | 2026-03-15 | 18 | 2026-08-07 | 2026-05-06 | 2026-08-21 | LANAO DEL SUR | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 10/17: Pending site | 8.9237 | 125.5694 | MW | 25
P13 | 2020T8_RgPM_BrgyBalSig_Dipolog City (Capital) | For Awarding | 28. sRFI/TRS Ready | ERICSSON | ALLIANCE | 18. RTB for Mobilization | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-02-12 | 2026-05-18 | 36 | 2026-11-18 | 2026-11-04 | 2026-01-07 | ZAMBOANGA DEL SUR | DIPOLOG CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 8.5888 | 123.3339 | MW | 33
B208 | 2023Capsite_BrgySigLib_Ipil (Capital) | s-RFI | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | TBD | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-10-06 | 2026-12-21 | 68 | 2026-11-18 | 2026-10-06 | 2026-03-05 | MISAMIS OCCIDENTAL | IPIL (CAPITAL) | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 6/20: RFI with Perm | 3/31: Brgy Permit S | 7.7531 | 122.553 | Fiber Extension | 23
G146 | 2021CapSite_BrgyMalLun_Cagayan De Oro City (Capital) | RTB'd | 14. LC Applied | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-12-18 | 2026-02-27 | 125 | 2026-03-28 | 2026-02-26 | 2026-04-25 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/18: Power energized | 5/20: LOS check passed | 8.4523 | 124.6411 | AN + LEOSAT | 25
B918 | 2024CapSite_BrgyBagSig_Marawi City (Capital) | LGU Permitting | 03. For Awarding | NOKIA | FRONTIER | 20. Excavation | FADI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-11-16 | 2026-05-27 | 89 | 2026-02-23 | 2026-05-19 | 2026-09-13 | TAWI-TAWI | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 7.9631 | 124.306 | MW/FSO | 33
B808 | 2021CapSite_BrgySigNal_Ipil (Capital) | RFI'd | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 23. Concrete Pouring | COMTEL | (00) Not Started | Fiber Extension | 2026-10-23 | 2026-08-07 | 71 | 2026-03-16 | 2026-02-16 | 2026-06-15 | SURIGAO DEL SUR | IPIL (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (02) Ongoing Survey | 7/05: Integration complete | 12/10: no pole yet | 7.7814 | 122.5547 | Fiber Extension | 33
K711 | 2024M2SC2_BrgySigNal_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | JISEDAI | (05) Permitting | AN + LEOSAT | 2026-10-09 | 2026-09-12 | 137 | 2026-10-01 | 2026-09-10 | 2026-09-30 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 10/17: Pending site | 8.4528 | 124.6023 | AN + LEOSAT | 24
Q796 | 2020Capsite_BrgyLunKaw_Isabela City | RTB'd | 14. LC Applied | ERICSSON | ISON | 19. Site Clearing | HT | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-03-10 | 2026-02-26 | 15 | 2026-06-28 | 2026-07-04 | 2026-03-13 | ZAMBOANGA DEL NORTE | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | JUN | Q2 | N/A | N/A | (05.2) TSSR for Approval | 6/20: RFI with Perm | 5/20: LOS check passed | 6.7124 | 121.9973 | AN + LEOSAT | 25
G249 | 2021Capsite_BrgyMalBur_Lamitan City (Capital) | TRFS | 36. TRFS | ERICSSON | EDOTCO | 26. ODU Pad / Electrical | TBD | (05) Permitting | Fiber Extension | 2026-12-23 | 2026-08-06 | 95 | 2026-01-28 | 2026-12-26 | 2026-02-24 | ZAMBOANGA DEL SUR | LAMITAN CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | Yes | FEB | Q1 | MAR | Q1 | (05.3) TSSR Approved | 6/30: Fiber link verified | 6/24: for checking | 6.6818 | 122.1553 | Fiber Extension | 33
A151 | 2021CDNPH_BrgySanLun_Lamitan City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | PHILTOWER | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | MW | 2026-08-29 | 2026-03-13 | 135 | 2026-12-24 | 2026-06-03 | 2026-08-29 | ZAMBOANGA DEL SUR | LAMITAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/05: Integration complete | 9/19: Awaiting tower | 6.6619 | 122.1351 | MW | 24
B160 | 2020CapSite_BrgyLibBag_Marawi City (Capital) | For Awarding | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | COMTEL | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-10-20 | 2026-09-14 | 78 | 2026-12-30 | 2026-04-27 | 2026-08-05 | LANAO DEL NORTE | MARAWI CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 6/24: for checking | 7.9896 | 124.2468 | MW/FSO | 24
C761 | 2023Capsite_BrgyLibMal_Iligan City | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-12-21 | 2026-08-28 | 122 | 2026-06-10 | 2026-12-01 | 2026-11-25 | COTABATO (NORTH COTABATO) | ILIGAN CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 3/31: Brgy Permit S | 8.2304 | 124.2236 | Fiber Extension | 23
D277 | 2020CapSite_BrgySanKaw_Surigao City (Capital) | LGU Permitting | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 20. Excavation | na | (00) Not Started | Fiber Extension | 2026-04-19 | 2026-11-02 | 2 | 2026-06-08 | 2026-04-07 | 2026-10-10 | ZAMBOANGA DEL SUR | SURIGAO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 9.8042 | 125.5132 | Fiber Extension | 27
A578 | 2020M2SC2_BrgyMalKaw_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 22. Rebar Installation | HUAXIN | (05) Permitting | MW | 2026-06-11 | 2026-07-20 | 91 | 2026-03-08 | 2026-12-26 | 2026-12-12 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (04) For Re-award | 7/18: Power energized | 3/31: Brgy Permit S | 6.9119 | 122.0861 | MW | 27
P794 | 2020Capsite_BrgyLibBal_General Luna | For Awarding | 03. For Awarding | NOKIA | LDIC | 19. Site Clearing | HUAXIN | (01) Precon/ Eng'g Hold | MW | 2026-12-16 | 2026-08-26 | 20 | 2026-11-17 | 2026-02-17 | 2026-04-29 | ZAMBOANGA DEL NORTE | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 6/24: for checking | 9.8021 | 126.1767 | MW | 33
L747 | 2024T8_RgPM_BrgySigKaw_Zamboanga City | Awarded | 36. TRFS | ERICSSON | FRONTIER | 22. Rebar Installation | FADI | (00) Not Started | AN + LEOSAT | 2026-05-03 | 2026-04-17 | 19 | 2026-03-20 | 2026-10-18 | 2026-11-18 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 01 Precon/ Eng'g Hold | 6.9371 | 122.0468 | AN + LEOSAT | 33
L889 | 2023CapSite_BrgySanDor_Zamboanga City | For Awarding | 36. TRFS | ERICSSON | EDOTCO | 20. Excavation | ZTE | (02) Survey | MW/FSO | 2026-06-30 | 2026-02-15 | 18 | 2026-04-02 | 2026-12-30 | 2026-08-24 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/20: RFI with Perm | 5/20: LOS check passed | 6.8921 | 122.0772 | MW/FSO | 33
C963 | 2024CapSite_BrgyDorMal_Malaybalay City (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | TBD | (05) Permitting | MW/FSO | 2026-09-20 | 2026-11-16 | 80 | 2026-07-11 | 2026-02-12 | 2026-12-16 | DAVAO DEL SUR | MALAYBALAY CITY (CAPITAL) | Davao Region | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | MAR | Q1 | (01) For Awarding | 6/12: Awaiting transmission hookup | 6/24: for checking | 8.1361 | 125.1565 | MW/FSO | 23
A636 | 2021CapSite_BrgyBurCab_Claveria | TRFS | 36. TRFS | ERICSSON | LDIC | 22. Rebar Installation | FADI | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-02-07 | 2026-04-25 | 99 | 2026-08-25 | 2026-12-09 | 2026-02-17 | LANAO DEL NORTE | CLAVERIA | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | FEB | Q1 | MAY | Q2 | (03) PSH | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.596 | 124.9232 | AN + LEOSAT | 24
B88 | 2020Capsite_BrgyBalSig_Dipolog City (Capital) | TRS Ready | 32. Ongoing Integration | ERICSSON | FRONTIER | 22. Rebar Installation | HT | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-19 | 2026-12-26 | 121 | 2026-02-28 | 2026-05-23 | 2026-08-21 | LANAO DEL NORTE | DIPOLOG CITY (CAPITAL) | Northern Mindanao | Y | TowerCo (Micro) - BTS | Yes | FEB | Q1 | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 06 RTB (FOC/ AN/ ... | 8.5812 | 123.3154 | AN + LEOSAT | 27
F582 | 2024CapSite_BrgySigBal_Butuan City (Capital) | LGU Permitting | 18. RTB for Mobilization | ERICSSON | ALLIANCE | 23. Concrete Pouring | JISEDAI | (00) Not Started | MW | 2026-01-12 | 2026-12-17 | 108 | 2026-05-19 | 2026-05-10 | 2026-11-22 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 3/31: Brgy Permit S | 8.9642 | 125.5638 | MW | 25
O463 | 2024M2SC2_BrgyLunNal_Cagayan De Oro City (Capital) | RTB'd | 03. For Awarding | ERICSSON | ALLIANCE | 19. Site Clearing | FADI | (02) Survey | MW/FSO | 2026-03-26 | 2026-04-12 | 89 | 2026-08-03 | 2026-09-04 | 2026-09-01 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 10/17: Pending site | 8.4604 | 124.6013 | MW/FSO | 27
Q399 | 2024CapSite_BrgySigLib_Butuan City (Capital) | For Awarding | 36. TRFS | ERICSSON | UNITY | 24. Backfilling | TBD | (02) Survey | MW/FSO | 2026-01-08 | 2026-03-19 | 117 | 2026-03-17 | 2026-09-13 | 2026-06-12 | COTABATO (NORTH COTABATO) | BUTUAN CITY (CAPITAL) | SOCCSKSARGEN | Y | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 8.9081 | 125.553 | MW/FSO | 24
C650 | 2024M2SC2_BrgySanMal_Pagadian City (Capital) | TRFS | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | TBD | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-04-21 | 2026-06-28 | 53 | 2026-04-08 | 2026-12-14 | 2026-10-23 | BASILAN | PAGADIAN CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | Yes | JUN | Q2 | JUL | Q3 | (05.1) TSSR for Submission | 6/30: Fiber link verified | 10/17: Pending site | 7.8407 | 123.4223 | AN + LEOSAT | 24
L839 | 2023CapSite_BrgyNalDor_Zamboanga City | Awarded | 36. TRFS | ERICSSON | FRONTIER | 18. RTB for Mobilization | na | (05) Permitting | MW/FSO | 2026-02-28 | 2026-04-01 | 117 | 2026-08-08 | 2026-07-11 | 2026-04-01 | BUKIDNON | ZAMBOANGA CITY | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/20: RfId site 7/15 | 6/15: MW dish installed | 6.9104 | 122.0514 | MW/FSO | 25
T706 | 2022M2SC2_BrgyBurLib_Butuan City (Capital) | TRFS | 06. With Issue | ERICSSON | ALLIANCE | 19. Site Clearing | ZTE | (00) Not Started | AN + LEOSAT | 2026-02-23 | 2026-09-12 | 139 | 2026-02-21 | 2026-11-21 | 2026-08-16 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | Yes | SEP | Q3 | JUN | Q2 | (06.1) Brgy Applied | 6/18: Permanent Po | 6/24: for checking | 8.9596 | 125.5209 | AN + LEOSAT | 23
D229 | 2024M2SC2_BrgyBalSan_Valencia City | For Awarding | 36. TRFS | ERICSSON | EDOTCO | 22. Rebar Installation | COMTEL | (05) Permitting | AN + LEOSAT | 2026-01-04 | 2026-07-11 | 57 | 2026-09-17 | 2026-05-26 | 2026-05-18 | BUKIDNON | VALENCIA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 6/24: for checking | 7.9348 | 125.0881 | AN + LEOSAT | 27
T248 | 2023CapSite_BrgyMalSig_Balingasag | TSSR | 36. TRFS | ERICSSON | ALLIANCE | 18. RTB for Mobilization | na | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-06-21 | 2026-03-29 | 146 | 2026-08-09 | 2026-05-04 | 2026-10-12 | SULU | BALINGASAG | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/12: Awaiting transmission hookup | 10/17: Pending site | 8.7354 | 124.7553 | MW/FSO | 33
Q440 | 2023Capsite_BrgyBurBag_Cagayan De Oro City (Capital) | LGU Permitting | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | JISEDAI | (00) Not Started | MW | 2026-09-16 | 2026-03-02 | 147 | 2026-07-20 | 2026-11-18 | 2026-05-14 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 06 RTB (FOC/ AN/ ... | 8.4686 | 124.6523 | MW | 23
G12 | 2021T8_RgPM_BrgyMalLib_Zamboanga City | TRFS | 03. For Awarding | NOKIA | FRONTIER | 26. ODU Pad / Electrical | TBD | (05) Permitting | MW/FSO | 2026-04-06 | 2026-05-03 | 56 | 2026-06-02 | 2026-04-10 | 2026-10-02 | COTABATO (NORTH COTABATO) | ZAMBOANGA CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | APR | Q2 | (01) For Awarding | 7/21: FOC cut 7/10 | 10/17: Pending site | 6.9145 | 122.1017 | MW/FSO | 33
C643 | 2024CapSite_BrgySanSig_Valencia City | RTB'd | 07. Site Survey | NOKIA | FRONTIER | 20. Excavation | HUAXIN | (02) Survey | MW | 2026-02-17 | 2026-02-09 | 126 | 2026-07-05 | 2026-04-17 | 2026-07-20 | BUKIDNON | VALENCIA CITY | Northern Mindanao | Y | TowerCo (Micro) - BTS | Yes | MAR | Q1 | N/A | N/A | (04) For Re-award | 7/05: Integration complete | 9/19: Awaiting tower | 7.905 | 125.0838 | MW | 27
T79 | 2023Capsite_BrgyBalKaw_Cagayan De Oro City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 19. Site Clearing | TBD | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-03-02 | 2026-06-25 | 88 | 2026-09-05 | 2026-11-11 | 2026-11-04 | BUKIDNON | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/18: Power energized | 01 Precon/ Eng'g Hold | 8.4586 | 124.6122 | Fiber Extension | 25
D621 | 2024CapSite_BrgyMalCab_General Luna | LGU Permitting | 36. TRFS | ERICSSON | LDIC | 19. Site Clearing | JISEDAI | (00) Not Started | MW/FSO | 2026-03-12 | 2026-04-23 | 21 | 2026-12-21 | 2026-03-06 | 2026-05-18 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 6/15: MW dish installed | 9.7673 | 126.1433 | MW/FSO | 23
T302 | 2023M2SC2_BrgyBalCab_Zamboanga City | For Awarding | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 20. Excavation | HUAXIN | (05) Permitting | Fiber Extension | 2026-10-26 | 2026-10-28 | 79 | 2026-03-26 | 2026-04-16 | 2026-09-07 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | DEC | Q4 | N/A | N/A | (01) For Awarding | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 6.9378 | 122.0979 | Fiber Extension | 27
Q111 | 2023T8_RgPM_BrgyBalLun_General Luna | s-RFI & TRS Ready | 32. Ongoing Integration | ERICSSON | LDIC | 18. RTB for Mobilization | ZTE | (05) Permitting | MW | 2026-01-18 | 2026-09-19 | 64 | 2026-10-28 | 2026-07-29 | 2026-05-31 | LANAO DEL NORTE | GENERAL LUNA | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/05: Integration complete | 6/15: MW dish installed | 9.8112 | 126.1685 | MW | 33
F440 | 2022Capsite_BrgyLunSan_Zamboanga City | s-RFI & TRS Ready | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | HT | (00) Not Started | Fiber Extension | 2026-06-13 | 2026-12-19 | 2 | 2026-06-18 | 2026-04-20 | 2026-08-27 | TAWI-TAWI | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (05.1) TSSR for Submission | 6/12: Awaiting transmission hookup | 7/02: FOC splicing ongoing | 6.9412 | 122.0747 | Fiber Extension | 27
Q218 | 2021T8_RgPM_BrgySanCab_Dipolog City (Capital) | For Awarding | 14. LC Applied | NOKIA | EDOTCO | 18. RTB for Mobilization | ZTE | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-12-16 | 2026-08-11 | 81 | 2026-06-13 | 2026-04-12 | 2026-04-11 | SURIGAO DEL NORTE | DIPOLOG CITY (CAPITAL) | Caraga | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 06 RTB (FOC/ AN/ ... | 8.6044 | 123.3132 | AN + LEOSAT | 24
B464 | 2024Capsite_BrgyKawLib_Davao City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 22. Rebar Installation | NOKIA | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-08-25 | 2026-05-26 | 33 | 2026-07-26 | 2026-01-19 | 2026-10-01 | LANAO DEL SUR | DAVAO CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 7.1679 | 125.4473 | Fiber Extension | 24
P426 | 2022CDNPH_BrgyKawSig_Zamboanga City | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 22. Rebar Installation | COMTEL | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-07-21 | 2026-06-02 | 116 | 2026-09-10 | 2026-11-25 | 2026-03-04 | SULU | ZAMBOANGA CITY | BARMM | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 6.9085 | 122.083 | Fiber Extension | 27
C108 | 2023CDNPH_BrgyLunBag_Zamboanga City | RFI'd | 32. Ongoing Integration | ERICSSON | UNITY | 18. RTB for Mobilization | HT | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-12-19 | 2026-01-27 | 66 | 2026-01-23 | 2026-02-26 | 2026-01-25 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/20: RFI with Perm | 12/10: no pole yet | 6.9372 | 122.0955 | Fiber Extension | 33
G277 | 2021Capsite_BrgyLibDor_Valencia City | LGU Permitting | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 20. Excavation | FADI | (05) Permitting | Fiber Extension | 2026-09-25 | 2026-09-28 | 61 | 2026-10-23 | 2026-09-02 | 2026-12-05 | BASILAN | VALENCIA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | JAN | Q1 | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 6/15: MW dish installed | 7.8793 | 125.1314 | Fiber Extension | 24
E785 | 2020CDNPH_BrgyKawCab_General Luna | TRFS | 03. For Awarding | ERICSSON | UNITY | 19. Site Clearing | COMTEL | (00) Not Started | MW | 2026-01-07 | 2026-12-10 | 55 | 2026-08-28 | 2026-07-17 | 2026-04-07 | SULU | GENERAL LUNA | BARMM | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | JUN | Q2 | (06.1) Brgy Applied | 6/30: Fiber link verified | 10/17: Pending site | 9.7432 | 126.1231 | MW | 27
L880 | 2022CDNPH_BrgyBurDor_Ipil (Capital) | RTB'd | 30. RFI/TRS Ready | NOKIA | FRONTIER | 20. Excavation | JISEDAI | (02) Survey | AN + LEOSAT | 2026-08-20 | 2026-11-14 | 131 | 2026-04-14 | 2026-07-24 | 2026-04-07 | SULU | IPIL (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/20: RfId site 7/15 | 10/17: Pending site | 7.7527 | 122.6194 | AN + LEOSAT | 27
Q664 | 2021CapSite_BrgyDorSan_Valencia City | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 23. Concrete Pouring | TBD | (02) Survey | Fiber Extension | 2026-09-01 | 2026-12-05 | 135 | 2026-08-20 | 2026-06-30 | 2026-05-16 | LANAO DEL NORTE | VALENCIA CITY | Northern Mindanao | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 7/02: FOC splicing ongoing | 7.9012 | 125.0593 | Fiber Extension | 33
L442 | 2022T8_RgPM_BrgyMalDor_Butuan City (Capital) | s-RFI | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | FADI | (05) Permitting | MW | 2026-05-31 | 2026-04-07 | 103 | 2026-04-01 | 2026-11-01 | 2026-05-22 | ZAMBOANGA DEL SUR | BUTUAN CITY (CAPITAL) | Zamboanga Peninsula | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 6/28: For MOS. Pull | 5/20: LOS check passed | 8.9252 | 125.507 | MW | 24
T255 | 2021CapSite_BrgySanMal_Butuan City (Capital) | For Awarding | 27. sRFI Pending Pole | NOKIA | FRONTIER | 19. Site Clearing | na | (00) Not Started | MW/FSO | 2026-04-26 | 2026-11-14 | 103 | 2026-07-20 | 2026-07-21 | 2026-02-21 | LANAO DEL SUR | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 6/15: MW dish installed | 8.9105 | 125.5313 | MW/FSO | 33
T295 | 2022T8_RgPM_BrgyBurMal_Zamboanga City | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | COMTEL | (02) Survey | MW | 2026-03-29 | 2026-06-11 | 17 | 2026-03-27 | 2026-04-06 | 2026-06-20 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | JUN | Q2 | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 10/17: Pending site | 6.9602 | 122.0881 | MW | 33
A182 | 2020CDNPH_BrgyBagNal_Valencia City | LGU Permitting | 14. LC Applied | NOKIA | FRONTIER | 23. Concrete Pouring | NOKIA | (05) Permitting | MW | 2026-08-30 | 2026-02-26 | 11 | 2026-01-09 | 2026-10-18 | 2026-12-15 | COTABATO (NORTH COTABATO) | VALENCIA CITY | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/21: FOC cut 7/10 | 01 Precon/ Eng'g Hold | 7.9081 | 125.1111 | MW | 33
B103 | 2022CDNPH_BrgyDorSig_Zamboanga City | RFI'd | 03. For Awarding | NOKIA | FRONTIER | 23. Concrete Pouring | HUAXIN | (02) Survey | AN + LEOSAT | 2026-01-07 | 2026-06-30 | 77 | 2026-12-30 | 2026-06-20 | 2026-09-23 | LANAO DEL SUR | ZAMBOANGA CITY | BARMM | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 06 RTB (FOC/ AN/ ... | 6.9292 | 122.1147 | AN + LEOSAT | 24
T22 | 2023Capsite_BrgyLunNal_Cagayan De Oro City (Capital) | Awarded | 14. LC Applied | ERICSSON | PHILTOWER | 20. Excavation | FADI | (02) Survey | MW | 2026-02-15 | 2026-04-10 | 96 | 2026-11-24 | 2026-02-25 | 2026-05-21 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.4798 | 124.6431 | MW | 24
L180 | 2022CDNPH_BrgyKawBal_Butuan City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 19. Site Clearing | na | (02) Survey | Fiber Extension | 2026-08-10 | 2026-08-21 | 145 | 2026-06-27 | 2026-05-28 | 2026-02-26 | SURIGAO DEL NORTE | BUTUAN CITY (CAPITAL) | Caraga | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/20: RFI with Perm | 3/31: Brgy Permit S | 8.9426 | 125.5167 | Fiber Extension | 23
L990 | 2024CDNPH_BrgyCabNal_Zamboanga City | LGU Permitting | 27. sRFI Pending Pole | ERICSSON | PHILTOWER | 19. Site Clearing | HUAXIN | (00) Not Started | AN + LEOSAT | 2026-01-21 | 2026-04-22 | 72 | 2026-10-31 | 2026-03-05 | 2026-01-28 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 6.934 | 122.1033 | AN + LEOSAT | 25
A258 | 2022Capsite_BrgyTagCab_Cagayan De Oro City (Capital) | RFI'd | 32. Ongoing Integration | ERICSSON | UNITY | 20. Excavation | JISEDAI | (05) Permitting | Fiber Extension | 2026-05-29 | 2026-04-23 | 8 | 2026-08-31 | 2026-07-01 | 2026-05-08 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 10/17: Pending site | 8.4371 | 124.5946 | Fiber Extension | 27
E943 | 2024CDNPH_BrgyTagBag_Arakan | RTB'd | 03. For Awarding | ERICSSON | ALLIANCE | 20. Excavation | JISEDAI | (02) Survey | MW | 2026-08-02 | 2026-10-11 | 51 | 2026-06-04 | 2026-06-06 | 2026-02-13 | LANAO DEL NORTE | ARAKAN | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 7/02: FOC splicing ongoing | 8.236 | 124.2465 | MW | 25
P897 | 2020M2SC2_BrgyBagCab_Butuan City (Capital) | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | HT | (05) Permitting | MW/FSO | 2026-08-07 | 2026-08-27 | 107 | 2026-07-30 | 2026-08-25 | 2026-01-15 | SURIGAO DEL NORTE | BUTUAN CITY (CAPITAL) | Caraga | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (01.1) TBD | 7/18: Power energized | 12/10: no pole yet | 8.926 | 125.5142 | MW/FSO | 33
Q929 | 2021CDNPH_BrgyLibCab_Cagayan De Oro City (Capital) | RFI'd | 30. RFI/TRS Ready | ERICSSON | PHILTOWER | 24. Backfilling | HUAXIN | (00) Not Started | AN + LEOSAT | 2026-03-06 | 2026-07-26 | 1 | 2026-08-25 | 2026-09-23 | 2026-08-24 | COTABATO (NORTH COTABATO) | CAGAYAN DE ORO CITY (CAPITAL) | SOCCSKSARGEN | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/18: Power energized | 12/10: no pole yet | 8.4171 | 124.611 | AN + LEOSAT | 23
F609 | 2022CapSite_BrgyLibDor_Ipil (Capital) | LGU Permitting | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 24. Backfilling | na | (00) Not Started | MW | 2026-09-22 | 2026-03-15 | 143 | 2026-09-11 | 2026-03-11 | 2026-04-25 | ZAMBOANGA DEL SUR | IPIL (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 5/12: CR applied, AP | 10/17: Pending site | 7.7411 | 122.5579 | MW | 23
A825 | 2024M2SC2_BrgyBurLun_Cagayan De Oro City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 24. Backfilling | ZTE | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-05-07 | 2026-04-15 | 26 | 2026-08-31 | 2026-01-13 | 2026-09-16 | SULU | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 10/17: Pending site | 8.4939 | 124.6543 | Fiber Extension | 27
C840 | 2024Capsite_BrgyTagLib_Zamboanga City | TRFS | 14. LC Applied | NOKIA | FRONTIER | 20. Excavation | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-12-03 | 2026-05-04 | 43 | 2026-09-19 | 2026-12-25 | 2026-10-07 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | DEC | Q4 | APR | Q2 | (03) PSH | 5/12: CR applied, AP | 6/24: for checking | 6.9097 | 122.0706 | MW | 27
Q505 | 2022CDNPH_BrgyBalSig_Cagayan De Oro City (Capital) | TRS Ready | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | TBD | (00) Not Started | MW/FSO | 2026-08-23 | 2026-03-03 | 144 | 2026-07-19 | 2026-01-06 | 2026-10-25 | LANAO DEL NORTE | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/28: For MOS. Pull | 06 RTB (FOC/ AN/ ... | 8.4611 | 124.6333 | MW/FSO | 25
F986 | 2023Capsite_BrgyBurDor_Bongao (Capital) | TSSR | 18. RTB for Mobilization | ERICSSON | EDOTCO | 22. Rebar Installation | na | (06) RTB (FOC/AN/Pending) | MW | 2026-06-28 | 2026-12-28 | 134 | 2026-07-19 | 2026-09-20 | 2026-02-02 | MISAMIS ORIENTAL | BONGAO (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 7/18: Power energized | 7/02: FOC splicing ongoing | 5.0712 | 119.738 | MW | 25
O880 | 2022Capsite_BrgySigNal_Pagadian City (Capital) | LGU Permitting | 07. Site Survey | ERICSSON | FRONTIER | 18. RTB for Mobilization | COMTEL | (05) Permitting | AN + LEOSAT | 2026-11-07 | 2026-12-04 | 46 | 2026-10-22 | 2026-12-29 | 2026-09-17 | TAWI-TAWI | PAGADIAN CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 06 RTB (FOC/ AN/ ... | 7.7929 | 123.4198 | AN + LEOSAT | 24
Q357 | 2024T8_RgPM_BrgyBalSan_Pagadian City (Capital) | RTB'd | 18. RTB for Mobilization | ERICSSON | LDIC | 20. Excavation | JISEDAI | (00) Not Started | Fiber Extension | 2026-09-13 | 2026-12-14 | 121 | 2026-06-15 | 2026-04-29 | 2026-05-02 | BASILAN | PAGADIAN CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/18: Power energized | 6/24: for checking | 7.8521 | 123.4702 | Fiber Extension | 25
Q257 | 2020CapSite_BrgyBurSan_Cagayan De Oro City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | PHILTOWER | 18. RTB for Mobilization | NOKIA | (01) Precon/ Eng'g Hold | MW/FSO | 2026-02-25 | 2026-12-24 | 115 | 2026-07-13 | 2026-03-10 | 2026-11-23 | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 10/17: Pending site | 8.442 | 124.669 | MW/FSO | 25
E231 | 2021Capsite_BrgyBalCab_Cagayan De Oro City (Capital) | TRFS | 14. LC Applied | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | ZTE | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-03-13 | 2026-01-03 | 92 | 2026-07-28 | 2026-10-18 | 2026-10-07 | ZAMBOANGA SIBUGAY | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | FEB | Q1 | JAN | Q1 | (03) PSH | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 8.4363 | 124.6404 | Fiber Extension | 33
T541 | 2021M2SC2_BrgyLunLib_General Luna | For Awarding | 36. TRFS | NOKIA | FRONTIER | 24. Backfilling | na | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-08-13 | 2026-08-07 | 96 | 2026-02-06 | 2026-10-19 | 2026-02-10 | ZAMBOANGA DEL SUR | GENERAL LUNA | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/18: Power energized | 6/15: MW dish installed | 9.7584 | 126.1902 | Fiber Extension | 23
Q554 | 2020CDNPH_BrgyLunTag_Zamboanga City | TSSR | 03. For Awarding | ERICSSON | UNITY | 19. Site Clearing | TBD | (02) Survey | Fiber Extension | 2026-10-01 | 2026-10-22 | 61 | 2026-09-23 | 2026-11-09 | 2026-09-14 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 06 RTB (FOC/ AN/ ... | 6.9274 | 122.0599 | Fiber Extension | 25
Q483 | 2020CDNPH_BrgyMalKaw_Dipolog City (Capital) | For Awarding | 36. TRFS | ERICSSON | FRONTIER | 18. RTB for Mobilization | NOKIA | (01) Precon/ Eng'g Hold | MW | 2026-10-08 | 2026-06-18 | 15 | 2026-05-01 | 2026-09-10 | 2026-02-07 | MISAMIS ORIENTAL | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 3/31: Brgy Permit S | 8.5811 | 123.3088 | MW | 24
B973 | 2024M2SC2_BrgyBurLib_Malaybalay City (Capital) | Awarded | 03. For Awarding | NOKIA | PHILTOWER | 20. Excavation | HUAXIN | (00) Not Started | Fiber Extension | 2026-01-19 | 2026-09-12 | 129 | 2026-04-26 | 2026-11-29 | 2026-06-29 | MISAMIS ORIENTAL | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 8.1233 | 125.1113 | Fiber Extension | 25
A954 | 2020CapSite_BrgySigLun_Lamitan City (Capital) | For Awarding | 36. TRFS | ERICSSON | PHILTOWER | 19. Site Clearing | FADI | (05) Permitting | MW | 2026-08-09 | 2026-12-26 | 109 | 2026-10-09 | 2026-03-12 | 2026-03-01 | SULU | LAMITAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 6.6858 | 122.1575 | MW | 33
D352 | 2020M2SC2_BrgyLunSig_Davao City | RFI'd | 14. LC Applied | NOKIA | FRONTIER | 23. Concrete Pouring | na | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-01-08 | 2026-05-08 | 14 | 2026-02-09 | 2026-01-30 | 2026-03-06 | SURIGAO DEL NORTE | DAVAO CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | JUL | Q3 | N/A | N/A | (01) For Awarding | 6/28: For MOS. Pull | 5/20: LOS check passed | 7.2272 | 125.4854 | Fiber Extension | 27
D300 | 2024Capsite_BrgyBalDor_Cagayan De Oro City (Capital) | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 24. Backfilling | JISEDAI | (05) Permitting | MW/FSO | 2026-04-23 | 2026-08-16 | 77 | 2026-07-07 | 2026-10-10 | 2026-05-30 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 10/17: Pending site | 8.4793 | 124.6379 | MW/FSO | 33
L107 | 2022CapSite_BrgyBalBur_Cagayan De Oro City (Capital) | RFI'd | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 20. Excavation | na | (01) Precon/ Eng'g Hold | MW/FSO | 2026-10-11 | 2026-04-18 | 31 | 2026-07-10 | 2026-03-14 | 2026-01-19 | LANAO DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 8.4697 | 124.6692 | MW/FSO | 24
K857 | 2022CapSite_BrgyTagLib_Butuan City (Capital) | RFI'd | 03. For Awarding | ERICSSON | ALLIANCE | 19. Site Clearing | NOKIA | (02) Survey | AN + LEOSAT | 2026-09-11 | 2026-01-10 | 97 | 2026-07-16 | 2026-08-16 | 2026-01-23 | MISAMIS ORIENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | NOV | Q4 | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 9/19: Awaiting tower | 8.9526 | 125.5622 | AN + LEOSAT | 27
A555 | 2020CDNPH_BrgyLibKaw_Valencia City | RTB'd | 14. LC Applied | NOKIA | FRONTIER | 19. Site Clearing | HT | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-08-07 | 2026-01-30 | 27 | 2026-10-11 | 2026-07-18 | 2026-12-14 | ZAMBOANGA DEL NORTE | VALENCIA CITY | Zamboanga Peninsula | N | TowerCo (Micro) - BTS | Yes | SEP | Q3 | N/A | N/A | (01.1) TBD | 6/18: Permanent Po | 3/31: Brgy Permit S | 7.927 | 125.1311 | AN + LEOSAT | 23
L267 | 2023Capsite_BrgyDorBur_Isabela City | LGU Permitting | 18. RTB for Mobilization | ERICSSON | LDIC | 22. Rebar Installation | HUAXIN | (00) Not Started | MW | 2026-10-05 | 2026-06-01 | 86 | 2026-10-20 | 2026-07-22 | 2026-01-20 | LANAO DEL NORTE | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 6/15: MW dish installed | 6.7008 | 121.968 | MW | 24
P791 | 2020T8_RgPM_BrgySanTag_Valencia City | TSSR | 30. RFI/TRS Ready | ERICSSON | ALLIANCE | 23. Concrete Pouring | COMTEL | (00) Not Started | AN + LEOSAT | 2026-01-05 | 2026-08-27 | 9 | 2026-07-03 | 2026-09-03 | 2026-11-23 | TAWI-TAWI | VALENCIA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 7.9133 | 125.0564 | AN + LEOSAT | 24
Q565 | 2020CDNPH_BrgyDorBag_Isabela City | LGU Permitting | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | TBD | (01) Precon/ Eng'g Hold | MW | 2026-03-17 | 2026-11-13 | 12 | 2026-04-30 | 2026-02-28 | 2026-12-02 | ZAMBOANGA DEL NORTE | ISABELA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 10/17: Pending site | 6.6734 | 121.9365 | MW | 25
O234 | 2022CapSite_BrgyTagMal_Gingoog City | TRS Ready | 18. RTB for Mobilization | NOKIA | UNITY | 24. Backfilling | JISEDAI | (02) Survey | Fiber Extension | 2026-02-09 | 2026-09-17 | 113 | 2026-02-27 | 2026-09-19 | 2026-02-09 | MISAMIS ORIENTAL | GINGOOG CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 8.8318 | 125.1426 | Fiber Extension | 24
G74 | 2022M2SC2_BrgyBagMal_Cagayan De Oro City (Capital) | For Awarding | 32. Ongoing Integration | NOKIA | ALLIANCE | 22. Rebar Installation | FADI | (02) Survey | AN + LEOSAT | 2026-05-31 | 2026-11-15 | 7 | 2026-03-24 | 2026-07-08 | 2026-01-23 | SULU | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 7/21: FOC cut 7/10 | 6/15: MW dish installed | 8.4684 | 124.6103 | AN + LEOSAT | 23
P321 | 2024T8_RgPM_BrgySigLib_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | FRONTIER | 24. Backfilling | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-11-29 | 2026-02-10 | 19 | 2026-04-25 | 2026-10-17 | 2026-09-15 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 5/20: LOS check passed | 6.9067 | 122.1154 | AN + LEOSAT | 23
L818 | 2024CapSite_BrgyDorNal_Dipolog City (Capital) | RFI'd | 03. For Awarding | ERICSSON | FRONTIER | 18. RTB for Mobilization | HUAXIN | (01) Precon/ Eng'g Hold | MW/FSO | 2026-05-05 | 2026-07-05 | 59 | 2026-08-22 | 2026-06-11 | 2026-03-01 | BUKIDNON | DIPOLOG CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | N/A | N/A | (05.2) TSSR for Approval | 6/18: Permanent Po | 6/24: for checking | 8.5898 | 123.3011 | MW/FSO | 23
B361 | 2024T8_RgPM_BrgySanKaw_Arakan | For Awarding | 14. LC Applied | NOKIA | FRONTIER | 18. RTB for Mobilization | FADI | (01) Precon/ Eng'g Hold | MW | 2026-10-03 | 2026-05-06 | 104 | 2026-12-12 | 2026-10-27 | 2026-12-07 | LANAO DEL NORTE | ARAKAN | Northern Mindanao | N | Self-Build - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/30: Fiber link verified | 12/10: no pole yet | 8.2546 | 124.2251 | MW | 24
B419 | 2024M2SC2_BrgyBagLib_Cagayan De Oro City (Capital) | For Awarding | 07. Site Survey | ERICSSON | LDIC | 23. Concrete Pouring | NOKIA | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-08-03 | 2026-05-15 | 141 | 2026-12-31 | 2026-08-29 | 2026-02-21 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/05: Integration complete | 3/31: Brgy Permit S | 8.4216 | 124.6458 | Fiber Extension | 33
L888 | 2023T8_RgPM_BrgyBalKaw_Zamboanga City | TRFS | 03. For Awarding | ERICSSON | UNITY | 20. Excavation | HUAXIN | (00) Not Started | MW/FSO | 2026-06-22 | 2026-10-30 | 27 | 2026-01-24 | 2026-02-07 | 2026-07-01 | AGUSAN DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | MAR | Q1 | (06.1) Brgy Applied | 6/20: RFI with Perm | 3/31: Brgy Permit S | 6.9471 | 122.0451 | MW/FSO | 24
P489 | 2021Capsite_BrgyBurLib_General Luna | RTB'd | 14. LC Applied | ERICSSON | LDIC | 24. Backfilling | HT | (05) Permitting | AN + LEOSAT | 2026-06-14 | 2026-08-13 | 45 | 2026-09-18 | 2026-10-29 | 2026-05-24 | MISAMIS ORIENTAL | GENERAL LUNA | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 6/30: Fiber link verified | 9/19: Awaiting tower | 9.8173 | 126.1539 | AN + LEOSAT | 25
L594 | 2023T8_RgPM_BrgyTagKaw_Cagayan De Oro City (Capital) | s-RFI | 18. RTB for Mobilization | ERICSSON | ALLIANCE | 20. Excavation | NOKIA | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-09-23 | 2026-05-23 | 147 | 2026-11-12 | 2026-06-10 | 2026-02-20 | BASILAN | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/20: RFI with Perm | 6/15: MW dish installed | 8.4425 | 124.6634 | AN + LEOSAT | 23
C296 | 2024CDNPH_BrgySigSan_Cagayan De Oro City (Capital) | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | na | (06) RTB (FOC/AN/Pending) | MW | 2026-01-15 | 2026-11-03 | 10 | 2026-10-04 | 2026-10-03 | 2026-04-10 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Micro) - BTS | Yes | AUG | Q3 | MAY | Q2 | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 12/10: no pole yet | 8.4357 | 124.6677 | MW | 25
Q437 | 2024M2SC2_BrgyBagDor_Zamboanga City | s-RFI | 03. For Awarding | ERICSSON | UNITY | 18. RTB for Mobilization | ZTE | (05) Permitting | AN + LEOSAT | 2026-09-10 | 2026-05-15 | 22 | 2026-03-12 | 2026-05-23 | 2026-12-09 | AGUSAN DEL NORTE | ZAMBOANGA CITY | Caraga | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 6.936 | 122.1118 | AN + LEOSAT | 23
B335 | 2024Capsite_BrgyKawTag_General Luna | LGU Permitting | 03. For Awarding | NOKIA | UNITY | 19. Site Clearing | HT | (00) Not Started | AN + LEOSAT | 2026-02-21 | 2026-12-28 | 133 | 2026-06-12 | 2026-04-08 | 2026-10-13 | BUKIDNON | GENERAL LUNA | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/20: RfId site 7/15 | 6/24: for checking | 9.7827 | 126.1318 | AN + LEOSAT | 25
Q386 | 2021Capsite_BrgyTagDor_Marawi City (Capital) | For Awarding | 03. For Awarding | ERICSSON | ALLIANCE | 26. ODU Pad / Electrical | COMTEL | (02) Survey | MW | 2026-04-12 | 2026-11-22 | 22 | 2026-09-22 | 2026-04-20 | 2026-01-02 | COTABATO (NORTH COTABATO) | MARAWI CITY (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 6/24: for checking | 8.0188 | 124.3131 | MW | 27
A429 | 2024CDNPH_BrgyBalNal_Isabela City | For Awarding | 28. sRFI/TRS Ready | ERICSSON | PHILTOWER | 26. ODU Pad / Electrical | TBD | (02) Survey | MW | 2026-05-30 | 2026-12-09 | 124 | 2026-09-08 | 2026-11-19 | 2026-07-20 | LANAO DEL SUR | ISABELA CITY | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.6806 | 121.9473 | MW | 27
P783 | 2023CDNPH_BrgyDorKaw_Cagayan De Oro City (Capital) | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | HT | (00) Not Started | MW/FSO | 2026-12-23 | 2026-07-23 | 32 | 2026-09-05 | 2026-09-08 | 2026-11-04 | MISAMIS OCCIDENTAL | CAGAYAN DE ORO CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | APR | Q2 | (06.2) Brgy Secured | 7/18: Power energized | 5/20: LOS check passed | 8.4342 | 124.6414 | MW/FSO | 23
P419 | 2024CapSite_BrgySigKaw_Cagayan De Oro City (Capital) | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 18. RTB for Mobilization | COMTEL | (05) Permitting | AN + LEOSAT | 2026-05-14 | 2026-01-28 | 68 | 2026-09-06 | 2026-04-23 | 2026-06-23 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/28: For MOS. Pull | 7/02: FOC splicing ongoing | 8.4267 | 124.6004 | AN + LEOSAT | 25
C549 | 2020Capsite_BrgyLibSig_Cagayan De Oro City (Capital) | RFI'd | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 19. Site Clearing | NOKIA | (05) Permitting | Fiber Extension | 2026-12-27 | 2026-06-20 | 90 | 2026-10-11 | 2026-02-02 | 2026-12-02 | SULU | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | Y | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 10/17: Pending site | 8.4878 | 124.646 | Fiber Extension | 24
L406 | 2022Capsite_BrgySigBag_Dipolog City (Capital) | RTB'd | 36. TRFS | ERICSSON | PHILTOWER | 24. Backfilling | JISEDAI | (00) Not Started | Fiber Extension | 2026-01-11 | 2026-09-27 | 26 | 2026-09-14 | 2026-07-23 | 2026-09-06 | ZAMBOANGA SIBUGAY | DIPOLOG CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 7/18: Power energized | 7/02: FOC splicing ongoing | 8.6016 | 123.3494 | Fiber Extension | 33
O254 | 2022CapSite_BrgyBurSan_Zamboanga City | LGU Permitting | 18. RTB for Mobilization | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | HUAXIN | (00) Not Started | Fiber Extension | 2026-02-07 | 2026-09-16 | 106 | 2026-01-11 | 2026-01-08 | 2026-10-05 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | OCT | Q4 | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 5/20: LOS check passed | 6.9425 | 122.0823 | Fiber Extension | 24
Q880 | 2022CDNPH_BrgyBalCab_Isabela City | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 20. Excavation | ZTE | (02) Survey | AN + LEOSAT | 2026-07-12 | 2026-05-30 | 109 | 2026-02-17 | 2026-04-24 | 2026-07-28 | ZAMBOANGA DEL SUR | ISABELA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.6675 | 121.9697 | AN + LEOSAT | 24
D392 | 2023CapSite_BrgyBurBal_Balingasag | s-RFI | 14. LC Applied | NOKIA | UNITY | 23. Concrete Pouring | JISEDAI | (06) RTB (FOC/AN/Pending) | Fiber Extension | 2026-07-23 | 2026-04-29 | 114 | 2026-07-09 | 2026-09-02 | 2026-10-16 | LANAO DEL NORTE | BALINGASAG | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/28: For MOS. Pull | 6/15: MW dish installed | 8.7558 | 124.7727 | Fiber Extension | 33
B575 | 2021Capsite_BrgyDorLib_Surigao City (Capital) | LGU Permitting | 36. TRFS | ERICSSON | FRONTIER | 24. Backfilling | COMTEL | (06) RTB (FOC/AN/Pending) | MW | 2026-01-31 | 2026-09-10 | 64 | 2026-07-30 | 2026-06-09 | 2026-06-22 | SULU | SURIGAO CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.1) Brgy Applied | 6/28: For MOS. Pull | 01 Precon/ Eng'g Hold | 9.8188 | 125.5218 | MW | 33
A275 | 2024Capsite_BrgySigDor_Dipolog City (Capital) | For Awarding | 14. LC Applied | ERICSSON | EDOTCO | 20. Excavation | HT | (05) Permitting | AN + LEOSAT | 2026-09-21 | 2026-10-12 | 20 | 2026-02-23 | 2026-08-06 | 2026-12-25 | SULU | DIPOLOG CITY (CAPITAL) | BARMM | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 8.618 | 123.3396 | AN + LEOSAT | 25
B171 | 2023Capsite_BrgySanMal_Zamboanga City | TRFS | 14. LC Applied | ERICSSON | FRONTIER | 18. RTB for Mobilization | na | (05) Permitting | MW | 2026-10-08 | 2026-08-03 | 102 | 2026-01-05 | 2026-06-01 | 2026-03-02 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | JUL | Q3 | (06.1) Brgy Applied | 6/28: For MOS. Pull | 9/19: Awaiting tower | 6.9602 | 122.1123 | MW | 33
F630 | 2024CDNPH_BrgyNalBag_Claveria | RTB'd | 06. With Issue | ERICSSON | PHILTOWER | 20. Excavation | HT | (06) RTB (FOC/AN/Pending) | MW/FSO | 2026-08-30 | 2026-08-25 | 53 | 2026-06-19 | 2026-03-11 | 2026-03-26 | MISAMIS ORIENTAL | CLAVERIA | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (03) PSH | 7/18: Power energized | 5/20: LOS check passed | 8.5957 | 124.8709 | MW/FSO | 27
B6 | 2021CDNPH_BrgyLunBur_Cagayan De Oro City (Capital) | TSSR | 03. For Awarding | NOKIA | PHILTOWER | 19. Site Clearing | NOKIA | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-11-01 | 2026-03-22 | 17 | 2026-06-29 | 2026-11-22 | 2026-10-14 | ZAMBOANGA DEL SUR | CAGAYAN DE ORO CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | MAY | Q2 | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 8.4603 | 124.5962 | AN + LEOSAT | 33
G599 | 2022CDNPH_BrgyLibBal_Labason | Awarded | 07. Site Survey | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | JISEDAI | (00) Not Started | MW | 2026-02-22 | 2026-04-21 | 71 | 2026-04-02 | 2026-05-15 | 2026-10-16 | MISAMIS ORIENTAL | LABASON | Northern Mindanao | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.1) TSSR for Submission | 6/20: RFI with Perm | 3/31: Brgy Permit S | 8.0906 | 122.515 | MW | 24
F590 | 2024T8_RgPM_BrgyTagBur_Isabela City | TSSR | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 18. RTB for Mobilization | JISEDAI | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-11-11 | 2026-03-17 | 36 | 2026-03-26 | 2026-09-01 | 2026-01-01 | BUKIDNON | ISABELA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (05.1) TSSR for Submission | 7/05: Integration complete | 10/17: Pending site | 6.7074 | 121.9713 | Fiber Extension | 23
K436 | 2022M2SC2_BrgyTagCab_Zamboanga City | For Awarding | 14. LC Applied | ERICSSON | PHILTOWER | 23. Concrete Pouring | FADI | (05) Permitting | MW/FSO | 2026-06-09 | 2026-09-25 | 81 | 2026-09-29 | 2026-02-10 | 2026-11-06 | SURIGAO DEL NORTE | ZAMBOANGA CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 7/20: RfId site 7/15 | 5/20: LOS check passed | 6.9129 | 122.0939 | MW/FSO | 27
G574 | 2023M2SC2_BrgyBurTag_Ipil (Capital) | TRFS | 28. sRFI/TRS Ready | NOKIA | LDIC | 26. ODU Pad / Electrical | HT | (01) Precon/ Eng'g Hold | Fiber Extension | 2026-07-07 | 2026-08-27 | 88 | 2026-08-06 | 2026-04-20 | 2026-11-12 | COTABATO (NORTH COTABATO) | IPIL (CAPITAL) | SOCCSKSARGEN | N | TowerCo (Macro) - BTS | Yes | APR | Q2 | JUN | Q2 | (06.1) Brgy Applied | 6/28: For MOS. Pull | 9/19: Awaiting tower | 7.7551 | 122.6234 | Fiber Extension | 33
A201 | 2022M2SC2_BrgyCabLun_Zamboanga City | RTB'd | 30. RFI/TRS Ready | NOKIA | FRONTIER | 19. Site Clearing | HT | (02) Survey | Fiber Extension | 2026-11-07 | 2026-05-20 | 8 | 2026-11-28 | 2026-05-21 | 2026-11-25 | ZAMBOANGA DEL NORTE | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/20: RFI with Perm | 6/24: for checking | 6.9373 | 122.0758 | Fiber Extension | 33
T59 | 2020T8_RgPM_BrgyBurDor_Pagadian City (Capital) | RFI'd | 03. For Awarding | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | na | (00) Not Started | Fiber Extension | 2026-07-09 | 2026-01-15 | 39 | 2026-12-28 | 2026-04-01 | 2026-03-09 | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 6/20: RFI with Perm | 12/10: no pole yet | 7.8408 | 123.3979 | Fiber Extension | 23
O64 | 2020CDNPH_BrgyCabTag_Zamboanga City | s-RFI | 14. LC Applied | NOKIA | UNITY | 22. Rebar Installation | HT | (01) Precon/ Eng'g Hold | MW/FSO | 2026-09-22 | 2026-01-08 | 103 | 2026-08-02 | 2026-12-08 | 2026-12-09 | AGUSAN DEL NORTE | ZAMBOANGA CITY | Caraga | Y | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.2) TSSR for Approval | 7/21: FOC cut 7/10 | 6/24: for checking | 6.8983 | 122.0855 | MW/FSO | 25
E86 | 2023Capsite_BrgyMalTag_Malaybalay City (Capital) | TRFS | 03. For Awarding | NOKIA | PHILTOWER | 26. ODU Pad / Electrical | NOKIA | (02) Survey | MW/FSO | 2026-10-15 | 2026-06-29 | 30 | 2026-06-24 | 2026-08-27 | 2026-10-18 | ZAMBOANGA DEL SUR | MALAYBALAY CITY (CAPITAL) | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | DEC | Q4 | MAY | Q2 | (06.1) Brgy Applied | 6/20: RFI with Perm | 6/15: MW dish installed | 8.1435 | 125.1368 | MW/FSO | 24
B187 | 2021CapSite_BrgyKawLib_Butuan City (Capital) | TSSR | 03. For Awarding | ERICSSON | ALLIANCE | 20. Excavation | HT | (05) Permitting | Fiber Extension | 2026-05-07 | 2026-06-07 | 48 | 2026-03-09 | 2026-06-08 | 2026-01-28 | MISAMIS ORIENTAL | BUTUAN CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 6/18: Permanent Po | 12/10: no pole yet | 8.9283 | 125.5445 | Fiber Extension | 23
D856 | 2022Capsite_BrgyLunBag_Zamboanga City | Awarded | 07. Site Survey | ERICSSON | UNITY | 22. Rebar Installation | ZTE | (05) Permitting | MW/FSO | 2026-10-24 | 2026-07-06 | 89 | 2026-11-25 | 2026-09-25 | 2026-08-19 | ZAMBOANGA DEL SUR | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/21: FOC cut 7/10 | 9/19: Awaiting tower | 6.9004 | 122.0767 | MW/FSO | 25
L583 | 2023Capsite_BrgyKawNal_Lamitan City (Capital) | For Awarding | 14. LC Applied | ERICSSON | FRONTIER | 24. Backfilling | na | (02) Survey | Fiber Extension | 2026-09-20 | 2026-04-18 | 66 | 2026-04-22 | 2026-08-28 | 2026-05-14 | ZAMBOANGA DEL SUR | LAMITAN CITY (CAPITAL) | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 7/05: Integration complete | 9/19: Awaiting tower | 6.659 | 122.1226 | Fiber Extension | 24
K601 | 2022CDNPH_BrgyLibBal_Marawi City (Capital) | LGU Permitting | 14. LC Applied | ERICSSON | UNITY | 26. ODU Pad / Electrical | HT | (00) Not Started | MW | 2026-08-04 | 2026-09-01 | 85 | 2026-06-22 | 2026-11-28 | 2026-02-21 | LANAO DEL SUR | MARAWI CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.2) Brgy Secured | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 7.9999 | 124.2601 | MW | 33
A450 | 2023T8_RgPM_BrgyLibSig_Butuan City (Capital) | For Awarding | 03. For Awarding | ERICSSON | PHILTOWER | 20. Excavation | HUAXIN | (02) Survey | MW/FSO | 2026-09-05 | 2026-12-14 | 102 | 2026-06-03 | 2026-01-21 | 2026-04-30 | SULU | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/20: RFI with Perm | 10/17: Pending site | 8.9636 | 125.5304 | MW/FSO | 25
G608 | 2021CapSite_BrgyCabBag_Malaybalay City (Capital) | LGU Permitting | 36. TRFS | NOKIA | EDOTCO | 24. Backfilling | JISEDAI | (06) RTB (FOC/AN/Pending) | MW | 2026-03-08 | 2026-12-06 | 85 | 2026-01-28 | 2026-02-16 | 2026-06-08 | LANAO DEL NORTE | MALAYBALAY CITY (CAPITAL) | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (06.2) Brgy Secured | 6/30: Fiber link verified | 7/02: FOC splicing ongoing | 8.1858 | 125.1102 | MW | 23
C206 | 2022Capsite_BrgyTagSan_Zamboanga City | TRFS | 03. For Awarding | ERICSSON | LDIC | 23. Concrete Pouring | ZTE | (01) Precon/ Eng'g Hold | MW | 2026-12-17 | 2026-10-12 | 95 | 2026-01-03 | 2026-09-02 | 2026-03-23 | LANAO DEL NORTE | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | FEB | Q1 | (05.2) TSSR for Approval | 6/28: For MOS. Pull | 10/17: Pending site | 6.8958 | 122.0495 | MW | 27
K685 | 2023M2SC2_BrgyBurLun_Valencia City | RFI'd | 28. sRFI/TRS Ready | ERICSSON | FRONTIER | 18. RTB for Mobilization | TBD | (05) Permitting | MW/FSO | 2026-05-25 | 2026-12-12 | 108 | 2026-11-02 | 2026-07-21 | 2026-10-01 | LANAO DEL NORTE | VALENCIA CITY | Northern Mindanao | Y | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (05.2) TSSR for Approval | 7/05: Integration complete | 9/19: Awaiting tower | 7.9125 | 125.0725 | MW/FSO | 23
Q183 | 2022Capsite_BrgyKawSig_General Luna | TRFS | 18. RTB for Mobilization | NOKIA | PHILTOWER | 23. Concrete Pouring | ZTE | (01) Precon/ Eng'g Hold | MW | 2026-09-13 | 2026-04-07 | 11 | 2026-04-19 | 2026-06-04 | 2026-08-11 | LANAO DEL SUR | GENERAL LUNA | BARMM | Y | TowerCo (Macro) - BTS | Yes | SEP | Q3 | APR | Q2 | (02) Ongoing Survey | 7/05: Integration complete | 01 Precon/ Eng'g Hold | 9.7508 | 126.1374 | MW | 23
E397 | 2020M2SC2_BrgyTagBal_Zamboanga City | s-RFI | 03. For Awarding | ERICSSON | FRONTIER | 24. Backfilling | ZTE | (05) Permitting | Fiber Extension | 2026-06-27 | 2026-12-18 | 25 | 2026-12-02 | 2026-07-27 | 2026-01-07 | ZAMBOANGA DEL NORTE | ZAMBOANGA CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (04) For Re-award | 6/12: Awaiting transmission hookup | 9/19: Awaiting tower | 6.9003 | 122.0736 | Fiber Extension | 27
A498 | 2023M2SC2_BrgySigMal_Iligan City | Awarded | 27. sRFI Pending Pole | ERICSSON | FRONTIER | 26. ODU Pad / Electrical | ZTE | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-09-15 | 2026-07-10 | 121 | 2026-12-31 | 2026-06-21 | 2026-10-01 | ZAMBOANGA DEL SUR | ILIGAN CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 6/15: MW dish installed | 8.2185 | 124.2169 | AN + LEOSAT | 25
G892 | 2021CapSite_BrgyMalKaw_Davao City | LGU Permitting | 14. LC Applied | ERICSSON | PHILTOWER | 24. Backfilling | COMTEL | (05) Permitting | Fiber Extension | 2026-08-26 | 2026-05-25 | 10 | 2026-03-04 | 2026-09-08 | 2026-08-24 | BUKIDNON | DAVAO CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 06 RTB (FOC/ AN/ ... | 7.2274 | 125.4273 | Fiber Extension | 25
F692 | 2020CDNPH_BrgyCabTag_Valencia City | TSSR | 03. For Awarding | ERICSSON | FRONTIER | 19. Site Clearing | COMTEL | (02) Survey | MW/FSO | 2026-11-22 | 2026-01-19 | 28 | 2026-07-02 | 2026-01-19 | 2026-09-30 | SURIGAO DEL NORTE | VALENCIA CITY | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (05.3) TSSR Approved | 7/05: Integration complete | 06 RTB (FOC/ AN/ ... | 7.9309 | 125.0683 | MW/FSO | 23
O149 | 2023M2SC2_BrgyTagKaw_Zamboanga City | RTB'd | 03. For Awarding | NOKIA | FRONTIER | 18. RTB for Mobilization | na | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-01-21 | 2026-02-09 | 83 | 2026-07-10 | 2026-01-20 | 2026-03-17 | BASILAN | ZAMBOANGA CITY | BARMM | N | TowerCo (Macro) - BTS | Yes | SEP | Q3 | N/A | N/A | (05.3) TSSR Approved | 7/18: Power energized | 5/20: LOS check passed | 6.9214 | 122.1186 | AN + LEOSAT | 23
T768 | 2023CDNPH_BrgyBalMal_Davao City | LGU Permitting | 03. For Awarding | ERICSSON | UNITY | 26. ODU Pad / Electrical | ZTE | (05) Permitting | Fiber Extension | 2026-04-09 | 2026-10-20 | 66 | 2026-06-05 | 2026-11-12 | 2026-09-21 | ZAMBOANGA DEL NORTE | DAVAO CITY | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/28: For MOS. Pull | 6/24: for checking | 7.2187 | 125.4567 | Fiber Extension | 25
D779 | 2022M2SC2_BrgyBurSig_Zamboanga City | For Awarding | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 19. Site Clearing | FADI | (01) Precon/ Eng'g Hold | MW/FSO | 2026-05-20 | 2026-01-03 | 104 | 2026-04-17 | 2026-01-10 | 2026-08-01 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.939 | 122.1018 | MW/FSO | 27
T326 | 2021CapSite_BrgyLunMal_Butuan City (Capital) | For Awarding | 30. RFI/TRS Ready | ERICSSON | FRONTIER | 22. Rebar Installation | COMTEL | (06) RTB (FOC/AN/Pending) | AN + LEOSAT | 2026-11-22 | 2026-11-01 | 84 | 2026-10-05 | 2026-07-19 | 2026-09-01 | BASILAN | BUTUAN CITY (CAPITAL) | BARMM | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01.1) TBD | 6/12: Awaiting transmission hookup | 10/17: Pending site | 8.9315 | 125.5456 | AN + LEOSAT | 24
C474 | 2021M2SC2_BrgyCabBur_Cagayan De Oro City (Capital) | LGU Permitting | 32. Ongoing Integration | ERICSSON | FRONTIER | 19. Site Clearing | ZTE | (05) Permitting | MW/FSO | 2026-02-12 | 2026-04-17 | 135 | 2026-07-09 | 2026-06-05 | 2026-05-30 | TAWI-TAWI | CAGAYAN DE ORO CITY (CAPITAL) | BARMM | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/12: Awaiting transmission hookup | 06 RTB (FOC/ AN/ ... | 8.4596 | 124.6238 | MW/FSO | 27
C640 | 2024CDNPH_BrgyBalSig_Zamboanga City | LGU Permitting | 18. RTB for Mobilization | ERICSSON | PHILTOWER | 23. Concrete Pouring | JISEDAI | (05) Permitting | MW | 2026-07-13 | 2026-11-07 | 31 | 2026-02-19 | 2026-07-22 | 2026-04-22 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | Yes | MAR | Q1 | N/A | N/A | (06.2) Brgy Secured | 6/18: Permanent Po | 7/02: FOC splicing ongoing | 6.9366 | 122.0438 | MW | 33
P753 | 2024M2SC2_BrgyBalKaw_Zamboanga City | RTB'd | 03. For Awarding | ERICSSON | LDIC | 22. Rebar Installation | HT | (02) Survey | Fiber Extension | 2026-12-07 | 2026-12-18 | 81 | 2026-09-15 | 2026-10-02 | 2026-09-30 | MISAMIS ORIENTAL | ZAMBOANGA CITY | Northern Mindanao | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (01) For Awarding | 6/30: Fiber link verified | 10/17: Pending site | 6.9465 | 122.0771 | Fiber Extension | 23
K161 | 2023Capsite_BrgyTagMal_Iligan City | Awarded | 14. LC Applied | ERICSSON | UNITY | 26. ODU Pad / Electrical | ZTE | (05) Permitting | AN + LEOSAT | 2026-08-03 | 2026-07-30 | 48 | 2026-11-22 | 2026-01-15 | 2026-11-13 | AGUSAN DEL NORTE | ILIGAN CITY | Caraga | N | TowerCo (Macro) - BTS | Yes | FEB | Q1 | N/A | N/A | (05.3) TSSR Approved | 7/20: RfId site 7/15 | 6/24: for checking | 8.2384 | 124.2412 | AN + LEOSAT | 25
Q750 | 2020M2SC2_BrgyKawLib_Iligan City | RFI'd | 03. For Awarding | ERICSSON | PHILTOWER | 23. Concrete Pouring | ZTE | (02) Survey | Fiber Extension | 2026-11-04 | 2026-12-01 | 99 | 2026-10-10 | 2026-09-19 | 2026-04-09 | MISAMIS ORIENTAL | ILIGAN CITY | Northern Mindanao | N | TowerCo (Micro) - BTS | No | N/A | N/A | N/A | N/A | (05.2) TSSR for Approval | 5/12: CR applied, AP | 9/19: Awaiting tower | 8.2148 | 124.2341 | Fiber Extension | 27
O944 | 2022Capsite_BrgyBagTag_Claveria | TRFS | 03. For Awarding | ERICSSON | FRONTIER | 23. Concrete Pouring | COMTEL | (01) Precon/ Eng'g Hold | AN + LEOSAT | 2026-05-04 | 2026-04-01 | 118 | 2026-09-14 | 2026-11-25 | 2026-02-26 | ZAMBOANGA DEL NORTE | CLAVERIA | Zamboanga Peninsula | N | TowerCo (Macro) - BTS | Yes | AUG | Q3 | APR | Q2 | (05.2) TSSR for Approval | 6/12: Awaiting transmission hookup | 6/15: MW dish installed | 8.6181 | 124.9276 | AN + LEOSAT | 33
O986 | 2020CapSite_BrgyBurMal_Balingasag | RFI'd | 03. For Awarding | NOKIA | ISON | 18. RTB for Mobilization | FADI | (00) Not Started | AN + LEOSAT | 2026-05-14 | 2026-10-03 | 30 | 2026-11-07 | 2026-11-28 | 2026-10-01 | AGUSAN DEL SUR | BALINGASAG | Caraga | N | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (06.1) Brgy Applied | 6/18: Permanent Po | 3/31: Brgy Permit S | 8.7267 | 124.7349 | AN + LEOSAT | 33
P408 | 2022CapSite_BrgyBalBur_Ipil (Capital) | RTB'd | 03. For Awarding | ERICSSON | ALLIANCE | 19. Site Clearing | TBD | (02) Survey | Fiber Extension | 2026-03-28 | 2026-07-07 | 105 | 2026-12-03 | 2026-06-23 | 2026-03-14 | LANAO DEL NORTE | IPIL (CAPITAL) | Northern Mindanao | N | TowerCo (Micro) - BTS | Yes | MAR | Q1 | N/A | N/A | (06.1) Brgy Applied | 5/12: CR applied, AP | 3/31: Brgy Permit S | 7.7508 | 122.6147 | Fiber Extension | 23
B470 | 2021M2SC2_BrgySigTag_Zamboanga City | s-RFI & TRS Ready | 27. sRFI Pending Pole | ERICSSON | UNITY | 22. Rebar Installation | COMTEL | (02) Survey | MW/FSO | 2026-11-01 | 2026-01-19 | 35 | 2026-03-17 | 2026-09-25 | 2026-05-28 | ZAMBOANGA SIBUGAY | ZAMBOANGA CITY | Zamboanga Peninsula | Y | TowerCo (Macro) - BTS | No | N/A | N/A | N/A | N/A | (02) Ongoing Survey | 7/18: Power energized | 7/02: FOC splicing ongoing | 6.9584 | 122.0549 | MW/FSO | 24